## Slide 1: Maintenance and Repair Methodology
MSC ships follow a commercial maritime model for maintenance and repair with small crews, relying primarily on industrial assistance
Ships are classed by the American Bureau of Shipping (ABS) and certificated by the US Coast Guard
Ships have a 5-year Special Survey Cycle, Dry docking (or UWILD) the ship 2x in 5 years
Typical MSC Maintenance Schedule
  Quarterly Voyage Repair (VR) periods
  Alternating Annual Regular Overhaul/Dry-Docking and Mid-Term Availabilities
MSC has an aging fleet, with vessels operating past the design service life. An aging fleet it introduces many issues that are not typical with many commercial vessels. This includes material obsolescence, corrosion, fatigue, and having machinery hours past the OEM technical manuals.

## Slide 2: T-AO Gap Mitigation
Inventory after POM25 T-AO 205 Deferments (gray area)
T-AO 187 Extensions
Chart: 
| FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY36 | FY37 | FY38 | FY39 | FY40 | FY41 | FY42
Excursion | 15 | 17 | 17 | 15 | 16 | 17 | 18 | 17 | 18 | 19 | 19 | 17 | 17 | 17 | 17 | 17 | 18 | 19 | 20 | 20
LEN | 1 | 1 | 1 | 1
HUM | 1 | 1 | 1
GRU | 1 | 1
KAN | 1 | 1
GUAD | 1 | 1
YUK | 1 | 1 | 1
LAR | 1 | 1
187 Extended | 16 | 18 | 19 | 18 | 17 | 18 | 19 | 19 | 19 | 19 | 20 | 18 | 18 | 18 | 18 | 17 | 18 | 19 | 20 | 20
KANAWHA
YUKON
GUADALUPE
LARAMIE
GRUMMAN
LENTHALL
HUMPHREYS
    T-AOs and T-AOEs Ready for Tasking
Ship | Decom Date Shift | INACT Age
Lenthall | FY23 to FY27 | 41
Grumman | FY25 to FY28 | 39
Humphreys | FY26 to FY29 | 43
Kanawha | FY29 to FY31 | 40
Guadalupe | FY30 to FY32 | 42
Yukon | FY33 to FY36 | 43
Laramie | FY35 to FY38 | 44
    OPNAV Proposal with Slower 205 Class Procurement
    187 Class ESL 35 Years

## Slide 3: Other Life Extension Plans
CUI
Ship | Decom Date | Age
MT Whitney | FY26 to FY39 | 68
USNS Emory S. Land | FY31 to FY33 | 54
USNS Frank Cable | FY32 to FY34 | 55
USNS CATAWBA | FY24 to FY25 | 45
USNS GRASP | FY24 to FY26 | 41
USNS ZEUS | FY27 to FY31 | 47

## Slide 4: T-AO Fg Model

## Slide 5
Our standard logistics ship overhaul cycle includes:
Dry docking Availabilities every 2.5 years (60 - 120 days)
Mid-term Availabilities every 18 months (45 - 60 days)
Quarterly Voyage Repair periods (2 weeks pier-side)
Inspections and Surveys at regular intervals:
Continuous ABS surveys (5-year cycle)
Annual USCG inspections
Ship Material Assessment and Readiness Testing (every 5 years by MSC engineers)
Annual Safety Management and Environmental Audits
Continuous maintenance pier-side whenever practical
Note: High-Speed Vessels require annual dry-docking
UNCLASSIFIED
Maintenance Plans
(Government-Owned/Government-Operated)

## Slide 6: Maintenance Planning
Identify Issues Early
  Instituted government material condition surveys SMART, PEVI, VSA, Corrosion and Load-line assessments, Material Readiness Inspections
    SMART/VSA – Testing and evaluation of machinery and systems
    PEVI – Static examination of the vessel by the Principal Port Engineer to evaluate hull, structures, coating condition, main and auxiliary spaces.
  3rd party oversight ABS Annuals and USCG COI
Advanced Planning and Package Development
  MSC goal is to have work package assembly and material order requests for the next 3 to 5 years for all major availabilities.
  Package includes standard work items, cross class and class standard work items.
    SWI/CCSI/CSIs constitute 80% of the work package.
    Repair items constitute 15% of the work package and these are items that are identified through ship’s force and material assessments. MSC is in the process of creating template style repair items so that they are easily biddable and are similar across the fleet.
    Trans-Alts or fleet modernization make up the remaining 5%.
    Class standard work items and template repair items are evaluated after repair periods and lessons learn are incorporated into the work item and updated in the SAMM library.

## Slide 7: Planned Maintenance
CCSI are fleet wide standardized items, CSI are class specific items;
  Ensure fleet/class wide consistency
  Tracking maintenance costs
  Improve technical rigor, ensure technical requirements are met
  Apply Lessons Learned
  Changes are tracked via the Standard Change Review Board process with concurrence from N7, Legal, N10
  Reduces review time
  Provides Industrial base with repeatable requirements
  Approximately 90 CCSI and estimate of 100 CSI per class
  Less CFRs and CCOs = cost savings
Planned Maintenance
Availabilities:
VR, MTA, ROH
OEM Maintenance Schedule, CCSI/CSI
Feedback into CCSI/CSI
Notes: USNS LARAMIE (T-AO 203)
43 Work Requests Entered
890 SQFT of Suspect Plating
50,850 SQFT Coating Maintenance

## Slide 8: CSI/CCSI Usage vs Change Orders
Use of CCSI/CSI continues to drive down Change Orders for PMIA items

## Slide 9: Integrated Requirements in SAMM
OPR: N7
PMIA
VRR
T-ALT
Deferred Work
(lower risk)
Work Package
(higher risk)
SFWL
POM input
Work Req.
PMSF
OEM/TWH
OEM/TWH
Regulatory
Condition Monitoring
Regulatory/ PMP
Self Directed
Material Assessments
ABS COC/SC
Closed Loop Assessments
Ship Generated
PPE Generated
Mission/ Sponsor
Safety/ Regulatory
OERA
CCSI
CSI
T-ALTs
Repairs
Command Directed
Command Directed
C/E
Repair Officer
PPE
85%
10%
5%
Risk Assessed
Life Cycle Plan
Notes: As a ship ages, maintenance, repair and alterations requirements continue to be generated from a variety of sources and analyses of ship condition. Risk is continuously assessed and the higher & med risk required M&R are completed by S/F (SAMM req maintenance, SF Repair) or contract support including Ship Repair Facilities (Repair & Alterations) and OEMs. Higher risk alteration requirements are submitted as TRANSALT Requests for PM Approval then designed and integrated into work packages. Lower risk items that cannot be completed due to budget, resource availability, etc. are deferred and submitted for POM input.
Focus on budgeting VS technical risk and Unfunded M&R

## Slide 10: T-AO Fg Model and Maintenance Planning
OPR N7
Acquisition Timelines:
Deliberate ;
Not responsive
-381
-296
-228
-212
-60
0
-370
Advanced Planning Letter
LLTM GFM
Job Cut-off
Planning Con / Ship Check/PEVI
Mission /CASREP Job C/O
Solicitation
Award
Start
-356
Award
Planning Letter
Final Package
Solicitation
Start
0
-30
-90
-115
-150
Planning/package Generation
Package locked
Execution
MTA
ROH
VR Period
Planning/package Generation
Package
locked
Execution
Overlapping Planning Cycles
Notes: Need the words that were spoken during brief in here. Admirals comment
+++++++++++++++++
This is a graphical portrayal of the Fg Model.
Starting left to right on a monthly basis to show the Fg Model over the course of 5 years.
The Green bars indicate a Mid Term Availability (MTA), the Light Blue indicate a Regular Overhaul (ROH)
The light Gray bars are preplanned training/ Ready for Sea periods
The Dark Blue bars indicate VR periods.
The progression of the maintenance periods show some of the variability of the schedule.
Also notice the overlapping Planning Cycles. We are planning at least one availability while another is going on. The presumption is that the intermittent one is executed and those job are completed prior to next one
Shown below the table with the Green and Bluecircles are the scaled planning and contracting POAMs for MTA/ROHs and VR periods respectively.
  Please notice the timelines involved. The planning for one Avail occurs while the ship is conducting another.
  There are also presumptions made that the work that is expected to be completed during the intervening VR periods will be completed and not put into the Maintenance package.
  Or a final assessment of the material condition of something for a work item may be evaluated to determine the scope of that work item for planning prior to releasing the solicitation.
When a ship suffers a Casualty and pulls into port for emergent maintenance, intuitively one may think that this could suffice for a VR period, however due to Contracting restrictions and no planning, this maintenance will be limited solely to repair the casualty.
  MSC generally does not have the flexibility to conduct additional maintenance during that period.
If one of these maintenance period is cancelled that planned work will then become growth onto the existing package eating the planned growth margin expected on open and inspect items planned during the avail.
This overall growth may be too much for the industrial capacity to absorb and result in extensions on the avail.

## Slide 11: Shipyard Execution

## Slide 12: Execution Support
Execution meetings and deliverables
  Prior to the start of the availability
    A-40 Contract Award Meeting/Pre-Availability Execution Discussion with the SMT, Repair Yard, Pre-Arrival Conference
  During execution
    Daily production meeting, weekly progress meeting, weekly execution meeting with Program, Engineering, ABS, Contracting.
  Post Overhaul
    Post Overhaul Analysis Report, Ready For Tasking Letter (ROH), Lesson Learned Conference with OMT
Project Planning and Monitoring
  All government contractors shall provide production schedules to the gaining repair yard 7 days prior to the vessel arrival to incorporate into the integrated master schedule.
  Shipyard support work item, the government is developing a standard shipyard support work item for all government sub contractors.
Condition Found Reports and Contract Change Order (CCO) Support
  Complete all Regulatory structural and SOLAS Surveys within the first couple of weeks.
  Submit Condition Found Reports as quickly as possible, send heads up to Port Engineer
  Repair Yard shall respond to the CCO with a quote within 3 days of receipt.
  Each CCO shall state if the additional work will result in a change in the schedule.
COMMUNICATION IS THE KEY TO SUCCESS

## Slide 13: Successful OEM /MSC Relationship
Reoccurring and Open communication between OEM and MSC:
  Reoccurring Meeting to review
    Market research request (part/service availability, T-ALT Scope, etc.)
    Review status of awarded contracts (DO, TO, T-ALTs, etc.)
    Discuss any MSC issues
    Identify upcoming obsolescence
    Any OEM questions, concerns, or updates
  MSC provides the following in an effort to be more transparent in order for OEM to be more prepared and efficient:
    MSC Availability Schedule (Fleet Maintenance Schedule Center – FSC)
    Forecasted OEM Preventive Maintenance
    Customer Feedback
  OEM provides the following in an effort to help MSC improve and meet mission to maintain national security:
    Obsolescence Forecast
    Industrial Knowledge
    Industrial Feedback
COMMUNICATION IS THE KEY TO SUCCESS