## Industry
Battle Group | Ship | Hull | Event Type | Status | Start Date | End Date | Duration (D) | Updated Date | Repair Activity
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2023-03-24 | 2023-04-06 | 14 | 2023-01-08 |  | DELIVERY | Scheduled date for delivery of a new ship
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2023-03-28 | 2023-04-14 | 18 | 2022-12-28 | C7F | INAC | Projected date for a ship to go off-line
PM8 | NEWPORT | T-EPF 12 | VR (Z) MSC | ACTIVE | 2023-04-01 | 2023-04-20 | 20 | 2023-01-26 | C2F | MTA | MidTerm Availability: middle ground between BIG work (like in an ROH/DD) and the small work (like in a VR)
PM1 | JOHN LENTHALL | T-AO 189 | MTA (MSC) | CANCELED | 2023-04-03 | 2023-05-22 | 50 | 2022-05-26 | C2F | DELIVERY | Scheduled date for delivery of a new ship
PM3 | 2ND LT JOHN P BOBO | T-AK 3008 | ROH / DD (MSC) | ACTIVE | 2023-04-06 | 2023-08-05 | 122 | 2023-01-12 | CTF 80 | INAC | Projected date for a ship to go off-line
PM2 | PATHFINDER | T-AGS 60 | VR (Z) MSC | ACTIVE | 2023-04-06 | 2023-05-02 | 27 | 2023-03-20 | Cardiff USA Port Canaveral | MTA | MidTerm Availability: middle ground between BIG work (like in an ROH/DD) and the small work (like in a VR)
PM1 | JOHN ERICSSON | T-AO 194 | MTA (MSC) | ACTIVE | 2023-04-10 | 2023-07-09 | 91 | 2023-03-03 | SEMBAWANG SHIPYARD | ROH | Regular OverHaul
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | ROH / DD (MSC) | ACTIVE | 2023-04-10 | 2023-07-05 | 87 | 2023-02-24 | C6F | DD | Dry Dock
PM2 | WATERS | T-AGS 45 | VR (Z) MSC | ACTIVE | 2023-04-14 | 2023-05-15 | 32 | 2023-03-02 | Cardiff USA Port Canaveral | VR | Voyage Repair (might also be referred to as VRA (Voyage Repair Availability))
PM6 | ROBERT E PEARY | T-AKE 5 | ROH / DD (MSC) | ACTIVE | 2023-04-17 | 2023-07-16 | 91 | 2023-03-02 | Alabama Shipyard LLC
PM8 | MILLINOCKET | T-EPF 3 | MTA (MSC) | ACTIVE | 2023-04-17 | 2023-06-15 | 60 | 2023-02-03 | SUBIC BAY
PM6 | MATTHEW PERRY | T-AKE 9 | ROH (MSC) | ACTIVE | 2023-04-17 | 2023-05-31 | 45 | 2023-03-16 | SEMBAWANG SHIPYARD
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2023-04-18 | 2023-05-01 | 14 | 2022-06-15 | C7F
PM8 | CARSON CITY | T-EPF 7 | ROH / DD (MSC) | ACTIVE | 2023-04-20 | 2023-06-21 | 63 | 2022-12-09 | C6F
PM6 | WILLIAM MCLEAN | T-AKE 12 | MTA (MSC) | ACTIVE | 2023-04-24 | 2023-06-07 | 45 | 2023-02-09 | Alabama Shipyard LLC
PM8 | APALACHICOLA | T-EPF 13 | VR (Z) MSC | ACTIVE | 2023-04-24 | 2023-05-14 | 21 | 2023-01-26 | JEB/LCRK
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2023-04-30 | 2023-05-14 | 15 | 2022-12-21 | C5F
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2023-05-01 | 2023-05-15 | 15 | 2023-03-16
PM3 | MONTFORD POINT | T-ESD 1 | ROH / DD (MSC) | ACTIVE | 2023-05-01 | 2023-06-30 | 61 | 2019-10-24
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | ACTIVE | 2023-05-02 | 2023-05-14 | 13 | 2023-03-08 | C3F
PM8 | PUERTO RICO | T-EPF 11 | VR (Z) MSC | ACTIVE | 2023-05-06 | 2023-05-27 | 22 | 2022-11-30 | C7F
PM8 | CITY OF BISMARCK | T-EPF 9 | VR (Z) MSC | ACTIVE | 2023-05-08 | 2023-05-29 | 22 | 2023-02-22 | C3F
PM2 | MARIE THARP | T-AGS 66 | VR (Z) MSC | ACTIVE | 2023-05-08 | 2023-06-07 | 31 | 2023-02-10 | C6F
PM6 | CHARLES DREW | T-AKE 10 | ROH (MSC) | ACTIVE | 2023-05-08 | 2023-06-22 | 46 | 2023-03-16 | THAILAND
PM2 | ABLE | T-AGOS 20 | VR (Z) MSC | ACTIVE | 2023-05-09 | 2023-06-06 | 29 | 2023-01-10
PM1 | KANAWHA | T-AO 196 | ROH / DD (MSC) | ACTIVE | 2023-05-14 | 2023-08-12 | 91 | 2022-11-10 | DETYENS
PM8 | CHOCTAW COUNTY | T-EPF 2 | ROH / DD (MSC) | CANCELED | 2023-05-15 | 2023-07-28 | 75 | 2023-02-17 | C5F
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2023-05-16 | 2023-05-29 | 14 | 2021-05-26 | C6F
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | ACTIVE | 2023-05-16 | 2023-06-01 | 17 | 2023-01-26 | C3F
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | ACTIVE | 2023-05-16 | 2023-06-06 | 22 | 2023-02-24
PM2 | EAGLEVIEW | T-AGSE 3 | MTA (MSC) | ACTIVE | 2023-05-17 | 2023-06-29 | 44 | 2021-12-14 | C3F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2023-05-17 | 2023-06-07 | 22 | 2022-11-17
PM1 | PECOS | T-AO 197 | ROH / DD (MSC) | ACTIVE | 2023-05-19 | 2023-09-05 | 110 | 2023-01-03
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2023-05-23 | 2023-06-06 | 15 | 2023-01-26 | C7F
PM6 | ALAN SHEPARD | T-AKE 3 | MTA (MSC) | ACTIVE | 2023-05-28 | 2023-07-11 | 45 | 2023-02-02 | C5F
PM6 | WALLY SCHIRRA | T-AKE 8 | MTA (MSC) | ACTIVE | 2023-06-01 | 2023-07-15 | 45 | 2022-11-09 | C7F
PM8 | BURLINGTON | T-EPF 10 | VR (Z) MSC | ACTIVE | 2023-06-01 | 2023-06-23 | 23 | 2022-12-16 | MAYPORT
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | ACTIVE | 2023-06-02 | 2023-06-18 | 17 | 2023-02-14 | C7F
PM4 | EMORY S LAND | AS 39 | VR (Z) MSC | ACTIVE | 2023-06-04 | 2023-07-04 | 31 | 2022-09-26 | NOT ASSGINED
PM1 | HENRY J KAISER | T-AO 187 | VR (Z) MSC | ACTIVE | 2023-06-05 | 2023-06-18 | 14 | 2021-06-01 | C3F
PM6 | LEWIS AND CLARK | T-AKE 1 | VR (Z) MSC | ACTIVE | 2023-06-06 | 2023-07-03 | 28 | 2021-08-17 | C7F
PM3 | LEWIS B PULLER | ESB 3 | ROH (MSC) | ACTIVE | 2023-06-11 | 2023-08-10 | 61 | 2023-01-08 | C5F
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | CANCELED | 2023-06-11 | 2023-06-24 | 14 | 2023-01-20
PM1 | WALTER S DIEHL | T-AO 193 | VR (Z) MSC | DEFERRED | 2023-06-12 | 2023-06-26 | 15 | 2022-10-06 | C2F
PM8 | BRUNSWICK | T-EPF 6 | VR (Z) MSC | CANCELED | 2023-06-12 | 2023-07-03 | 22 | 2022-03-28 | C7F
PM1 | JOHN LENTHALL | T-AO 189 | DECOM AVAIL (MSC) | ACTIVE | 2023-06-13 | 2023-07-27 | 45 | 2022-08-24
PM1 | JOHN LENTHALL | T-AO 189 | MTA (MSC) | ACTIVE | 2023-06-13 | 2023-07-27 | 45 | 2023-02-09 | CTF 80
PM6 | SACAGAWEA | T-AKE 2 | ROH / DD (MSC) | ACTIVE | 2023-06-15 | 2023-10-15 | 123 | 2023-03-02 | CTF 80
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2023-06-15 | 2023-07-01 | 17 | 2023-01-26 | C7F
PM6 | ARCTIC | T-AOE 8 | MTA (MSC) | ACTIVE | 2023-06-16 | 2023-08-26 | 72 | 2023-01-20 | CTF 80
PM2 | IMPECCABLE | T-AGOS 23 | ROH (MSC) | ACTIVE | 2023-06-16 | 2023-08-16 | 62 | 2023-03-09 | C7F
PM2 | BOWDITCH | T-AGS 62 | VR (Z) MSC | ACTIVE | 2023-06-23 | 2023-07-19 | 27 | 2023-02-10
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | CANCELED | 2023-06-26 | 2023-07-17 | 22 | 2023-02-21
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | ACTIVE | 2023-07-01 | 2023-07-15 | 15 | 2021-08-19
PM8 | YUMA | T-EPF 8 | VR (Z) MSC | ACTIVE | 2023-07-01 | 2023-07-22 | 22 | 2023-03-20 | C6F
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | CANCELED | 2023-07-01 | 2023-07-15 | 15 | 2023-01-20
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2023-07-03 | 2023-07-17 | 15 | 2023-01-11 | C6F
PM1 | LEROY GRUMMAN | T-AO 195 | VR (Z) MSC | ACTIVE | 2023-07-03 | 2023-07-17 | 15 | 2022-07-29 | C6F
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2023-07-03 | 2023-07-18 | 16 | 2021-08-19
PM1 | GUADALUPE | T-AO 200 | MTA (MSC) | ACTIVE | 2023-07-10 | 2023-09-07 | 60 | 2022-08-12 | C3F
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | ACTIVE | 2023-07-10 | 2023-07-24 | 15 | 2021-06-01 | C7F
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | ACTIVE | 2023-07-10 | 2023-07-31 | 22 | 2021-11-08 | C6F
PM8 | CITY OF BISMARCK | T-EPF 9 | VR (Z) MSC | ACTIVE | 2023-07-10 | 2023-07-31 | 22 | 2021-09-29
PM8 | NEWPORT | T-EPF 12 | ROH / DD (MSC) | ACTIVE | 2023-07-10 | 2023-09-07 | 60 | 2023-02-10 | CTF 80
PM3 | SGT WILLIAM R BUTTON | T-AK 3012 | ROH / DD (MSC) | ACTIVE | 2023-07-10 | 2023-11-06 | 120 | 2022-11-17
PM8 | FALL RIVER | T-EPF 4 | VR (Z) MSC | ACTIVE | 2023-07-10 | 2023-09-07 | 60 | 2022-08-03 | C3F
PM4 | MERCY | T-AH 19 | VR (Z) MSC | ACTIVE | 2023-07-10 | 2023-08-11 | 33 | 2022-08-23
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2023-07-12 | 2023-07-25 | 14 | 2021-05-26 | C3F
PM2 | LOYAL | T-AGOS 22 | ROH (MSC) | ACTIVE | 2023-07-13 | 2023-09-13 | 63 | 2023-01-10 | C7F
PM1 | PATUXENT | T-AO 201 | ROH / DD (MSC) | ACTIVE | 2023-07-14 | 2023-10-05 | 84 | 2023-02-07
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | MTA (MSC) | ACTIVE | 2023-07-14 | 2023-08-27 | 45 | 2023-01-20 | C3F
PM1 | LARAMIE | T-AO 203 | VR (Z) MSC | ACTIVE | 2023-07-17 | 2023-07-31 | 15 | 2023-03-17 | C6F
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2023-07-21 | 2023-08-03 | 14 | 2023-01-26 | C7F
PM6 | AMELIA EARHART | T-AKE 6 | ROH / DD (MSC) | ACTIVE | 2023-07-30 | 2023-10-27 | 90 | 2023-01-13 | C5F
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | ACTIVE | 2023-07-31 | 2023-09-02 | 34 | 2023-03-08 | C3F
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2023-07-31 | 2023-08-15 | 16 | 2023-02-10 | CTF 80
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | ACTIVE | 2023-07-31 | 2023-08-12 | 13 | 2023-01-20 | C3F
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2023-08-01 | 2023-08-30 | 30 | 2022-06-15
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2023-08-07 | 2023-08-21 | 15 | 2022-07-29 | C6F
PM2 | BRUCE C HEEZEN | T-AGS 64 | VR (Z) MSC | ACTIVE | 2023-08-09 | 2023-09-04 | 27 | 2023-02-10 | C6F
PM8 | PUERTO RICO | T-EPF 11 | VR (Z) MSC | ACTIVE | 2023-08-10 | 2023-08-31 | 22 | 2023-01-13 | C7F
PM8 | CODY | T-EPF 14 | PDA | ACTIVE | 2023-08-12 | 2023-09-10 | 30 | 2023-01-08 | MOBILE
PM1 | JOHN LENTHALL | T-AO 189 | VR (Z) MSC | CANCELED | 2023-08-14 | 2023-08-28 | 15 | 2022-05-12 | C2F
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2023-08-14 | 2023-08-30 | 17 | 2022-11-29 | C7F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | CANCELED | 2023-08-14 | 2023-08-28 | 15 | 2022-07-08 | CTF 80
PM2 | ZEUS | T-ARC 7 | VR (Z) MSC | ACTIVE | 2023-08-15 | 2023-08-28 | 14 | 2021-12-14
PM2 | EFFECTIVE | T-AGOS 21 | MTA (MSC) | ACTIVE | 2023-08-16 | 2023-09-30 | 46 | 2023-01-10
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2023-08-18 | 2023-09-02 | 16 | 2023-02-21 | C7F
PM8 | BURLINGTON | T-EPF 10 | VR (Z) MSC | ACTIVE | 2023-08-20 | 2023-08-30 | 11 | 2022-08-16 | Command Fourth Fleet
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | CANCELED | 2023-08-21 | 2023-09-03 | 14 | 2023-03-16 | CTF 80
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | ACTIVE | 2023-08-22 | 2023-09-07 | 17 | 2023-02-14 | C7F
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2023-08-28 | 2023-09-11 | 15 | 2023-01-26 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2023-08-28 | 2023-09-11 | 15 | 2022-11-09 | CTF 80
PM1 | BIG HORN | T-AO 198 | VR (Z) MSC | ACTIVE | 2023-08-30 | 2023-09-14 | 16 | 2022-07-28 | C7F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | MTA (MSC) | ACTIVE | 2023-09-01 | 2023-12-04 | 95 | 2022-10-27 | C2F
PM1 | JOHN LEWIS | T-AO 205 | PSA (MSC) | ACTIVE | 2023-09-01 | 2024-02-13 | 166 | 2023-01-18
PM8 | MILLINOCKET | T-EPF 3 | VR (Z) MSC | ACTIVE | 2023-09-01 | 2023-09-22 | 22 | 2022-11-30
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2023-09-02 | 2023-09-15 | 14 | 2021-05-26 | C5F
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | CANCELED | 2023-09-04 | 2023-09-18 | 15 | 2021-08-19 | C7F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2023-09-04 | 2023-09-17 | 14 | 2022-11-17
PM1 | LEROY GRUMMAN | T-AO 195 | VR (Z) MSC | ACTIVE | 2023-09-04 | 2023-09-18 | 15 | 2022-07-29 | C6F
PM2 | BLACK POWDER | T-AGSE 1 | ROH (MSC) | ACTIVE | 2023-09-04 | 2023-10-23 | 50 | 2022-11-18
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2023-09-05 | 2023-09-26 | 22 | 2023-02-21 | C6F
PM1 | WALTER S DIEHL | T-AO 193 | ROH (MSC) | DEFERRED | 2023-09-05 | 2023-11-18 | 75 | 2022-10-06 | C2F
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | ACTIVE | 2023-09-06 | 2023-09-21 | 16 | 2023-02-24 | C7F
PM8 | CARSON CITY | T-EPF 7 | VR (Z) MSC | CANCELED | 2023-09-07 | 2023-09-28 | 22 | 2022-04-08 | C6F
PM1 | PECOS | T-AO 197 | VR (Z) MSC | ACTIVE | 2023-09-11 | 2023-09-25 | 15 | 2021-06-03
PM4 | CATAWBA | T-ATF 168 | MTA (MSC) | ACTIVE | 2023-09-11 | 2023-11-09 | 60 | 2023-01-09
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2023-09-12 | 2023-09-26 | 15 | 2023-01-26 | C7F
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2023-09-14 | 2023-09-28 | 15 | 2022-11-09 | C7F
PM4 | CHEROKEE NATION | T-ATS 7 | PSA (MSC) | ACTIVE | 2023-09-14 | 2023-11-12 | 60 | 2021-04-23
PM4 | COMFORT | T-AH 20 | MTA (MSC) | ACTIVE | 2023-09-15 | 2024-01-12 | 120 | 2022-12-14
PM6 | SACAGAWEA | T-AKE 2 | VR (Z) MSC | CANCELED | 2023-09-15 | 2023-09-30 | 16 | 2023-03-23 | C7F
PM1 | JOHN ERICSSON | T-AO 194 | VR (Z) MSC | ACTIVE | 2023-09-15 | 2023-09-30 | 16 | 2022-11-08 | C7F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2023-09-17 | 2023-09-30 | 14 | 2023-01-20 | C3F
PM3 | JOHN L CANLEY | ESB 6 | PSA (MSC) | ACTIVE | 2023-09-20 | 2024-01-17 | 120 | 2023-01-10
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2023-09-23 | 2023-10-06 | 14 | 2023-03-01
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2023-10-02 | 2023-10-16 | 15 | 2023-02-16 | CTF 80
PM4 | EMORY S LAND | AS 39 | MTA (MSC) | ACTIVE | 2023-10-04 | 2024-02-05 | 125 | 2021-08-26 | C7F
PM6 | CESAR CHAVEZ | T-AKE 14 | MTA (MSC) | ACTIVE | 2023-10-04 | 2023-11-17 | 45 | 2022-03-31 | C7F
PM8 | BURLINGTON | T-EPF 10 | VR (Z) MSC | ACTIVE | 2023-10-06 | 2023-10-27 | 22 | 2022-08-16 | JEB/LCRK
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2023-10-09 | 2023-10-23 | 15 | 2022-07-29 | C6F
PM1 | HENRY J KAISER | T-AO 187 | VR (Z) MSC | ACTIVE | 2023-10-09 | 2023-10-23 | 15 | 2021-06-01 | C3F
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2023-10-09 | 2023-10-23 | 15 | 2022-10-31 | CTF 80
PM2 | MARY SEARS | T-AGS 65 | VR (Z) MSC | ACTIVE | 2023-10-10 | 2023-11-05 | 27 | 2023-02-16 | C3F
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2023-10-10 | 2023-10-24 | 15 | 2023-01-26 | C7F
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | ACTIVE | 2023-10-10 | 2023-10-30 | 21 | 2023-02-16 | C6F
PM2 | PATHFINDER | T-AGS 60 | VR (Z) MSC | ACTIVE | 2023-10-10 | 2023-11-03 | 25 | 2023-02-10 | CTF 80
PM2 | HOWARD O LORENZEN | T-AGM 25 | VR (Z) MSC | ACTIVE | 2023-10-15 | 2023-10-29 | 15 | 2023-03-09
PM8 | YUMA | T-EPF 8 | VR (Z) MSC | ACTIVE | 2023-10-16 | 2023-11-06 | 22 | 2021-11-08 | C6F
PM2 | VICTORIOUS | T-AGOS 19 | MTA (MSC) | ACTIVE | 2023-10-16 | 2023-11-30 | 46 | 2023-01-10
PM8 | CITY OF BISMARCK | T-EPF 9 | VR (Z) MSC | ACTIVE | 2023-10-16 | 2023-12-14 | 60 | 2022-03-28
PM8 | SPEARHEAD | T-EPF 1 | VR (Z) MSC | ACTIVE | 2023-10-16 | 2023-12-14 | 60 | 2023-02-14 | Philadelphia Navy Yard
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | ACTIVE | 2023-10-16 | 2023-10-31 | 16 | 2023-01-26 | C7F
PM1 | BIG HORN | T-AO 198 | VR (Z) MSC | ACTIVE | 2023-10-17 | 2023-11-02 | 17 | 2023-01-26 | C7F
PM5 | RED CLOUD | T-AKR 313 | ROH / DD (MSC) | ACTIVE | 2023-10-17 | 2024-01-30 | 106 | 2022-11-17 | C2F
PM2 | ARROWHEAD | T-AGSE 4 | MTA (MSC) | ACTIVE | 2023-10-18 | 2023-12-02 | 46 | 2022-11-18 | C3F
PM2 | HENSON | T-AGS 63 | VR (Z) MSC | ACTIVE | 2023-10-23 | 2023-11-18 | 27 | 2023-02-10 | C7F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2023-10-24 | 2023-11-06 | 14 | 2021-05-26 | C3F
PM1 | LARAMIE | T-AO 203 | VR (Z) MSC | ACTIVE | 2023-10-30 | 2023-11-13 | 15 | 2022-07-29 | C6F
PM8 | MILLINOCKET | T-EPF 3 | VR (Z) MSC | ACTIVE | 2023-10-30 | 2023-11-20 | 22 | 2022-06-02
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2023-11-01 | 2023-11-14 | 14 | 2023-01-26 | C7F
PM4 | MOUNT WHITNEY | LCC 20 | MTA (MSC) | ACTIVE | 2023-11-01 | 2023-12-15 | 45 | 2023-02-07 | C6F
PM8 | BURLINGTON | T-EPF 10 | ROH / DD (MSC) | ACTIVE | 2023-11-01 | 2024-02-06 | 98 | 2023-01-29 | CTF 80
PM3 | MIGUEL KEITH | ESB 5 | MTA (MSC) | ACTIVE | 2023-11-04 | 2023-12-19 | 46 | 2022-10-17
PM5 | BENAVIDEZ | T-AKR 306 | ROH / DD (MSC) | DEFERRED | 2023-11-04 | 2024-01-18 | 76 | 2022-10-06
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2023-11-05 | 2023-11-18 | 14 | 2023-02-02 | C5F
PM1 | RAPPAHANNOCK | T-AO 204 | ROH (MSC) | ACTIVE | 2023-11-06 | 2024-02-14 | 101 | 2022-12-20
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2023-11-06 | 2023-11-19 | 14 | 2022-07-22 | CTF 80
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2023-11-06 | 2023-11-21 | 16 | 2021-08-19
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2023-11-06 | 2023-11-22 | 17 | 2023-01-26 | C7F
PM1 | PECOS | T-AO 197 | VR (Z) MSC | ACTIVE | 2023-11-06 | 2023-11-22 | 17 | 2023-02-14 | C7F
PM1 | LEROY GRUMMAN | T-AO 195 | VR (Z) MSC | ACTIVE | 2023-11-13 | 2023-11-24 | 12 | 2022-07-29 | NORFOLK
PM2 | ABLE | T-AGOS 20 | MTA (MSC) | ACTIVE | 2023-11-15 | 2023-12-29 | 45 | 2023-01-10
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2023-11-16 | 2023-11-29 | 14 | 2023-01-26 | C7F
PM1 | YUKON | T-AO 202 | MTA (MSC) | CANCELED | 2023-11-19 | 2023-12-23 | 35 | 2021-05-25
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | CANCELED | 2023-11-20 | 2023-12-04 | 15 | 2022-08-03
PM4 | SALVOR | T-ARS 52 | ROH / DD (MSC) | ACTIVE | 2023-11-20 | 2024-02-02 | 75 | 2023-03-23 | C7F
PM8 | CARSON CITY | T-EPF 7 | VR (Z) MSC | CANCELED | 2023-11-27 | 2023-12-18 | 22 | 2022-04-08 | C6F
PM6 | LEWIS AND CLARK | T-AKE 1 | VR (Z) MSC | ACTIVE | 2023-11-28 | 2023-12-11 | 14 | 2021-08-17 | C7F
PM8 | PUERTO RICO | T-EPF 11 | MTA (MSC) | ACTIVE | 2023-11-28 | 2024-02-10 | 75 | 2023-02-16 | C7F
PM3 | DAHL | T-AKR 312 | ROH / DD (MSC) | ACTIVE | 2023-12-01 | 2024-04-05 | 127 | 2022-05-05
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2023-12-03 | 2023-12-16 | 14 | 2023-02-02 | C5F
PM1 | JOHN LENTHALL | T-AO 189 | VR (Z) MSC | CANCELED | 2023-12-04 | 2023-12-18 | 15 | 2022-05-12 | C2F
PM1 | JOHN ERICSSON | T-AO 194 | VR (Z) MSC | ACTIVE | 2023-12-04 | 2023-12-19 | 16 | 2023-02-14 | C7F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | MTA (MSC) | ACTIVE | 2023-12-04 | 2024-01-30 | 58 | 2023-02-21
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | CANCELED | 2023-12-04 | 2023-12-18 | 15 | 2021-08-19 | C7F
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2023-12-04 | 2023-12-18 | 15 | 2022-07-29 | C6F
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2023-12-04 | 2023-12-17 | 14 | 2022-11-09 | C6F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2023-12-04 | 2023-12-17 | 14 | 2021-05-26 | CTF 80
PM1 | KANAWHA | T-AO 196 | VR (Z) MSC | ACTIVE | 2023-12-04 | 2023-12-18 | 15 | 2022-02-14 | C2F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | CANCELED | 2023-12-04 | 2023-12-22 | 19 | 2023-02-22
PM1 | BIG HORN | T-AO 198 | MTA (MSC) | ACTIVE | 2023-12-04 | 2024-02-17 | 76 | 2023-01-26
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2023-12-05 | 2023-12-19 | 15 | 2021-02-24
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2023-12-06 | 2023-12-19 | 14 | 2021-05-26 | C7F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2023-12-07 | 2023-12-20 | 14 | 2021-06-01 | C3F
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | CANCELED | 2023-12-10 | 2023-12-22 | 13 | 2023-01-10
PM4 | MOUNT WHITNEY | LCC 20 | VR (Z) MSC | ACTIVE | 2024-01-01 | 2024-01-14 | 14 | 2021-05-26 | C6F
PM4 | CHEROKEE NATION | T-ATS 7 | VR (Z) MSC | ACTIVE | 2024-01-01 | 2024-01-14 | 14 | 2021-04-22
PM6 | CARL BRASHEAR | T-AKE 7 | ROH / DD (MSC) | ACTIVE | 2024-01-02 | 2024-03-31 | 90 | 2022-11-09 | C7F
PM2 | ZEUS | T-ARC 7 | ROH (MSC) | ACTIVE | 2024-01-02 | 2024-04-30 | 120 | 2023-02-10
PM2 | WESTWIND | T-AGSE 2 | ROH (MSC) | ACTIVE | 2024-01-03 | 2024-02-20 | 49 | 2021-12-14
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2024-01-03 | 2024-01-17 | 15 | 2023-01-26
PM6 | RICHARD E BYRD | T-AKE 4 | MTA (MSC) | ACTIVE | 2024-01-04 | 2024-02-17 | 45 | 2022-03-31 | C3F
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | ACTIVE | 2024-01-04 | 2024-01-18 | 15 | 2021-06-01 | C3F
PM2 | IMPECCABLE | T-AGOS 23 | MTA (MSC) | ACTIVE | 2024-01-05 | 2024-02-20 | 47 | 2022-10-31
PM1 | PECOS | T-AO 197 | VR (Z) MSC | ACTIVE | 2024-01-08 | 2024-01-22 | 15 | 2021-06-03
PM1 | HENRY J KAISER | T-AO 187 | MTA (MSC) | ACTIVE | 2024-01-08 | 2024-03-07 | 60 | 2022-08-15 | C3F
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2024-01-08 | 2024-01-22 | 15 | 2022-07-29 | C5F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2024-01-09 | 2024-01-30 | 22 | 2021-02-23
PM8 | YUMA | T-EPF 8 | MTA (MSC) | CANCELED | 2024-01-09 | 2024-03-08 | 60 | 2022-04-08
PM8 | YUMA | T-EPF 8 | ROH / DD (MSC) | ACTIVE | 2024-01-09 | 2024-03-25 | 77 | 2023-02-15 | C6F
PM8 | APALACHICOLA | T-EPF 13 | PSA (MSC) | ACTIVE | 2024-01-15 | 2024-04-13 | 90 | 2022-11-22 | C2F
PM1 | LEROY GRUMMAN | T-AO 195 | ROH (MSC) | ACTIVE | 2024-01-15 | 2024-03-29 | 75 | 2021-06-21
PM4 | GRASP | T-ARS 51 | MTA (MSC) | ACTIVE | 2024-01-15 | 2024-03-14 | 60 | 2023-01-18
PM4 | SAGINAW OJIBWE ANISHINABEK | T-ATS 8 | PSA (MSC) | ACTIVE | 2024-01-16 | 2024-03-15 | 60 | 2021-04-28
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2024-01-16 | 2024-01-29 | 14 | 2021-05-26 | C7F
PM8 | BRUNSWICK | T-EPF 6 | ROH / DD (MSC) | ACTIVE | 2024-01-17 | 2024-03-31 | 75 | 2023-02-11 | CTF 80
PM2 | MARIE THARP | T-AGS 66 | ROH (MSC) | ACTIVE | 2024-01-18 | 2024-03-20 | 63 | 2023-02-10 | C6F
PM6 | MEDGAR EVERS | T-AKE 13 | MTA (MSC) | ACTIVE | 2024-01-29 | 2024-03-29 | 61 | 2022-07-22 | CTF 80
PM8 | MILLINOCKET | T-EPF 3 | ROH / DD (MSC) | ACTIVE | 2024-01-29 | 2024-04-28 | 91 | 2023-02-06
PM1 | TIPPECANOE | T-AO 199 | ROH (MSC) | ACTIVE | 2024-01-30 | 2024-05-09 | 101 | 2022-12-20
PM2 | BRUCE C HEEZEN | T-AGS 64 | VR (Z) MSC | ACTIVE | 2024-01-31 | 2024-02-25 | 26 | 2023-02-10 | C5F
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2024-02-01 | 2024-02-14 | 14 | 2021-05-26 | C7F
PM6 | ARCTIC | T-AOE 8 | MTA (MSC) | ACTIVE | 2024-02-01 | 2024-03-16 | 45 | 2022-02-17
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2024-02-01 | 2024-02-14 | 14 | 2021-05-26 | C5F
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2024-02-01 | 2024-03-03 | 32 | 2022-02-23
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2024-02-01 | 2024-02-16 | 16 | 2023-02-14 | C7F
PM2 | EFFECTIVE | T-AGOS 21 | VR (Z) MSC | ACTIVE | 2024-02-05 | 2024-03-05 | 30 | 2023-01-10 | C7F
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | ACTIVE | 2024-02-05 | 2024-02-18 | 14 | 2023-03-01
PM6 | MATTHEW PERRY | T-AKE 9 | MTA (MSC) | ACTIVE | 2024-02-09 | 2024-03-24 | 45 | 2022-03-31 | C7F
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | CANCELED | 2024-02-12 | 2024-02-26 | 15 | 2023-02-26
PM1 | LARAMIE | T-AO 203 | ROH (MSC) | ACTIVE | 2024-02-12 | 2024-04-26 | 75 | 2021-06-21
PM2 | HENSON | T-AGS 63 | VR (Z) MSC | ACTIVE | 2024-02-12 | 2024-03-08 | 26 | 2023-02-10 | C7F
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2024-02-13 | 2024-02-26 | 14 | 2021-05-26 | C7F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2024-02-13 | 2024-02-26 | 14 | 2021-06-01 | C3F
PM8 | TRENTON | T-EPF 5 | MTA (MSC) | CANCELED | 2024-02-15 | 2024-04-15 | 61 | 2022-04-08
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | CANCELED | 2024-02-17 | 2024-02-27 | 11 | 2023-03-08
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2024-02-20 | 2024-03-04 | 14 | 2021-05-26 | C7F
PM6 | SACAGAWEA | T-AKE 2 | VR (Z) MSC | ACTIVE | 2024-02-25 | 2024-03-16 | 21 | 2021-05-26 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2024-02-27 | 2024-03-11 | 14 | 2021-06-01 | CTF 80
PM1 | JOHN ERICSSON | T-AO 194 | VR (Z) MSC | ACTIVE | 2024-03-01 | 2024-03-17 | 17 | 2023-02-14 | C7F
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2024-03-04 | 2024-03-18 | 15 | 2021-02-24
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2024-03-04 | 2024-03-18 | 15 | 2022-07-29 | C6F
PM1 | KANAWHA | T-AO 196 | VR (Z) MSC | ACTIVE | 2024-03-04 | 2024-03-18 | 15 | 2022-07-29 | C6F
PM1 | WALTER S DIEHL | T-AO 193 | VR (Z) MSC | DEFERRED | 2024-03-04 | 2024-03-17 | 14 | 2022-10-06
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | ACTIVE | 2024-03-04 | 2024-03-19 | 16 | 2021-08-19 | C7F
PM8 | CHOCTAW COUNTY | T-EPF 2 | VR (Z) MSC | CANCELED | 2024-03-04 | 2024-05-02 | 60 | 2023-02-17 | CTF 80
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2024-03-04 | 2024-03-18 | 15 | 2022-07-29
PM2 | MARY SEARS | T-AGS 65 | VR (Z) MSC | ACTIVE | 2024-03-04 | 2024-03-29 | 26 | 2023-02-16 | C7F
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | ACTIVE | 2024-03-11 | 2024-03-25 | 15 | 2021-06-03
PM3 | JOHN GLENN | T-ESD 2 | ROH / DD (MSC) | ACTIVE | 2024-03-11 | 2024-05-10 | 61 | 2019-10-24
PM2 | LOYAL | T-AGOS 22 | MTA (MSC) | ACTIVE | 2024-03-11 | 2024-04-25 | 46 | 2023-01-10 | C7F
PM4 | MERCY | T-AH 19 | MTA (MSC) | ACTIVE | 2024-03-15 | 2024-06-15 | 93 | 2022-12-08 | C3F
PM2 | HOWARD O LORENZEN | T-AGM 25 | ROH (MSC) | ACTIVE | 2024-03-15 | 2024-05-15 | 62 | 2023-03-09
PM8 | CARSON CITY | T-EPF 7 | VR (Z) MSC | ACTIVE | 2024-03-18 | 2024-05-16 | 60 | 2022-08-26 | C2F
PM8 | CHOCTAW COUNTY | T-EPF 2 | ROH / DD (MSC) | ACTIVE | 2024-03-18 | 2024-05-31 | 75 | 2023-02-17 | CTF 80
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | CANCELED | 2024-03-20 | 2024-05-03 | 45 | 2023-03-08 | C3F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2024-03-22 | 2024-04-04 | 14 | 2023-02-21
PM2 | WATERS | T-AGS 45 | ROH (MSC) | ACTIVE | 2024-03-22 | 2024-06-03 | 74 | 2022-08-01
PM2 | BOWDITCH | T-AGS 62 | ROH / DD (MSC) | ACTIVE | 2024-03-26 | 2024-05-24 | 60 | 2022-08-22
PM1 | JOHN LENTHALL | T-AO 189 | MTA (MSC) | CANCELED | 2024-04-01 | 2024-05-20 | 50 | 2022-05-12
PM1 | PECOS | T-AO 197 | MTA (MSC) | ACTIVE | 2024-04-01 | 2024-05-30 | 60 | 2022-08-12
PM4 | MOUNT WHITNEY | LCC 20 | VR (Z) MSC | ACTIVE | 2024-04-01 | 2024-04-14 | 14 | 2021-05-26 | C6F
PM4 | CHEROKEE NATION | T-ATS 7 | VR (Z) MSC | ACTIVE | 2024-04-01 | 2024-04-14 | 14 | 2021-04-22
PM8 | TRENTON | T-EPF 5 | ROH / DD (MSC) | ACTIVE | 2024-04-01 | 2024-07-01 | 92 | 2023-02-19 | C6F
PM8 | SPEARHEAD | T-EPF 1 | ROH / DD (MSC) | CANCELED | 2024-04-01 | 2024-07-29 | 120 | 2023-02-19 | C2F
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | ACTIVE | 2024-04-01 | 2024-05-15 | 45 | 2023-03-08
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2024-04-01 | 2024-04-17 | 17 | 2023-02-21 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | ROH (MSC) | ACTIVE | 2024-04-01 | 2024-05-15 | 45 | 2021-06-01 | CTF 80
PM1 | YUKON | T-AO 202 | ROH (MSC) | ACTIVE | 2024-04-03 | 2024-07-12 | 101 | 2022-12-20 | C7F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | ROH (MSC) | ACTIVE | 2024-04-08 | 2024-05-22 | 45 | 2021-06-01 | C3F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2024-04-08 | 2024-04-22 | 15 | 2021-02-23
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2024-04-09 | 2024-04-22 | 14 | 2023-02-10 | C6F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2024-04-12 | 2024-04-26 | 15 | 2022-02-14
PM6 | ROBERT E PEARY | T-AKE 5 | MTA (MSC) | CANCELED | 2024-04-29 | 2024-05-29 | 31 | 2020-03-04
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | ACTIVE | 2024-04-29 | 2024-05-14 | 16 | 2023-02-14 | C7F
PM4 | SAGINAW OJIBWE ANISHINABEK | T-ATS 8 | VR (Z) MSC | ACTIVE | 2024-05-01 | 2024-05-14 | 14 | 2021-04-28
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2024-05-01 | 2024-05-30 | 30 | 2022-02-23
PM4 | COMFORT | T-AH 20 | ROH / DD (MSC) | ACTIVE | 2024-05-01 | 2024-09-27 | 150 | 2022-05-09
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2024-05-02 | 2024-05-15 | 14 | 2021-05-26 | C7F
PM3 | PFC DEWAYNE T WILLIAMS | T-AK 3009 | ROH / DD (MSC) | ACTIVE | 2024-05-06 | 2024-09-13 | 131 | 2022-05-05
PM8 | PUERTO RICO | T-EPF 11 | VR (Z) MSC | ACTIVE | 2024-05-06 | 2024-05-27 | 22 | 2022-07-06 | C7F
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2024-05-06 | 2024-05-20 | 15 | 2022-07-29 | C5F
PM1 | BIG HORN | T-AO 198 | VR (Z) MSC | ACTIVE | 2024-05-06 | 2024-05-20 | 15 | 2023-01-26
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | ACTIVE | 2024-05-06 | 2024-05-19 | 14 | 2023-03-01
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2024-05-08 | 2024-05-21 | 14 | 2021-05-26 | C7F
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | ACTIVE | 2024-05-08 | 2024-05-24 | 17 | 2022-07-28 | C3F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2024-05-13 | 2024-05-27 | 15 | 2022-07-29 | C6F
PM2 | VICTORIOUS | T-AGOS 19 | VR (Z) MSC | ACTIVE | 2024-05-13 | 2024-06-07 | 26 | 2023-01-10
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2024-05-14 | 2024-05-27 | 14 | 2021-05-26 | C7F
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2024-05-20 | 2024-06-03 | 15 | 2021-06-01 | C7F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | ROH (MSC) | ACTIVE | 2024-05-20 | 2024-08-02 | 75 | 2021-06-01 | C2F
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2024-05-20 | 2024-06-02 | 14 | 2023-03-01
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2024-05-21 | 2024-06-03 | 14 | 2021-05-26 | C7F
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2024-05-21 | 2024-06-05 | 16 | 2021-05-26 | C7F
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | CANCELED | 2024-05-27 | 2024-06-25 | 30 | 2023-01-20
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2024-05-28 | 2024-06-11 | 15 | 2023-02-10 | CTF 80
PM6 | ALAN SHEPARD | T-AKE 3 | MTA (MSC) | ACTIVE | 2024-05-30 | 2024-07-13 | 45 | 2022-07-06 | C5F
PM6 | CHARLES DREW | T-AKE 10 | MTA (MSC) | ACTIVE | 2024-05-30 | 2024-07-13 | 45 | 2022-07-06 | C7F
PM4 | EMORY S LAND | AS 39 | VR (Z) MSC | ACTIVE | 2024-06-01 | 2024-06-30 | 30 | 2021-07-15 | C7F
PM3 | LEWIS B PULLER | ESB 3 | MTA (MSC) | ACTIVE | 2024-06-02 | 2024-07-17 | 46 | 2021-02-23
PM2 | PATHFINDER | T-AGS 60 | ROH (MSC) | ACTIVE | 2024-06-02 | 2024-07-31 | 60 | 2022-08-01
PM6 | SUPPLY | T-AOE 6 | MTA (MSC) | ACTIVE | 2024-06-03 | 2024-07-18 | 46 | 2023-02-02 | CTF 80
PM1 | HENRY J KAISER | T-AO 187 | VR (Z) MSC | ACTIVE | 2024-06-03 | 2024-06-17 | 15 | 2021-06-01 | C3F
PM2 | EAGLEVIEW | T-AGSE 3 | ROH (MSC) | ACTIVE | 2024-06-04 | 2024-07-23 | 50 | 2021-12-14 | C3F
PM6 | LEWIS AND CLARK | T-AKE 1 | VR (Z) MSC | ACTIVE | 2024-06-04 | 2024-07-01 | 28 | 2022-10-24 | C7F
PM1 | LEROY GRUMMAN | T-AO 195 | VR (Z) MSC | ACTIVE | 2024-06-05 | 2024-06-19 | 15 | 2021-06-21
PM1 | JOHN ERICSSON | T-AO 194 | ROH (MSC) | ACTIVE | 2024-06-05 | 2024-09-13 | 101 | 2022-12-20 | C7F
PM5 | BOB HOPE | T-AKR 300 | ROH / DD (MSC) | ACTIVE | 2024-06-09 | 2024-08-23 | 76 | 2021-01-14
PM1 | WALTER S DIEHL | T-AO 193 | VR (Z) MSC | DEFERRED | 2024-06-10 | 2024-06-24 | 15 | 2022-10-06
PM2 | ABLE | T-AGOS 20 | ROH (MSC) | ACTIVE | 2024-06-10 | 2024-08-10 | 62 | 2023-01-31
PM2 | HENSON | T-AGS 63 | MTA (MSC) | ACTIVE | 2024-06-10 | 2024-07-19 | 40 | 2023-02-10 | C7F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2024-06-11 | 2024-06-24 | 14 | 2021-05-26 | C3F
PM8 | FALL RIVER | T-EPF 4 | ROH / DD (MSC) | ACTIVE | 2024-06-11 | 2024-09-08 | 90 | 2022-08-03 | C3F
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | ACTIVE | 2024-06-17 | 2024-07-01 | 15 | 2021-06-03
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2024-06-17 | 2024-06-30 | 14 | 2023-02-21
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2024-06-18 | 2024-07-01 | 14 | 2022-08-04 | CTF 80
PM4 | CHEROKEE NATION | T-ATS 7 | VR (Z) MSC | ACTIVE | 2024-07-01 | 2024-07-14 | 14 | 2021-04-22
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | ACTIVE | 2024-07-01 | 2024-07-16 | 16 | 2021-08-19 | C7F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2024-07-07 | 2024-07-21 | 15 | 2021-02-23
PM1 | GUADALUPE | T-AO 200 | MTA (MSC) | ACTIVE | 2024-07-08 | 2024-09-05 | 60 | 2022-08-30 | C3F
PM8 | PUERTO RICO | T-EPF 11 | VR (Z) MSC | ACTIVE | 2024-07-08 | 2024-07-29 | 22 | 2022-07-06 | C7F
PM8 | NEWPORT | T-EPF 12 | VR (Z) MSC | ACTIVE | 2024-07-08 | 2024-09-05 | 60 | 2022-08-04 | C2F
PM1 | KANAWHA | T-AO 196 | MTA (MSC) | ACTIVE | 2024-07-15 | 2024-09-12 | 60 | 2021-06-01 | C2F
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | ACTIVE | 2024-07-15 | 2024-07-28 | 14 | 2023-03-01
PM6 | WALLY SCHIRRA | T-AKE 8 | ROH / DD (MSC) | ACTIVE | 2024-07-30 | 2024-10-27 | 90 | 2023-01-17 | C3F
PM4 | SAGINAW OJIBWE ANISHINABEK | T-ATS 8 | VR (Z) MSC | ACTIVE | 2024-08-01 | 2024-08-14 | 14 | 2021-04-28
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2024-08-01 | 2024-08-30 | 30 | 2022-02-23
PM1 | JOHN LENTHALL | T-AO 189 | VR (Z) MSC | CANCELED | 2024-08-05 | 2024-08-19 | 15 | 2022-05-12 | C2F
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | ACTIVE | 2024-08-05 | 2024-08-19 | 15 | 2021-06-03
PM1 | JOHN ERICSSON | T-AO 194 | VR (Z) MSC | ACTIVE | 2024-08-05 | 2024-08-19 | 15 | 2022-07-29
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2024-08-06 | 2024-08-19 | 14 | 2021-05-26 | C7F
PM1 | LARAMIE | T-AO 203 | VR (Z) MSC | ACTIVE | 2024-08-12 | 2024-08-26 | 15 | 2022-07-29 | C5F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2024-08-12 | 2024-08-25 | 14 | 2021-05-26 | C3F
PM2 | MARY SEARS | T-AGS 65 | ROH (MSC) | ACTIVE | 2024-08-12 | 2024-11-10 | 91 | 2023-02-16 | C3F
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2024-08-13 | 2024-08-26 | 14 | 2021-05-26 | C5F
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2024-08-13 | 2024-08-26 | 14 | 2021-05-26 | C5F
PM6 | AMELIA EARHART | T-AKE 6 | MTA (MSC) | ACTIVE | 2024-08-14 | 2024-09-28 | 46 | 2022-07-06 | C7F
PM2 | ZEUS | T-ARC 7 | VR (Z) MSC | ACTIVE | 2024-08-15 | 2024-08-28 | 14 | 2021-12-14
PM6 | ROBERT E PEARY | T-AKE 5 | MTA (MSC) | ACTIVE | 2024-08-19 | 2024-10-02 | 45 | 2022-07-06 | CTF 80
PM2 | EFFECTIVE | T-AGOS 21 | MTA (MSC) | ACTIVE | 2024-08-19 | 2024-10-03 | 46 | 2023-01-10 | C7F
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2024-08-19 | 2024-09-01 | 14 | 2023-03-01
PM1 | PECOS | T-AO 197 | VR (Z) MSC | ACTIVE | 2024-08-26 | 2024-09-09 | 15 | 2021-06-03
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2024-08-27 | 2024-09-09 | 14 | 2021-05-26 | C7F
PM6 | SACAGAWEA | T-AKE 2 | VR (Z) MSC | ACTIVE | 2024-08-27 | 2024-09-16 | 21 | 2021-05-26 | C7F
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2024-08-27 | 2024-09-09 | 14 | 2022-08-30 | C6F
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2024-08-31 | 2024-09-28 | 29 | 2021-02-24
PM6 | ALAN SHEPARD | T-AKE 3 | ROH (MSC) | CANCELED | 2024-09-01 | 2024-10-14 | 44 | 2019-03-14
PM1 | PATUXENT | T-AO 201 | MTA (MSC) | ACTIVE | 2024-09-02 | 2024-11-01 | 61 | 2022-07-28
PM2 | VICTORIOUS | T-AGOS 19 | ROH (MSC) | ACTIVE | 2024-09-02 | 2024-11-01 | 61 | 2023-01-10
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2024-09-04 | 2024-09-18 | 15 | 2021-05-26 | C7F
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2024-09-09 | 2024-09-23 | 15 | 2021-06-01 | C7F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2024-09-09 | 2024-09-23 | 15 | 2023-02-21
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2024-09-12 | 2024-09-25 | 14 | 2021-06-01 | C3F
PM1 | BIG HORN | T-AO 198 | VR (Z) MSC | ACTIVE | 2024-09-15 | 2024-09-30 | 16 | 2022-07-29
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2024-09-16 | 2024-09-30 | 15 | 2022-09-08 | CTF 80
PM4 | CATAWBA | T-ATF 168 | MTA (MSC) | ACTIVE | 2024-09-16 | 2024-11-14 | 60 | 2023-03-01
PM2 | ARROWHEAD | T-AGSE 4 | ROH (MSC) | ACTIVE | 2024-09-17 | 2024-11-05 | 50 | 2022-11-18 | C3F
PM6 | LEWIS AND CLARK | T-AKE 1 | VR (Z) MSC | ACTIVE | 2024-09-17 | 2024-09-30 | 14 | 2021-05-26 | C7F
| ROBERT E. SIMANEK | T-ESB 7 | PDA | ACTIVE | 2024-09-30 | 2024-11-29 | 61 | 2023-03-22 | NASSCO General Dynamics
PM4 | MERCY | T-AH 19 | VR (Z) MSC | ACTIVE | 2024-10-01 | 2024-11-29 | 60 | 2022-07-29 | C3F
PM4 | MOUNT WHITNEY | LCC 20 | MTA (MSC) | ACTIVE | 2024-10-01 | 2024-10-30 | 30 | 2021-05-26 | C6F
PM4 | CHEROKEE NATION | T-ATS 7 | MTA (MSC) | ACTIVE | 2024-10-01 | 2024-11-29 | 60 | 2021-04-22
PM4 | GRASP | T-ARS 51 | ROH / DD (MSC) | ACTIVE | 2024-10-01 | 2024-12-14 | 75 | 2023-03-01
PM6 | CESAR CHAVEZ | T-AKE 14 | MTA (MSC) | ACTIVE | 2024-10-02 | 2024-11-15 | 45 | 2022-07-06 | C7F
PM2 | BLACK POWDER | T-AGSE 1 | MTA (MSC) | ACTIVE | 2024-10-02 | 2024-10-31 | 30 | 2022-11-18
PM3 | MIGUEL KEITH | ESB 5 | ROH / DD (MSC) | ACTIVE | 2024-10-05 | 2024-12-04 | 61 | 2021-02-24
PM1 | HENRY J KAISER | T-AO 187 | VR (Z) MSC | ACTIVE | 2024-10-07 | 2024-10-21 | 15 | 2021-06-01 | C3F
PM8 | CITY OF BISMARCK | T-EPF 9 | ROH / DD (MSC) | ACTIVE | 2024-10-07 | 2024-12-20 | 75 | 2022-10-28 | C3F
PM2 | LOYAL | T-AGOS 22 | VR (Z) MSC | ACTIVE | 2024-10-07 | 2024-11-08 | 33 | 2023-01-10 | C7F
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2024-10-07 | 2024-10-21 | 15 | 2023-02-10 | CTF 80
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2024-10-14 | 2024-10-28 | 15 | 2022-07-29 | C6F
PM8 | SPEARHEAD | T-EPF 1 | VR (Z) MSC | ACTIVE | 2024-10-16 | 2024-12-14 | 60 | 2023-02-14 | Philadelphia Navy Yard
PM8 | CODY | T-EPF 14 | PSA (MSC) | ACTIVE | 2024-10-16 | 2025-01-13 | 90 | 2022-08-03 | C2F
PM8 | BRUNSWICK | T-EPF 6 | VR (Z) MSC | ACTIVE | 2024-10-16 | 2024-12-14 | 60 | 2023-02-11 | CTF 80
PM1 | LARAMIE | T-AO 203 | VR (Z) MSC | ACTIVE | 2024-10-21 | 2024-11-04 | 15 | 2022-07-29 | C5F
PM1 | TIPPECANOE | T-AO 199 | MTA (MSC) | ACTIVE | 2024-10-21 | 2025-01-03 | 75 | 2023-02-16
PM1 | LEROY GRUMMAN | T-AO 195 | VR (Z) MSC | ACTIVE | 2024-10-21 | 2024-11-03 | 14 | 2022-07-27
PM8 | BURLINGTON | T-EPF 10 | MTA (MSC) | ACTIVE | 2024-10-21 | 2024-12-19 | 60 | 2022-08-04 | C2F
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2024-10-28 | 2024-11-11 | 15 | 2022-07-29 | C6F
PM8 | PUERTO RICO | T-EPF 11 | ROH / DD (MSC) | ACTIVE | 2024-10-28 | 2025-02-02 | 98 | 2023-02-19 | C7F
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2024-10-29 | 2024-11-11 | 14 | 2023-01-13 | C5F
PM4 | SAGINAW OJIBWE ANISHINABEK | T-ATS 8 | VR (Z) MSC | ACTIVE | 2024-11-01 | 2024-11-14 | 14 | 2021-04-28
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | MTA (MSC) | ACTIVE | 2024-11-02 | 2024-12-18 | 47 | 2022-08-03
PM1 | KANAWHA | T-AO 196 | VR (Z) MSC | ACTIVE | 2024-11-04 | 2024-11-18 | 15 | 2021-06-01 | C2F
PM1 | JOHN ERICSSON | T-AO 194 | VR (Z) MSC | ACTIVE | 2024-11-04 | 2024-11-18 | 15 | 2022-07-29
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2024-11-05 | 2024-11-18 | 14 | 2023-01-13 | C7F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2024-11-05 | 2024-11-18 | 14 | 2021-05-26 | C3F
PM4 | NAVAJO | T-ATS 6 | PSA (MSC) | ACTIVE | 2024-11-10 | 2025-01-08 | 60 | 2023-02-14
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2024-11-11 | 2024-11-25 | 15 | 2021-05-26 | CTF 80
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2024-11-12 | 2024-11-25 | 14 | 2021-05-26 | C7F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2024-11-18 | 2024-12-02 | 15 | 2021-05-21
PM1 | RAPPAHANNOCK | T-AO 204 | MTA (MSC) | ACTIVE | 2024-11-24 | 2025-02-06 | 75 | 2023-02-16
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2024-11-29 | 2024-12-13 | 15 | 2021-02-24
PM2 | BRUCE C HEEZEN | T-AGS 64 | ROH (MSC) | ACTIVE | 2024-12-01 | 2025-02-13 | 75 | 2023-02-10 | C6F
PM4 | LENNI LENAPE | T-ATS 9 | VR (Z) MSC | ACTIVE | 2024-12-01 | 2024-12-14 | 14 | 2022-07-07
PM1 | JOHN LENTHALL | T-AO 189 | VR (Z) MSC | CANCELED | 2024-12-02 | 2024-12-16 | 15 | 2022-05-12 | C2F
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2024-12-02 | 2024-12-15 | 14 | 2021-05-26 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2024-12-02 | 2024-12-16 | 15 | 2022-09-08 | CTF 80
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | ACTIVE | 2024-12-02 | 2024-12-17 | 16 | 2021-08-19 | C7F
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2024-12-04 | 2024-12-18 | 15 | 2023-01-13 | C5F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2024-12-05 | 2024-12-18 | 14 | 2021-06-01 | C3F
PM2 | WATERS | T-AGS 45 | VR (Z) MSC | ACTIVE | 2024-12-09 | 2024-12-20 | 12 | 2022-08-22
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2024-12-10 | 2024-12-23 | 14 | 2021-05-26 | C7F
PM4 | CHEROKEE NATION | T-ATS 7 | VR (Z) MSC | ACTIVE | 2025-01-01 | 2025-01-14 | 14 | 2021-04-22
PM4 | MOUNT WHITNEY | LCC 20 | VR (Z) MSC | ACTIVE | 2025-01-01 | 2025-01-14 | 14 | 2021-03-25
PM4 | MERCY | T-AH 19 | MTA (MSC) | ACTIVE | 2025-01-01 | 2025-03-01 | 60 | 2022-02-23 | C3F
PM1 | PECOS | T-AO 197 | VR (Z) MSC | ACTIVE | 2025-01-01 | 2025-01-14 | 14 | 2022-07-27
PM1 | HENRY J KAISER | T-AO 187 | ROH (MSC) | CANCELED | 2025-01-01 | 2025-03-11 | 70 | 2022-08-15
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2025-01-01 | 2025-01-15 | 15 | 2022-07-29 | C6F
PM1 | YUKON | T-AO 202 | MTA (MSC) | ACTIVE | 2025-01-06 | 2025-02-24 | 50 | 2021-05-25 | C7F
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2025-01-06 | 2025-01-20 | 15 | 2023-02-10 | CTF 80
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | ACTIVE | 2025-01-06 | 2025-01-20 | 15 | 2021-05-20 | C3F
PM4 | EMORY S LAND | AS 39 | VR (Z) MSC | ACTIVE | 2025-01-06 | 2025-02-05 | 31 | 2021-07-15 | C7F
PM3 | PILILAAU | T-AKR 304 | ROH / DD (MSC) | ACTIVE | 2025-01-06 | 2025-05-02 | 117 | 2022-05-05
PM6 | RICHARD E BYRD | T-AKE 4 | MTA (MSC) | ACTIVE | 2025-01-07 | 2025-02-20 | 45 | 2022-07-06 | C3F
PM2 | ZEUS | T-ARC 7 | MTA (MSC) | ACTIVE | 2025-01-07 | 2025-03-25 | 78 | 2021-12-14
PM8 | YUMA | T-EPF 8 | VR (Z) MSC | ACTIVE | 2025-01-08 | 2025-03-08 | 60 | 2022-08-26
PM8 | SPEARHEAD | T-EPF 1 | ROH / DD (MSC) | ACTIVE | 2025-01-08 | 2025-05-07 | 120 | 2023-02-19 | CTF 80
PM6 | MATTHEW PERRY | T-AKE 9 | ROH / DD (MSC) | ACTIVE | 2025-01-10 | 2025-04-09 | 90 | 2022-11-09 | C7F
PM5 | FISHER | T-AKR 301 | ROH / DD (MSC) | ACTIVE | 2025-01-11 | 2025-03-27 | 76 | 2021-01-14
PM8 | APALACHICOLA | T-EPF 13 | MTA (MSC) | ACTIVE | 2025-01-13 | 2025-03-28 | 75 | 2023-02-21 | C7F
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2025-01-14 | 2025-01-27 | 14 | 2023-01-13 | C5F
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2025-01-14 | 2025-01-27 | 14 | 2022-08-04 | CTF 80
PM1 | JOSHUA HUMPHREYS | T-AO 188 | MTA (MSC) | ACTIVE | 2025-01-15 | 2025-03-15 | 60 | 2023-02-17 | CTF 80
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2025-01-27 | 2025-02-10 | 15 | 2021-05-10 | CTF 80
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2025-01-30 | 2025-02-13 | 15 | 2021-02-23
PM4 | SAGINAW OJIBWE ANISHINABEK | T-ATS 8 | MTA (MSC) | ACTIVE | 2025-02-01 | 2025-04-01 | 60 | 2021-04-28
PM4 | LENNI LENAPE | T-ATS 9 | VR (Z) MSC | ACTIVE | 2025-02-01 | 2025-02-14 | 14 | 2022-07-07
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2025-02-02 | 2025-02-16 | 15 | 2022-07-29 | C6F
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2025-02-03 | 2025-03-06 | 32 | 2022-06-15
PM8 | MILLINOCKET | T-EPF 3 | VR (Z) MSC | ACTIVE | 2025-02-03 | 2025-04-03 | 60 | 2022-08-26
PM6 | CARL BRASHEAR | T-AKE 7 | MTA (MSC) | ACTIVE | 2025-02-04 | 2025-03-20 | 45 | 2022-07-06 | C5F
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2025-02-04 | 2025-02-17 | 14 | 2021-04-22 | C7F
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2025-02-05 | 2025-02-19 | 15 | 2021-04-22 | C7F
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2025-02-11 | 2025-02-24 | 14 | 2021-04-29 | C7F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2025-02-11 | 2025-02-24 | 14 | 2021-07-16 | CTF 80
PM1 | KANAWHA | T-AO 196 | VR (Z) MSC | ACTIVE | 2025-02-14 | 2025-02-28 | 15 | 2022-07-27 | C2F
PM1 | BIG HORN | T-AO 198 | VR (Z) MSC | ACTIVE | 2025-02-16 | 2025-03-03 | 16 | 2022-07-29
PM6 | LEWIS AND CLARK | T-AKE 1 | ROH / DD (MSC) | ACTIVE | 2025-02-18 | 2025-05-19 | 91 | 2022-10-17 | CTF 80
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2025-02-18 | 2025-03-03 | 14 | 2021-05-11 | C7F
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | ACTIVE | 2025-02-19 | 2025-04-19 | 60 | 2022-11-09 | C2F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | MTA (MSC) | ACTIVE | 2025-02-20 | 2025-04-05 | 45 | 2022-07-06 | C3F
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2025-02-24 | 2025-03-10 | 15 | 2023-02-10 | CTF 80
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2025-02-27 | 2025-03-13 | 15 | 2021-02-24
PM6 | SACAGAWEA | T-AKE 2 | VR (Z) MSC | ACTIVE | 2025-02-27 | 2025-03-18 | 20 | 2021-05-11 | C7F
PM4 | CATAWBA | T-ATF 168 | DECOM AVAIL (MSC) | ACTIVE | 2025-03-01 | 2025-03-30 | 30 | 2023-03-01
PM4 | NAVAJO | T-ATS 6 | VR (Z) MSC | ACTIVE | 2025-03-01 | 2025-03-14 | 14 | 2023-02-15
PM4 | SALVOR | T-ARS 52 | DECOM AVAIL (MSC) | ACTIVE | 2025-03-01 | 2025-03-30 | 30 | 2021-08-19
PM4 | MUSCOGEE CREEK NATION | T-ATS 10 | VR (Z) MSC | ACTIVE | 2025-03-01 | 2025-03-14 | 14 | 2022-07-07
PM1 | JOHN ERICSSON | T-AO 194 | VR (Z) MSC | ACTIVE | 2025-03-03 | 2025-03-17 | 15 | 2022-07-29
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2025-03-03 | 2025-03-17 | 15 | 2022-07-29 | C6F
PM8 | CHOCTAW COUNTY | T-EPF 2 | ROH / DD (MSC) | CANCELED | 2025-03-03 | 2025-05-16 | 75 | 2023-02-19 | C2F
PM8 | CHOCTAW COUNTY | T-EPF 2 | VR (Z) MSC | ACTIVE | 2025-03-03 | 2025-05-01 | 60 | 2023-02-19 | CTF 80
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2025-03-03 | 2025-03-16 | 14 | 2023-03-01
PM6 | MEDGAR EVERS | T-AKE 13 | ROH (MSC) | ACTIVE | 2025-03-04 | 2025-04-17 | 45 | 2021-05-10 | CTF 80
PM8 | POINT LOMA | T-EPF 15 | PDA | ACTIVE | 2025-03-11 | 2025-04-09 | 30 | 2023-02-11 | MOBILE
PM1 | KANAWHA | T-AO 196 | ROH (MSC) | ACTIVE | 2025-03-15 | 2025-06-13 | 91 | 2022-07-27 | C2F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2025-03-17 | 2025-03-31 | 15 | 2021-05-21
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2025-03-18 | 2025-04-02 | 16 | 2022-08-03
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2025-03-23 | 2025-04-06 | 15 | 2022-07-29 | C6F
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | ACTIVE | 2025-03-24 | 2025-04-07 | 15 | 2021-06-03
PM4 | CHEROKEE NATION | T-ATS 7 | VR (Z) MSC | ACTIVE | 2025-04-01 | 2025-04-14 | 14 | 2021-04-22
PM4 | MOUNT WHITNEY | LCC 20 | VR (Z) MSC | ACTIVE | 2025-04-01 | 2025-04-14 | 14 | 2021-03-25
PM4 | FRANK CABLE | AS 40 | MTA (MSC) | ACTIVE | 2025-04-01 | 2025-07-15 | 106 | 2021-07-09 | C3F
PM1 | PECOS | T-AO 197 | ROH (MSC) | ACTIVE | 2025-04-01 | 2025-06-29 | 90 | 2022-10-05
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | ACTIVE | 2025-04-07 | 2025-04-21 | 15 | 2021-05-20 | C3F
PM8 | CARSON CITY | T-EPF 7 | VR (Z) MSC | ACTIVE | 2025-04-09 | 2025-06-07 | 60 | 2022-08-26 | C2F
PM6 | ARCTIC | T-AOE 8 | ROH / DD (MSC) | ACTIVE | 2025-04-23 | 2025-07-22 | 91 | 2022-07-22 | CTF 80
PM1 | JOHN LENTHALL | T-AO 189 | ROH (MSC) | CANCELED | 2025-04-28 | 2025-06-26 | 60 | 2022-05-12 | C2F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2025-04-30 | 2025-05-14 | 15 | 2021-02-23
PM4 | SAGINAW OJIBWE ANISHINABEK | T-ATS 8 | VR (Z) MSC | ACTIVE | 2025-05-01 | 2025-05-14 | 14 | 2021-04-28
PM4 | EMORY S LAND | AS 39 | VR (Z) MSC | ACTIVE | 2025-05-01 | 2025-05-30 | 30 | 2021-07-09 | C7F
PM4 | LENNI LENAPE | T-ATS 9 | PSA (MSC) | ACTIVE | 2025-05-01 | 2025-06-30 | 61 | 2022-07-07
PM1 | PECOS | T-AO 197 | VR (Z) MSC | CANCELED | 2025-05-01 | 2025-05-14 | 14 | 2022-10-05
PM2 | WESTWIND | T-AGSE 2 | MTA (MSC) | ACTIVE | 2025-05-05 | 2025-06-04 | 31 | 2022-11-18
PM6 | CHARLES DREW | T-AKE 10 | ROH / DD (MSC) | ACTIVE | 2025-05-06 | 2025-08-03 | 90 | 2022-11-09 | C7F
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2025-05-06 | 2025-05-19 | 14 | 2021-04-22 | C7F
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2025-05-06 | 2025-05-19 | 14 | 2021-04-29 | C7F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2025-05-06 | 2025-05-19 | 14 | 2021-05-11 | C3F
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | ACTIVE | 2025-05-12 | 2025-05-26 | 15 | 2021-06-03
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2025-05-12 | 2025-05-26 | 15 | 2022-08-04 | C6F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | CANCELED | 2025-05-12 | 2025-05-26 | 15 | 2022-08-04 | C6F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | CANCELED | 2025-05-13 | 2025-05-27 | 15 | 2022-08-03
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2025-05-13 | 2025-05-26 | 14 | 2021-04-22 | C5F
PM6 | ALAN SHEPARD | T-AKE 3 | ROH (MSC) | ACTIVE | 2025-05-14 | 2025-06-28 | 46 | 2021-04-22 | C7F
PM1 | BIG HORN | T-AO 198 | ROH (MSC) | ACTIVE | 2025-05-18 | 2025-08-18 | 93 | 2022-07-29
PM1 | JOHN ERICSSON | T-AO 194 | MTA (MSC) | ACTIVE | 2025-05-19 | 2025-07-18 | 61 | 2022-07-29
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2025-05-20 | 2025-06-02 | 14 | 2021-05-11 | C7F
PM3 | LEWIS B PULLER | ESB 3 | ROH / DD (MSC) | ACTIVE | 2025-05-28 | 2025-07-27 | 61 | 2021-02-23
PM1 | PATUXENT | T-AO 201 | ROH (MSC) | ACTIVE | 2025-05-31 | 2025-08-29 | 91 | 2022-07-28
PM4 | COMFORT | T-AH 20 | MTA (MSC) | ACTIVE | 2025-06-01 | 2025-09-28 | 120 | 2022-02-24
PM4 | NAVAJO | T-ATS 6 | VR (Z) MSC | ACTIVE | 2025-06-01 | 2025-06-14 | 14 | 2023-02-15
PM4 | MUSCOGEE CREEK NATION | T-ATS 10 | VR (Z) MSC | ACTIVE | 2025-06-01 | 2025-06-14 | 14 | 2022-07-07
PM1 | HENRY J KAISER | T-AO 187 | VR (Z) MSC | ACTIVE | 2025-06-01 | 2025-06-14 | 14 | 2022-07-27
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2025-06-02 | 2025-06-16 | 15 | 2021-05-25 | C7F
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2025-06-02 | 2025-06-15 | 14 | 2021-05-10 | CTF 80
PM4 | MERCY | T-AH 19 | VR (Z) MSC | ACTIVE | 2025-06-02 | 2025-07-03 | 32 | 2021-07-09 | C3F
PM8 | NEWPORT | T-EPF 12 | ROH / DD (MSC) | ACTIVE | 2025-06-08 | 2025-09-14 | 99 | 2022-08-04 | C2F
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2025-06-09 | 2025-06-22 | 14 | 2023-03-01
PM6 | LEWIS AND CLARK | T-AKE 1 | VR (Z) MSC | ACTIVE | 2025-06-10 | 2025-07-07 | 28 | 2021-05-10
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2025-06-10 | 2025-06-23 | 14 | 2021-05-11 | C3F
PM1 | LARAMIE | T-AO 203 | MTA (MSC) | ACTIVE | 2025-06-16 | 2025-08-29 | 75 | 2022-07-27
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2025-06-17 | 2025-06-30 | 14 | 2021-05-10 | C7F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2025-06-30 | 2025-07-13 | 14 | 2021-11-04 | CTF 80
PM1 | GUADALUPE | T-AO 200 | ROH (MSC) | ACTIVE | 2025-06-30 | 2025-09-12 | 75 | 2021-05-20 | C3F
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | ACTIVE | 2025-06-30 | 2025-07-14 | 15 | 2021-06-03
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2025-06-30 | 2025-07-14 | 15 | 2022-07-29 | C5F
PM4 | CHEROKEE NATION | T-ATS 7 | VR (Z) MSC | ACTIVE | 2025-07-01 | 2025-07-14 | 14 | 2021-04-22
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2025-07-02 | 2025-07-17 | 16 | 2022-08-03
PM8 | APALACHICOLA | T-EPF 13 | ROH / DD (MSC) | CANCELED | 2025-07-07 | 2025-09-04 | 60 | 2023-02-19 | C7F
PM8 | FALL RIVER | T-EPF 4 | VR (Z) MSC | ACTIVE | 2025-07-07 | 2025-09-04 | 60 | 2023-02-14 | Joint Base Pearl Harbor Hickam
PM6 | ROBERT E PEARY | T-AKE 5 | MTA (MSC) | ACTIVE | 2025-07-28 | 2025-09-18 | 53 | 2022-07-22 | CTF 80
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2025-07-29 | 2025-08-12 | 15 | 2021-02-23
PM4 | SAGINAW OJIBWE ANISHINABEK | T-ATS 8 | VR (Z) MSC | ACTIVE | 2025-08-01 | 2025-08-14 | 14 | 2021-04-28
PM4 | EMORY S LAND | AS 39 | VR (Z) MSC | ACTIVE | 2025-08-01 | 2025-08-30 | 30 | 2021-07-09 | C7F
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | ACTIVE | 2025-08-04 | 2025-08-18 | 15 | 2021-06-03
PM6 | ROBERT E PEARY | T-AKE 5 | ROH (MSC) | CANCELED | 2025-08-04 | 2025-09-18 | 46 | 2022-07-22 | CTF 80
PM2 | EAGLEVIEW | T-AGSE 3 | MTA (MSC) | ACTIVE | 2025-08-04 | 2025-09-03 | 31 | 2022-11-18
PM6 | WALLY SCHIRRA | T-AKE 8 | MTA (MSC) | ACTIVE | 2025-08-05 | 2025-09-18 | 45 | 2022-07-06 | C7F
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2025-08-05 | 2025-08-18 | 14 | 2021-04-29 | C7F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2025-08-05 | 2025-08-18 | 14 | 2021-05-11 | C3F
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2025-08-11 | 2025-08-25 | 15 | 2022-07-29 | C6F
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2025-08-12 | 2025-08-25 | 14 | 2021-04-22 | C5F
PM6 | AMELIA EARHART | T-AKE 6 | MTA (MSC) | ACTIVE | 2025-08-14 | 2025-09-25 | 43 | 2022-07-06
PM2 | ZEUS | T-ARC 7 | VR (Z) MSC | ACTIVE | 2025-08-15 | 2025-08-28 | 14 | 2021-12-14
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | CANCELED | 2025-08-18 | 2025-09-01 | 15 | 2022-07-22 | CTF 80
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2025-08-19 | 2025-09-01 | 14 | 2021-05-10 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | MTA (MSC) | ACTIVE | 2025-08-26 | 2025-10-09 | 45 | 2022-07-06 | CTF 80
PM6 | SACAGAWEA | T-AKE 2 | VR (Z) MSC | ACTIVE | 2025-08-26 | 2025-09-15 | 21 | 2021-05-11 | C7F
PM4 | NAVAJO | T-ATS 6 | VR (Z) MSC | ACTIVE | 2025-09-01 | 2025-09-14 | 14 | 2021-04-22
PM4 | MERCY | T-AH 19 | VR (Z) MSC | ACTIVE | 2025-09-01 | 2025-09-25 | 25 | 2021-07-09 | C3F
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2025-09-01 | 2025-09-30 | 30 | 2022-02-23
PM4 | LENNI LENAPE | T-ATS 9 | VR (Z) MSC | ACTIVE | 2025-09-01 | 2025-09-14 | 14 | 2022-07-07
PM4 | MUSCOGEE CREEK NATION | T-ATS 10 | PSA (MSC) | ACTIVE | 2025-09-01 | 2025-10-30 | 60 | 2022-07-07
PM1 | PECOS | T-AO 197 | MTA (MSC) | CANCELED | 2025-09-01 | 2025-11-09 | 70 | 2022-10-05
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2025-09-01 | 2025-09-15 | 15 | 2022-07-29 | C5F
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2025-09-04 | 2025-09-17 | 14 | 2021-04-22 | C7F
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2025-09-08 | 2025-09-22 | 15 | 2021-05-25 | C7F
PM2 | BLACK POWDER | T-AGSE 1 | VR (Z) MSC | ACTIVE | 2025-09-08 | 2025-09-18 | 11 | 2022-11-18
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2025-09-09 | 2025-09-22 | 14 | 2021-05-11 | C3F
PM3 | 1ST LT BALDOMERO LOPEZ | T-AK 3010 | ROH / DD (MSC) | ACTIVE | 2025-09-15 | 2026-01-12 | 120 | 2023-02-01 | CTF 80
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2025-09-15 | 2025-09-28 | 14 | 2023-03-01
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2025-09-16 | 2025-09-28 | 13 | 2021-04-29 | C7F
PM6 | LEWIS AND CLARK | T-AKE 1 | VR (Z) MSC | ACTIVE | 2025-09-16 | 2025-09-29 | 14 | 2021-05-10 | C7F
PM4 | CHEROKEE NATION | T-ATS 7 | MTA (MSC) | ACTIVE | 2025-10-01 | 2025-11-29 | 60 | 2021-04-22
PM4 | MOUNT WHITNEY | LCC 20 | ROH (MSC) | ACTIVE | 2025-10-01 | 2026-01-28 | 120 | 2022-02-22
PM1 | HENRY J KAISER | T-AO 187 | VR (Z) MSC | ACTIVE | 2025-10-01 | 2025-10-14 | 14 | 2022-07-27
PM6 | CESAR CHAVEZ | T-AKE 14 | ROH (MSC) | ACTIVE | 2025-10-06 | 2025-11-20 | 46 | 2021-04-29 | C7F
PM8 | PUERTO RICO | T-EPF 11 | MTA (MSC) | ACTIVE | 2025-10-08 | 2025-12-21 | 75 | 2023-02-28 | C7F
PM1 | JOHN ERICSSON | T-AO 194 | VR (Z) MSC | ACTIVE | 2025-10-13 | 2025-10-27 | 15 | 2022-07-29
PM8 | BRUNSWICK | T-EPF 6 | ROH / DD (MSC) | ACTIVE | 2025-10-15 | 2026-01-12 | 90 | 2023-02-19 | CTF 80
PM8 | CITY OF BISMARCK | T-EPF 9 | VR (Z) MSC | ACTIVE | 2025-10-15 | 2025-12-13 | 60 | 2022-08-26 | C3F
PM8 | SPEARHEAD | T-EPF 1 | VR (Z) MSC | ACTIVE | 2025-10-15 | 2025-12-13 | 60 | 2023-02-14 | Philadelphia Navy Yard
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | ROH / DD (MSC) | CANCELED | 2025-10-17 | 2025-12-17 | 62 | 2022-08-04
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | ROH (MSC) | ACTIVE | 2025-10-17 | 2025-12-17 | 62 | 2022-08-04
PM6 | SUPPLY | T-AOE 6 | ROH / DD (MSC) | ACTIVE | 2025-10-27 | 2026-04-10 | 166 | 2023-02-02 | CTF 80
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2025-10-27 | 2025-11-10 | 15 | 2021-02-23
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2025-10-27 | 2025-11-09 | 14 | 2022-07-28
PM8 | BURLINGTON | T-EPF 10 | MTA (MSC) | ACTIVE | 2025-10-27 | 2026-01-09 | 75 | 2023-01-30 | CTF 80
PM2 | HENSON | T-AGS 63 | ROH (MSC) | ACTIVE | 2025-10-27 | 2026-01-25 | 91 | 2023-02-10 | C7F
PM4 | SAGINAW OJIBWE ANISHINABEK | T-ATS 8 | VR (Z) MSC | ACTIVE | 2025-11-01 | 2025-11-14 | 14 | 2021-04-28
PM1 | TIPPECANOE | T-AO 199 | ROH (MSC) | ACTIVE | 2025-11-01 | 2026-02-08 | 100 | 2023-02-22
PM1 | BIG HORN | T-AO 198 | VR (Z) MSC | ACTIVE | 2025-11-02 | 2025-11-17 | 16 | 2022-07-29
PM1 | LARAMIE | T-AO 203 | VR (Z) MSC | ACTIVE | 2025-11-03 | 2025-11-16 | 14 | 2022-07-27
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2025-11-04 | 2025-11-18 | 15 | 2021-04-22 | C5F
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2025-11-04 | 2025-11-17 | 14 | 2021-05-10 | C6F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2025-11-04 | 2025-11-17 | 14 | 2021-05-11 | C3F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | CANCELED | 2025-11-09 | 2025-11-23 | 15 | 2022-08-03
PM1 | KANAWHA | T-AO 196 | VR (Z) MSC | ACTIVE | 2025-11-10 | 2025-11-23 | 14 | 2022-07-27
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2025-11-11 | 2025-11-24 | 14 | 2021-05-10 | C7F
PM2 | ARROWHEAD | T-AGSE 4 | MTA (MSC) | ACTIVE | 2025-11-15 | 2025-12-14 | 30 | 2022-11-18
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2025-11-17 | 2025-12-01 | 15 | 2022-07-29 | C6F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2025-11-24 | 2025-12-08 | 15 | 2022-07-29 | C5F
PM4 | EMORY S LAND | AS 39 | ROH / DD (MSC) | ACTIVE | 2025-11-25 | 2026-05-25 | 182 | 2021-07-15 | C7F
PM4 | NAVAJO | T-ATS 6 | MTA (MSC) | ACTIVE | 2025-12-01 | 2026-01-29 | 60 | 2023-02-15
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2025-12-01 | 2025-12-15 | 15 | 2022-05-03 | CTF 80
PM1 | RAPPAHANNOCK | T-AO 204 | ROH (MSC) | ACTIVE | 2025-12-01 | 2026-03-01 | 91 | 2022-07-29
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2025-12-02 | 2025-12-15 | 14 | 2021-04-22
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2025-12-02 | 2025-12-15 | 14 | 2021-04-29 | C7F
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2025-12-02 | 2025-12-15 | 14 | 2021-05-11 | C7F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2025-12-02 | 2025-12-15 | 14 | 2021-05-11 | C3F
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2025-12-04 | 2025-12-17 | 14 | 2021-04-22 | C7F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2025-12-04 | 2025-12-18 | 15 | 2022-08-04 | CTF 80
PM1 | HENRY J KAISER | T-AO 187 | ROH (MSC) | ACTIVE | 2025-12-29 | 2026-03-29 | 91 | 2022-08-15
PM4 | CHEROKEE NATION | T-ATS 7 | VR (Z) MSC | ACTIVE | 2026-01-01 | 2026-01-14 | 14 | 2021-04-22
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | ACTIVE | 2026-01-01 | 2026-01-14 | 14 | 2022-07-27
PM1 | PECOS | T-AO 197 | VR (Z) MSC | ACTIVE | 2026-01-01 | 2026-01-14 | 14 | 2022-07-27
PM4 | MERCY | T-AH 19 | ROH (MSC) | ACTIVE | 2026-01-05 | 2026-05-04 | 120 | 2022-02-23 | C3F
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2026-01-05 | 2026-02-04 | 31 | 2022-06-15
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2026-01-05 | 2026-01-30 | 26 | 2023-03-01
PM6 | RICHARD E BYRD | T-AKE 4 | ROH (MSC) | ACTIVE | 2026-01-06 | 2026-02-19 | 45 | 2021-05-11 | C3F
PM8 | YUMA | T-EPF 8 | VR (Z) MSC | ACTIVE | 2026-01-07 | 2026-03-07 | 60 | 2022-08-26 | C2F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | ROH / DD (MSC) | ACTIVE | 2026-01-08 | 2026-04-07 | 90 | 2022-11-09 | C3F
PM8 | APALACHICOLA | T-EPF 13 | ROH / DD (MSC) | ACTIVE | 2026-01-12 | 2026-03-27 | 75 | 2023-02-21 | C7F
PM8 | MILLINOCKET | T-EPF 3 | ROH / DD (MSC) | ACTIVE | 2026-01-12 | 2026-03-27 | 75 | 2023-02-21
PM1 | LARAMIE | T-AO 203 | VR (Z) MSC | ACTIVE | 2026-01-20 | 2026-02-02 | 14 | 2022-07-27
PM3 | MIGUEL KEITH | ESB 5 | MTA (MSC) | ACTIVE | 2026-01-25 | 2026-03-11 | 46 | 2021-02-23
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2026-01-25 | 2026-02-09 | 16 | 2021-05-10 | CTF 80
PM4 | SAGINAW OJIBWE ANISHINABEK | T-ATS 8 | MTA (MSC) | ACTIVE | 2026-02-01 | 2026-04-01 | 60 | 2021-04-28
PM1 | HENRY J KAISER | T-AO 187 | MTA (MSC) | CANCELED | 2026-02-01 | 2026-04-01 | 60 | 2022-08-15
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2026-02-02 | 2026-02-15 | 14 | 2022-08-04 | CTF 80
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2026-02-02 | 2026-02-16 | 15 | 2022-07-29 | C6F
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2026-02-03 | 2026-02-16 | 14 | 2021-04-22 | C7F
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2026-02-03 | 2026-02-16 | 14 | 2021-04-22
PM6 | CARL BRASHEAR | T-AKE 7 | MTA (MSC) | ACTIVE | 2026-02-04 | 2026-03-20 | 45 | 2022-11-09 | C5F
PM6 | MATTHEW PERRY | T-AKE 9 | MTA (MSC) | ACTIVE | 2026-02-09 | 2026-03-25 | 45 | 2022-07-06 | C7F
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2026-02-10 | 2026-02-23 | 14 | 2021-04-29 | C7F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2026-02-10 | 2026-02-23 | 14 | 2022-08-04 | CTF 80
PM1 | BIG HORN | T-AO 198 | VR (Z) MSC | ACTIVE | 2026-02-16 | 2026-03-02 | 15 | 2022-07-29
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | ACTIVE | 2026-02-16 | 2026-04-16 | 60 | 2023-02-11 | CTF 80
PM6 | SACAGAWEA | T-AKE 2 | ROH / DD (MSC) | ACTIVE | 2026-02-17 | 2026-05-18 | 91 | 2022-10-17 | CTF 80
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2026-02-17 | 2026-03-02 | 14 | 2021-05-11 | C7F
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2026-02-23 | 2026-03-08 | 14 | 2022-07-28
PM4 | GRASP | T-ARS 51 | DECOM AVAIL (MSC) | ACTIVE | 2026-03-01 | 2026-03-30 | 30 | 2023-03-01
PM4 | NAVAJO | T-ATS 6 | VR (Z) MSC | ACTIVE | 2026-03-01 | 2026-03-14 | 14 | 2023-02-15
PM4 | MOUNT WHITNEY | LCC 20 | VR (Z) MSC | ACTIVE | 2026-03-01 | 2026-03-14 | 14 | 2021-03-25
PM8 | CHOCTAW COUNTY | T-EPF 2 | VR (Z) MSC | ACTIVE | 2026-03-02 | 2026-04-30 | 60 | 2022-08-26 | C2F
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2026-03-03 | 2026-03-16 | 14 | 2021-04-29 | C7F
PM1 | JOHN ERICSSON | T-AO 194 | ROH (MSC) | ACTIVE | 2026-03-03 | 2026-06-21 | 111 | 2022-07-29
PM2 | WESTWIND | T-AGSE 2 | VR (Z) MSC | ACTIVE | 2026-03-03 | 2026-03-13 | 11 | 2022-11-18
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2026-03-17 | 2026-04-01 | 16 | 2022-08-03