## FSC
Battle Group | Ship | Hull | Event Type | Status | Start Date | End Date | Duration (D) | Updated Date | Repair Activity
PM1 | LUCY STONE | T-AO 209 | PDA | ACTIVE | 2025-10-01 | 2025-12-03 | 64 | 2025-02-21 | C3F
PM6 | MEDGAR EVERS | T-AKE 13 | ROH (MSC) | ACTIVE | 2025-10-01 | 2025-12-30 | 91 | 2025-09-14 | CTF 80
PM8 | GUAM | HST 1 | ROH / DD (MSC) | ACTIVE | 2025-10-01 | 2025-11-14 | 45 | 2025-08-19 | ST Marine
PM8 | CODY | T-EPF 14 | VR (Z) MSC | ACTIVE | 2025-10-06 | 2025-10-25 | 20 | 2025-07-29 | JEB/LCRK
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2025-10-07 | 2025-10-28 | 22 | 2025-08-14 | C5F
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2025-10-07 | 2025-10-21 | 15 | 2025-08-27 | C6F
PM1 | HENRY J KAISER | T-AO 187 | VR (Z) MSC | ACTIVE | 2025-10-12 | 2025-10-25 | 14 | 2025-08-07 | C3F
PM1 | ROBERT F KENNEDY | T-AO 208 | VR (Z) MSC | ACTIVE | 2025-10-13 | 2025-10-25 | 13 | 2025-04-17 | CTF 80
PM1 | JOHN ERICSSON | T-AO 194 | VR (Z) MSC | DEFERRED | 2025-10-13 | 2025-10-27 | 15 | 2024-09-13
PM1 | EARL WARREN | T-AO 207 | PSA (MSC) | ACTIVE | 2025-10-15 | 2026-02-22 | 131 | 2025-09-23 | VIGOR MARINE
PM8 | CITY OF BISMARCK | T-EPF 9 | VR (Z) MSC | ACTIVE | 2025-10-15 | 2025-11-04 | 21 | 2025-04-01 | THAILAND
PM8 | PUERTO RICO | T-EPF 11 | MTA (MSC) | ACTIVE | 2025-10-16 | 2025-12-31 | 77 | 2025-09-15 | THAILAND
PM3 | ROBERT E SIMANEK | ESB 7 | PSA (MSC) | ACTIVE | 2025-10-18 | 2026-01-17 | 92 | 2025-09-29 | DETYENS
PM1 | JOHN LEWIS | T-AO 205 | MTA (MSC) | ACTIVE | 2025-10-20 | 2025-12-03 | 45 | 2025-09-11 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | MTA (MSC) | ACTIVE | 2025-10-27 | 2025-12-27 | 62 | 2025-05-01 | CTF 80
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2025-10-27 | 2025-11-09 | 14 | 2025-08-11 | C3F
PM2 | MARY SEARS | T-AGS 65 | VR (Z) MSC | ACTIVE | 2025-10-27 | 2025-11-14 | 19 | 2025-07-10 | C7F
PM4 | MOUNT WHITNEY | LCC 20 | ROH / DD (MSC) | ACTIVE | 2025-10-30 | 2026-02-26 | 120 | 2025-09-11 | C6F
PM4 | FRANK CABLE | AS 40 | MTA (MSC) | ACTIVE | 2025-11-01 | 2026-04-01 | 152 | 2025-09-03 | GUAM
PM2 | EFFECTIVE | T-AGOS 21 | MTA (MSC) | ACTIVE | 2025-11-01 | 2025-12-15 | 45 | 2025-07-10 | C7F
PM2 | IMPECCABLE | T-AGOS 23 | ROH (MSC) | ACTIVE | 2025-11-01 | 2026-02-01 | 93 | 2025-08-08 | C7F
PM1 | RAPPAHANNOCK | T-AO 204 | ROH / DD (MSC) | ACTIVE | 2025-11-01 | 2026-02-09 | 101 | 2025-07-23 | C7F
PM1 | ROBERT F KENNEDY | T-AO 208 | VR (Z) MSC | ACTIVE | 2025-11-01 | 2025-11-03 | 3 | 2025-04-17 | CTF 80
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2025-11-02 | 2025-11-22 | 21 | 2025-08-20 | GUAM
PM6 | WALLY SCHIRRA | T-AKE 8 | MTA (MSC) | ACTIVE | 2025-11-03 | 2025-12-22 | 50 | 2023-12-10 | C7F
PM2 | EAGLEVIEW | T-AGSE 3 | MTA (MSC) | ACTIVE | 2025-11-03 | 2025-12-22 | 50 | 2025-09-05 | C3F
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | ACTIVE | 2025-11-03 | 2025-11-23 | 21 | 2025-04-08 | CTF 80
PM8 | CARSON CITY | T-EPF 7 | VR (Z) MSC | ACTIVE | 2025-11-03 | 2025-11-23 | 21 | 2025-04-28 | C2F
PM8 | YUMA | T-EPF 8 | VR (Z) MSC | ACTIVE | 2025-11-03 | 2025-11-23 | 21 | 2025-04-28 | Rhoads Industries
PM8 | BURLINGTON | T-EPF 10 | VR (Z) MSC | ACTIVE | 2025-11-03 | 2025-11-23 | 21 | 2025-04-28 | Rhoads Industries
PM1 | OSCAR V PETERSON | T-AO 206 | VR (Z) MSC | ACTIVE | 2025-11-03 | 2025-11-16 | 14 | 2025-06-26 | CTF 80
PM2 | SBX-1 | SBX 1 | ROH (MSC) | ACTIVE | 2025-11-07 | 2026-02-28 | 114 | 2025-07-17 | Pearl Harbor Navy Shipyard
PM1 | ROBERT F KENNEDY | T-AO 208 | VR (Z) MSC | ACTIVE | 2025-11-08 | 2025-11-15 | 8 | 2025-04-17 | CTF 80
PM1 | BIG HORN | T-AO 198 | VR (Z) MSC | ACTIVE | 2025-11-09 | 2025-11-25 | 17 | 2023-04-03 | C7F
PM3 | MIGUEL KEITH | ESB 5 | MTA (MSC) | ACTIVE | 2025-11-10 | 2025-12-24 | 45 | 2025-05-30 | C7F
PM8 | POINT LOMA | T-EPF 15 | VR (Z) MSC | ACTIVE | 2025-11-10 | 2025-11-26 | 17 | 2025-08-05 | NORFOLK
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2025-11-10 | 2025-12-09 | 30 | 2025-09-25 | CROATIA
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2025-11-10 | 2025-11-23 | 14 | 2025-08-21 | C5F
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | ACTIVE | 2025-11-10 | 2025-11-23 | 14 | 2025-07-11 | C7F
PM2 | HOWARD O LORENZEN | T-AGM 25 | VR (Z) MSC | ACTIVE | 2025-11-10 | 2025-11-30 | 21 | 2025-07-17 | C7F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2025-11-10 | 2025-11-21 | 12 | 2025-06-27 | CTF 80
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2025-11-12 | 2025-12-01 | 20 | 2025-09-18 | C3F
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2025-11-23 | 2025-12-07 | 15 | 2025-09-11 | C5F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2025-11-24 | 2025-12-08 | 15 | 2025-04-08 | C6F
PM2 | BOWDITCH | T-AGS 62 | VR (Z) MSC | ACTIVE | 2025-11-24 | 2025-12-12 | 19 | 2025-07-02 | C7F
PM1 | TIPPECANOE | T-AO 199 | ROH / DD (MSC) | ACTIVE | 2025-12-01 | 2026-04-01 | 122 | 2025-07-23 | C7F
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2025-12-01 | 2025-12-15 | 15 | 2025-08-07 | CTF 80
PM8 | NEWPORT | T-EPF 12 | VR (Z) MSC | ACTIVE | 2025-12-01 | 2025-12-22 | 22 | 2025-08-11 | CTF 80
PM1 | KANAWHA | T-AO 196 | VR (Z) MSC | ACTIVE | 2025-12-01 | 2025-12-15 | 15 | 2025-04-08 | C5F
PM1 | LEROY GRUMMAN | T-AO 195 | VR (Z) MSC | ACTIVE | 2025-12-01 | 2025-12-15 | 15 | 2025-06-05 | CTF 80
PM1 | ROBERT F KENNEDY | T-AO 208 | VR (Z) MSC | ACTIVE | 2025-12-01 | 2026-01-09 | 40 | 2025-03-12 | CTF 80
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | ACTIVE | 2025-12-05 | 2025-12-19 | 15 | 2025-08-27 | Joint Base Pearl Harbor Hickam
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | ROH / DD (MSC) | ACTIVE | 2025-12-08 | 2026-03-09 | 92 | 2025-02-12 | C3F
PM6 | AMELIA EARHART | T-AKE 6 | MTA (MSC) | ACTIVE | 2025-12-15 | 2026-03-24 | 100 | 2025-07-10 | C7F
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | CANCELED | 2026-01-01 | 2026-01-14 | 14 | 2025-03-25
PM1 | PECOS | T-AO 197 | VR (Z) MSC | CANCELED | 2026-01-01 | 2026-01-14 | 14 | 2025-05-29
PM2 | LOYAL | T-AGOS 22 | VR (Z) MSC | ACTIVE | 2026-01-02 | 2026-01-31 | 30 | 2025-09-16 | C7F
PM1 | HENRY J KAISER | T-AO 187 | VR (Z) MSC | ACTIVE | 2026-01-04 | 2026-02-02 | 30 | 2025-08-07 | C3F
PM6 | CESAR CHAVEZ | T-AKE 14 | ROH (MSC) | ACTIVE | 2026-01-05 | 2026-03-05 | 60 | 2025-02-21 | C7F
PM8 | CITY OF BISMARCK | T-EPF 9 | ROH / DD (MSC) | ACTIVE | 2026-01-05 | 2026-04-04 | 90 | 2025-09-14 | THAILAND
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2026-01-05 | 2026-01-18 | 14 | 2024-01-05 | C7F
PM2 | BRUCE C HEEZEN | T-AGS 64 | VR (Z) MSC | ACTIVE | 2026-01-05 | 2026-01-23 | 19 | 2025-07-02 | C6F
PM2 | PATHFINDER | T-AGS 60 | VR (Z) MSC | ACTIVE | 2026-01-05 | 2026-01-23 | 19 | 2025-07-10 | CTF 80
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | CANCELED | 2026-01-05 | 2026-02-04 | 31 | 2024-03-08
PM4 | GRASP | T-ARS 51 | MTA (MSC) | ACTIVE | 2026-01-12 | 2026-03-12 | 60 | 2025-08-11 | C3F
PM3 | VADM K R WHEELER | T-AG 5001 | ROH / DD (MSC) | ACTIVE | 2026-01-12 | 2026-02-25 | 45 | 2025-07-22 | C3F
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2026-01-12 | 2026-01-25 | 14 | 2025-02-28 | C7F
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | ACTIVE | 2026-01-12 | 2026-01-25 | 14 | 2025-08-11 | C5F
PM4 | COMFORT | T-AH 20 | MTA (MSC) | ACTIVE | 2026-01-15 | 2026-04-26 | 102 | 2024-08-30 | CTF 80
PM3 | PILILAAU | T-AKR 304 | VR (Z) MSC | ACTIVE | 2026-01-15 | 2026-02-04 | 21 | 2025-07-25 | C7F
PM1 | JOHN LEWIS | T-AO 205 | VR (Z) MSC | ACTIVE | 2026-01-16 | 2026-01-29 | 14 | 2024-03-21 | C7F
PM2 | MARIE THARP | T-AGS 66 | ROH (MSC) | ACTIVE | 2026-01-19 | 2026-03-20 | 61 | 2025-04-07 | C6F
PM1 | LARAMIE | T-AO 203 | VR (Z) MSC | ACTIVE | 2026-01-20 | 2026-02-02 | 14 | 2025-08-07 | CTF 80
PM8 | YUMA | T-EPF 8 | VR (Z) MSC | ACTIVE | 2026-01-26 | 2026-02-15 | 21 | 2025-04-28 | Rhoads Industries
PM8 | BURLINGTON | T-EPF 10 | VR (Z) MSC | ACTIVE | 2026-01-26 | 2026-02-15 | 21 | 2025-04-28 | Rhoads Industries
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | ACTIVE | 2026-01-26 | 2026-02-08 | 14 | 2025-08-20 | GUAM
PM2 | ABLE | T-AGOS 20 | VR (Z) MSC | ACTIVE | 2026-01-30 | 2026-03-15 | 45 | 2025-07-18 | C7F
PM1 | LEROY GRUMMAN | T-AO 195 | MTA (MSC) | ACTIVE | 2026-02-01 | 2026-04-17 | 76 | 2025-01-17 | CTF 80
PM1 | YUKON | T-AO 202 | ROH / DD (MSC) | ACTIVE | 2026-02-01 | 2026-05-11 | 100 | 2025-07-23 | C7F
PM6 | SACAGAWEA | T-AKE 2 | VR (Z) MSC | ACTIVE | 2026-02-02 | 2026-02-23 | 22 | 2024-10-31 | C7F
PM1 | JOHN LENTHALL | T-AO 189 | VR (Z) MSC | ACTIVE | 2026-02-03 | 2026-02-17 | 15 | 2023-07-27 | C6F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2026-02-10 | 2026-02-23 | 14 | 2022-08-04 | CTF 80
PM1 | BIG HORN | T-AO 198 | VR (Z) MSC | ACTIVE | 2026-02-16 | 2026-03-02 | 15 | 2025-08-06 | C7F
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2026-02-16 | 2026-03-02 | 15 | 2025-04-24 | C5F
PM2 | HENSON | T-AGS 63 | ROH (MSC) | ACTIVE | 2026-02-19 | 2026-04-21 | 62 | 2025-07-17 | C7F
PM1 | OSCAR V PETERSON | T-AO 206 | MTA (MSC) | ACTIVE | 2026-02-20 | 2026-05-18 | 88 | 2025-08-14 | CTF 80
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2026-02-23 | 2026-03-08 | 14 | 2025-08-07 | CTF 80
PM8 | APALACHICOLA | T-EPF 13 | VR (Z) MSC | ACTIVE | 2026-02-23 | 2026-04-08 | 45 | 2025-07-29 | NORFOLK
PM8 | BRUNSWICK | T-EPF 6 | VR (Z) MSC | ACTIVE | 2026-02-23 | 2026-04-05 | 42 | 2025-07-29 | NORFOLK
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2026-02-25 | 2026-03-06 | 10 | 2025-07-30 | C7F
PM2 | LOYAL | T-AGOS 22 | VR (Z) MSC | ACTIVE | 2026-02-28 | 2026-04-13 | 45 | 2025-07-18 | C7F
PM2 | HOWARD O LORENZEN | T-AGM 25 | MTA (MSC) | ACTIVE | 2026-03-01 | 2026-04-14 | 45 | 2025-04-18 | C7F
PM2 | WATERS | T-AGS 45 | VR (Z) MSC | ACTIVE | 2026-03-01 | 2026-03-31 | 31 | 2025-04-07 | CTF 80
PM3 | SEAY | T-AKR 302 | VR (Z) MSC | ACTIVE | 2026-03-01 | 2026-03-21 | 21 | 2025-07-25 | C7F
PM1 | ROBERT F KENNEDY | T-AO 208 | PSA (MSC) | ACTIVE | 2026-03-02 | 2026-07-15 | 136 | 2025-05-09 | CTF 80
PM3 | JOHN L CANLEY | ESB 6 | ROH (MSC) | ACTIVE | 2026-03-02 | 2026-05-16 | 76 | 2025-04-25 | C7F
PM6 | SUPPLY | T-AOE 6 | ROH / DD (MSC) | ACTIVE | 2026-03-02 | 2026-08-14 | 166 | 2025-02-28 | CTF 80
PM8 | CHOCTAW COUNTY | T-EPF 2 | VR (Z) MSC | CANCELED | 2026-03-02 | 2026-04-30 | 60 | 2024-04-24 | C2F
PM1 | JOHN ERICSSON | T-AO 194 | ROH (MSC) | DEFERRED | 2026-03-03 | 2026-06-21 | 111 | 2024-01-04
PM2 | WESTWIND | T-AGSE 2 | VR (Z) MSC | ACTIVE | 2026-03-03 | 2026-03-13 | 11 | 2025-05-13 | CTF 80
PM3 | DAHL | T-AKR 312 | ROH / DD (MSC) | ACTIVE | 2026-03-05 | 2026-07-03 | 121 | 2025-07-21 | CTF 80
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2026-03-06 | 2026-03-20 | 15 | 2025-09-18 | CTF 80
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2026-03-09 | 2026-03-22 | 14 | 2025-07-24 | C7F
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2026-03-09 | 2026-03-20 | 12 | 2025-07-25 | CROATIA
PM1 | EARL WARREN | T-AO 207 | VR (Z) MSC | CANCELED | 2026-03-11 | 2026-03-24 | 14 | 2024-10-11 | C7F
PM2 | BOWDITCH | T-AGS 62 | ROH (MSC) | ACTIVE | 2026-03-16 | 2026-06-13 | 90 | 2025-07-17 | C7F
PM3 | JOHN GLENN | T-ESD 2 | VR (Z) MSC | ACTIVE | 2026-03-17 | 2026-04-07 | 22 | 2025-07-25 | C3F
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2026-03-19 | 2026-04-09 | 22 | 2025-09-11 | CTF 80
PM4 | MERCY | T-AH 19 | ROH / DD (MSC) | ACTIVE | 2026-03-20 | 2026-09-20 | 185 | 2025-09-08 | C3F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | MTA (MSC) | ACTIVE | 2026-03-23 | 2026-06-07 | 77 | 2025-05-08 | CTF 80
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2026-03-29 | 2026-04-11 | 14 | 2023-12-10 | C7F
PM2 | VICTORIOUS | T-AGOS 19 | VR (Z) MSC | ACTIVE | 2026-03-29 | 2026-05-12 | 45 | 2025-07-18 | C7F
PM6 | RICHARD E BYRD | T-AKE 4 | ROH (MSC) | ACTIVE | 2026-03-30 | 2026-05-28 | 60 | 2025-03-28 | C7F
PM8 | CODY | T-EPF 14 | ROH / DD (MSC) | ACTIVE | 2026-03-30 | 2026-06-27 | 90 | 2025-08-07 | CTF 80
PM1 | KANAWHA | T-AO 196 | VR (Z) MSC | ACTIVE | 2026-03-30 | 2026-04-12 | 14 | 2023-06-05 | C6F
PM1 | JOHN LENTHALL | T-AO 189 | VR (Z) MSC | ACTIVE | 2026-03-30 | 2026-04-12 | 14 | 2023-07-27 | C6F
PM2 | MARY SEARS | T-AGS 65 | VR (Z) MSC | ACTIVE | 2026-03-30 | 2026-04-17 | 19 | 2025-07-02 | C7F
PM6 | MATTHEW PERRY | T-AKE 9 | MTA (MSC) | ACTIVE | 2026-04-01 | 2026-09-30 | 183 | 2025-09-14 | C3F
PM6 | ROBERT E PEARY | T-AKE 5 | ROH (MSC) | ACTIVE | 2026-04-01 | 2026-06-01 | 62 | 2025-03-09 | CTF 80
PM2 | EFFECTIVE | T-AGOS 21 | ROH (MSC) | ACTIVE | 2026-04-01 | 2026-05-29 | 59 | 2025-09-16 | C7F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2026-04-01 | 2026-04-14 | 14 | 2025-07-25 | C7F
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | ACTIVE | 2026-04-01 | 2026-04-21 | 21 | 2025-08-05 | Port of Orange
PM8 | NEWPORT | T-EPF 12 | VR (Z) MSC | ACTIVE | 2026-04-01 | 2026-04-21 | 21 | 2025-08-05 | Port of Orange
PM8 | CARSON CITY | T-EPF 7 | VR (Z) MSC | ACTIVE | 2026-04-01 | 2026-04-21 | 21 | 2025-08-05 | Port of Orange
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | ACTIVE | 2026-04-06 | 2026-04-19 | 14 | 2025-08-11 | C5F
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2026-04-07 | 2026-04-27 | 21 | 2025-05-08 | C6F
PM8 | PUERTO RICO | T-EPF 11 | VR (Z) MSC | ACTIVE | 2026-04-13 | 2026-05-03 | 21 | 2025-04-27 | C7F
PM1 | LARAMIE | T-AO 203 | ROH (MSC) | ACTIVE | 2026-04-20 | 2026-07-29 | 101 | 2025-01-17 | CTF 80
PM4 | SALVOR | T-ARS 52 | ROH / DD (MSC) | ACTIVE | 2026-04-20 | 2026-06-18 | 60 | 2025-08-11 | C7F
PM1 | JOHN LEWIS | T-AO 205 | VR (Z) MSC | ACTIVE | 2026-04-24 | 2026-05-07 | 14 | 2025-08-20 | GUAM
PM3 | VADM K R WHEELER | T-AG 5001 | VR (Z) MSC | ACTIVE | 2026-04-25 | 2026-05-08 | 14 | 2025-08-08 | C3F
PM8 | YUMA | T-EPF 8 | VR (Z) MSC | ACTIVE | 2026-04-27 | 2026-05-17 | 21 | 2025-04-28 | Rhoads Industries
PM8 | BURLINGTON | T-EPF 10 | VR (Z) MSC | ACTIVE | 2026-04-27 | 2026-05-17 | 21 | 2025-04-28 | Rhoads Industries
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | DEFERRED | 2026-04-27 | 2026-05-11 | 15 | 2025-02-21
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2026-04-28 | 2026-05-07 | 10 | 2025-07-30 | C7F
PM4 | EMORY S LAND | AS 39 | ROH / DD (MSC) | ACTIVE | 2026-05-01 | 2026-12-01 | 215 | 2025-04-15 | C3F
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2026-05-01 | 2026-05-30 | 30 | 2025-09-03 | GUAM
PM1 | PECOS | T-AO 197 | VR (Z) MSC | CANCELED | 2026-05-01 | 2026-05-14 | 14 | 2025-05-29
PM2 | ARROWHEAD | T-AGSE 4 | MTA (MSC) | ACTIVE | 2026-05-04 | 2026-06-18 | 46 | 2025-05-23 | C3F
PM3 | PFC DEWAYNE T WILLIAMS | T-AK 3009 | ROH / DD (MSC) | ACTIVE | 2026-05-04 | 2026-08-31 | 120 | 2025-07-25 | C2F
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2026-05-10 | 2026-05-23 | 14 | 2024-01-05 | C3F
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2026-05-11 | 2026-05-24 | 14 | 2024-01-05 | C7F
PM1 | SOJOURNER TRUTH | T-AO 210 | PDA | ACTIVE | 2026-05-13 | 2026-07-15 | 64 | 2025-08-20 | CTF 80
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2026-05-14 | 2026-05-27 | 14 | 2025-02-21 | C7F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | MTA (MSC) | ACTIVE | 2026-05-22 | 2026-09-30 | 132 | 2025-09-25 | East Coast Repair & Fabrication
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | ACTIVE | 2026-05-22 | 2026-06-04 | 14 | 2025-02-21 | C3F
PM6 | CARL BRASHEAR | T-AKE 7 | MTA (MSC) | ACTIVE | 2026-05-25 | 2026-07-13 | 50 | 2025-09-03 | GUAM
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2026-05-26 | 2026-06-08 | 14 | 2025-04-07 | C6F
PM8 | APALACHICOLA | T-EPF 13 | VR (Z) MSC | ACTIVE | 2026-06-01 | 2026-06-21 | 21 | 2025-07-29 | NORFOLK
PM8 | BRUNSWICK | T-EPF 6 | VR (Z) MSC | ACTIVE | 2026-06-01 | 2026-06-21 | 21 | 2025-07-29 | NORFOLK
PM2 | EAGLEVIEW | T-AGSE 3 | VR (Z) MSC | ACTIVE | 2026-06-01 | 2026-06-15 | 15 | 2025-07-17 | C3F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | ROH (MSC) | ACTIVE | 2026-06-02 | 2026-09-30 | 121 | 2025-09-25
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2026-06-03 | 2026-06-16 | 14 | 2025-03-20 | C7F
PM1 | PATUXENT | T-AO 201 | MTA (MSC) | ACTIVE | 2026-06-08 | 2026-08-22 | 76 | 2023-06-05 | CTF 80
PM8 | CARSON CITY | T-EPF 7 | VR (Z) MSC | ACTIVE | 2026-06-08 | 2026-06-28 | 21 | 2025-04-03 | CTF 80
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | ACTIVE | 2026-06-08 | 2026-06-28 | 21 | 2025-04-28 | CTF 80
PM2 | PATHFINDER | T-AGS 60 | VR (Z) MSC | ACTIVE | 2026-06-08 | 2026-06-26 | 19 | 2025-07-10 | CTF 80
PM8 | NEWPORT | T-EPF 12 | VR (Z) MSC | ACTIVE | 2026-06-08 | 2026-06-28 | 21 | 2025-08-22 | CTF 80
PM1 | EARL WARREN | T-AO 207 | VR (Z) MSC | ACTIVE | 2026-06-09 | 2026-06-22 | 14 | 2024-03-16 | C7F
PM3 | LEWIS B PULLER | ESB 3 | MTA (MSC) | ACTIVE | 2026-06-15 | 2026-09-30 | 108 | 2025-09-25 | CROATIA
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2026-06-15 | 2026-06-28 | 14 | 2025-08-11 | C3F
PM3 | ROBERT E SIMANEK | ESB 7 | VR (Z) MSC | ACTIVE | 2026-06-15 | 2026-06-28 | 14 | 2025-08-08 | CTF 80
PM4 | BILLY FRANK JR | T-ATS 11 | VR (Z) MSC | ACTIVE | 2026-06-17 | 2026-06-30 | 14 | 2025-07-28 | C7F
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | ACTIVE | 2026-06-22 | 2026-07-05 | 14 | 2025-08-11 | C5F
PM2 | IMPECCABLE | T-AGOS 23 | VR (Z) MSC | ACTIVE | 2026-06-26 | 2026-08-09 | 45 | 2025-08-08 | C7F
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2026-06-26 | 2026-07-05 | 10 | 2025-07-30 | C7F
PM2 | EFFECTIVE | T-AGOS 21 | VR (Z) MSC | ACTIVE | 2026-06-28 | 2026-08-11 | 45 | 2025-07-18 | C7F
PM2 | ABLE | T-AGOS 20 | MTA (MSC) | ACTIVE | 2026-07-01 | 2026-08-29 | 60 | 2025-07-18 | C7F
PM4 | MOUNT WHITNEY | LCC 20 | VR (Z) MSC | ACTIVE | 2026-07-01 | 2026-07-14 | 14 | 2025-08-11 | C6F
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2026-07-01 | 2026-08-30 | 61 | 2025-09-03 | GUAM
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2026-07-01 | 2026-07-14 | 14 | 2025-07-25 | C7F
PM3 | JOHN GLENN | T-ESD 2 | VR (Z) MSC | ACTIVE | 2026-07-01 | 2026-07-21 | 21 | 2025-07-25 | C3F
PM3 | MONTFORD POINT | T-ESD 1 | VR (Z) MSC | ACTIVE | 2026-07-01 | 2026-07-21 | 21 | 2025-07-25 | C2F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | CANCELED | 2026-07-01 | 2026-07-16 | 16 | 2025-03-14
PM2 | LOYAL | T-AGOS 22 | ROH (MSC) | ACTIVE | 2026-07-02 | 2026-08-30 | 60 | 2025-07-18 | C7F
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2026-07-06 | 2026-07-19 | 14 | 2025-03-28 | C5F
PM8 | CITY OF BISMARCK | T-EPF 9 | VR (Z) MSC | ACTIVE | 2026-07-06 | 2026-07-26 | 21 | 2025-04-01 | C7F
PM2 | BRUCE C HEEZEN | T-AGS 64 | VR (Z) MSC | ACTIVE | 2026-07-06 | 2026-07-24 | 19 | 2025-07-02 | CTF 80
PM1 | EARL WARREN | T-AO 207 | MTA (MSC) | ACTIVE | 2026-07-11 | 2026-08-22 | 43 | 2025-07-11 | C7F
PM1 | KANAWHA | T-AO 196 | MTA (MSC) | ACTIVE | 2026-07-13 | 2026-09-26 | 76 | 2025-01-17 | CTF 80
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2026-07-20 | 2026-08-02 | 14 | 2024-01-05 | C7F
PM3 | VADM K R WHEELER | T-AG 5001 | VR (Z) MSC | ACTIVE | 2026-07-21 | 2026-08-03 | 14 | 2025-08-08 | C3F
PM1 | OSCAR V PETERSON | T-AO 206 | VR (Z) MSC | ACTIVE | 2026-07-21 | 2026-08-03 | 14 | 2025-06-26 | C6F
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2026-07-26 | 2026-08-08 | 14 | 2023-12-10 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | ROH / DD (MSC) | ACTIVE | 2026-07-27 | 2026-10-25 | 91 | 2022-07-22 | CTF 80
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | ACTIVE | 2026-07-27 | 2026-08-10 | 15 | 2025-08-20 | GUAM
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | ACTIVE | 2026-07-27 | 2026-08-10 | 15 | 2025-08-27 | C7F
PM4 | COMFORT | T-AH 20 | VR (Z) MSC | ACTIVE | 2026-08-01 | 2026-08-30 | 30 | 2025-08-11 | CTF 80
PM6 | SACAGAWEA | T-AKE 2 | VR (Z) MSC | ACTIVE | 2026-08-01 | 2026-09-14 | 45 | 2024-10-31 | C7F
PM2 | MARIE THARP | T-AGS 66 | VR (Z) MSC | ACTIVE | 2026-08-01 | 2026-08-18 | 18 | 2025-04-07 | C6F
PM3 | SEAY | T-AKR 302 | VR (Z) MSC | ACTIVE | 2026-08-01 | 2026-08-14 | 14 | 2025-07-25 | C7F
PM8 | POINT LOMA | T-EPF 15 | PSA (MSC) | ACTIVE | 2026-08-03 | 2026-10-31 | 90 | 2025-06-06 | CTF 80
PM1 | LEROY GRUMMAN | T-AO 195 | VR (Z) MSC | ACTIVE | 2026-08-03 | 2026-08-17 | 15 | 2023-07-27 | C6F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2026-08-10 | 2026-08-24 | 15 | 2024-09-14 | C6F
PM8 | CODY | T-EPF 14 | VR (Z) MSC | ACTIVE | 2026-08-10 | 2026-08-30 | 21 | 2025-08-15 | CTF 80
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2026-08-10 | 2026-08-23 | 14 | 2025-04-07 | C6F
PM8 | PUERTO RICO | T-EPF 11 | VR (Z) MSC | ACTIVE | 2026-08-10 | 2026-08-31 | 22 | 2025-04-02 | C7F
PM1 | JOHN LENTHALL | T-AO 189 | MTA (MSC) | ACTIVE | 2026-08-15 | 2026-10-30 | 77 | 2023-07-27 | CTF 80
PM2 | SBX-1 | SBX 1 | VR (Z) MSC | ACTIVE | 2026-08-15 | 2026-10-24 | 71 | 2025-08-08 | C3F
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2026-08-18 | 2026-08-31 | 14 | 2025-03-20 | C7F
PM6 | MEDGAR EVERS | T-AKE 13 | MTA (MSC) | ACTIVE | 2026-08-19 | 2026-10-07 | 50 | 2025-09-11 | CTF 80
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2026-08-25 | 2026-09-04 | 11 | 2025-07-30 | C7F
PM4 | EMORY S LAND | AS 39 | VR (Z) MSC | CANCELED | 2026-08-30 | 2026-09-28 | 30 | 2024-03-08 | C7F
PM2 | MARY SEARS | T-AGS 65 | ROH (MSC) | ACTIVE | 2026-08-31 | 2026-11-28 | 90 | 2025-04-07 | C7F
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | ACTIVE | 2026-08-31 | 2026-09-14 | 15 | 2025-08-08 | C7F
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2026-08-31 | 2026-09-14 | 15 | 2025-08-08 | C7F
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | CANCELED | 2026-08-31 | 2026-09-13 | 14 | 2025-02-21 | C7F
PM1 | PECOS | T-AO 197 | ROH (MSC) | CANCELED | 2026-09-01 | 2026-11-09 | 70 | 2025-05-29
PM4 | BILLY FRANK JR | T-ATS 11 | VR (Z) MSC | ACTIVE | 2026-09-01 | 2026-09-14 | 14 | 2025-07-28 | C7F
PM1 | ROBERT F KENNEDY | T-AO 208 | VR (Z) MSC | ACTIVE | 2026-09-04 | 2026-09-17 | 14 | 2025-08-08 | CTF 80
PM6 | ALAN SHEPARD | T-AKE 3 | MTA (MSC) | ACTIVE | 2026-09-05 | 2026-10-24 | 50 | 2024-01-05 | C3F
PM1 | JOHN LEWIS | T-AO 205 | MTA (MSC) | ACTIVE | 2026-09-07 | 2026-10-19 | 43 | 2025-08-20 | GUAM
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | ACTIVE | 2026-09-07 | 2026-09-20 | 14 | 2025-08-11 | C7F
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | ACTIVE | 2026-09-08 | 2026-09-28 | 21 | 2025-04-15 | CTF 80
PM8 | NEWPORT | T-EPF 12 | VR (Z) MSC | CANCELED | 2026-09-08 | 2026-09-28 | 21 | 2025-07-24 | CTF 80
PM8 | CARSON CITY | T-EPF 7 | VR (Z) MSC | ACTIVE | 2026-09-08 | 2026-09-28 | 21 | 2025-04-28 | C2F
PM2 | HENSON | T-AGS 63 | VR (Z) MSC | ACTIVE | 2026-09-11 | 2026-09-29 | 19 | 2025-07-02 | C7F
PM4 | CATAWBA | T-ATF 168 | MTA (MSC) | ACTIVE | 2026-09-14 | 2026-11-12 | 60 | 2025-08-11 | C5F
PM8 | PUERTO RICO | T-EPF 11 | ROH / DD (MSC) | ACTIVE | 2026-09-14 | 2026-12-12 | 90 | 2025-07-24 | C7F
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2026-09-14 | 2026-09-27 | 14 | 2025-08-11 | C3F
PM3 | PILILAAU | T-AKR 304 | VR (Z) MSC | ACTIVE | 2026-09-14 | 2026-09-27 | 14 | 2025-07-25 | C7F
PM3 | ROBERT E SIMANEK | ESB 7 | MTA (MSC) | ACTIVE | 2026-09-15 | 2026-10-31 | 47 | 2025-08-08 | CTF 80
PM1 | GUADALUPE | T-AO 200 | MTA (MSC) | ACTIVE | 2026-09-20 | 2026-12-03 | 75 | 2025-01-17 | C3F
PM2 | VICTORIOUS | T-AGOS 19 | MTA (MSC) | ACTIVE | 2026-09-24 | 2026-11-22 | 60 | 2025-08-08 | C7F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2026-09-29 | 2026-10-10 | 12 | 2025-03-10 | CTF 80
PM4 | MOUNT WHITNEY | LCC 20 | MTA (MSC) | ACTIVE | 2026-10-01 | 2026-11-29 | 60 | 2025-01-10 | C6F
PM8 | GUAM | HST 1 | ROH / DD (MSC) | ACTIVE | 2026-10-01 | 2026-12-15 | 76 | 2025-07-30 | C7F
PM1 | HENRY J KAISER | T-AO 187 | VR (Z) MSC | ACTIVE | 2026-10-01 | 2026-10-14 | 14 | 2025-08-07 | C3F
PM4 | MERCY | T-AH 19 | VR (Z) MSC | ACTIVE | 2026-10-04 | 2026-10-18 | 15 | 2025-06-04 | C3F
PM6 | AMELIA EARHART | T-AKE 6 | ROH (MSC) | ACTIVE | 2026-10-05 | 2026-12-03 | 60 | 2024-01-05 | C7F
PM2 | BLACK POWDER | T-AGSE 1 | ROH (MSC) | ACTIVE | 2026-10-06 | 2026-11-10 | 36 | 2025-08-08 | CTF 80
PM8 | CITY OF BISMARCK | T-EPF 9 | MTA (MSC) | ACTIVE | 2026-10-07 | 2026-12-20 | 75 | 2025-04-01 | C7F
PM6 | CHARLES DREW | T-AKE 10 | MTA (MSC) | ACTIVE | 2026-10-12 | 2026-11-30 | 50 | 2024-01-04 | C7F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2026-10-12 | 2026-10-25 | 14 | 2025-03-28 | C5F
PM1 | LARAMIE | T-AO 203 | VR (Z) MSC | ACTIVE | 2026-10-12 | 2026-10-26 | 15 | 2025-08-07 | CTF 80
PM8 | APALACHICOLA | T-EPF 13 | VR (Z) MSC | ACTIVE | 2026-10-14 | 2026-11-03 | 21 | 2025-07-29 | NORFOLK
PM8 | BRUNSWICK | T-EPF 6 | VR (Z) MSC | ACTIVE | 2026-10-14 | 2026-11-03 | 21 | 2025-07-24 | C2F
PM3 | VADM K R WHEELER | T-AG 5001 | VR (Z) MSC | ACTIVE | 2026-10-16 | 2026-10-29 | 14 | 2025-08-08 | C3F
PM2 | MARIE THARP | T-AGS 66 | VR (Z) MSC | ACTIVE | 2026-10-19 | 2026-11-06 | 19 | 2025-07-02 | C6F
PM6 | CESAR CHAVEZ | T-AKE 14 | MTA (MSC) | ACTIVE | 2026-10-20 | 2026-12-08 | 50 | 2023-12-10 | C7F
PM4 | NAVAJO | T-ATS 6 | VR (Z) MSC | ACTIVE | 2026-10-24 | 2026-11-06 | 14 | 2025-07-28 | C3F
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | ACTIVE | 2026-10-25 | 2026-11-08 | 15 | 2025-08-07 | C7F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2026-10-25 | 2026-11-07 | 14 | 2025-02-21 | C7F
PM6 | WALLY SCHIRRA | T-AKE 8 | MTA (MSC) | ACTIVE | 2026-10-26 | 2026-12-14 | 50 | 2025-09-18 | C3F
PM3 | MIGUEL KEITH | ESB 5 | MTA (MSC) | ACTIVE | 2026-10-26 | 2026-12-10 | 46 | 2024-05-06 | C7F
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2026-10-28 | 2026-11-10 | 14 | 2025-04-24 | C7F
PM4 | COMFORT | T-AH 20 | VR (Z) MSC | ACTIVE | 2026-11-01 | 2026-11-21 | 21 | 2025-08-11 | CTF 80
PM8 | CODY | T-EPF 14 | VR (Z) MSC | ACTIVE | 2026-11-01 | 2026-11-21 | 21 | 2025-08-15 | C7F
PM3 | MONTFORD POINT | T-ESD 1 | VR (Z) MSC | ACTIVE | 2026-11-01 | 2026-11-21 | 21 | 2025-07-25 | C2F
PM3 | 1ST LT JACK LUMMUS | T-AK 3011 | VR (Z) MSC | ACTIVE | 2026-11-01 | 2026-11-23 | 23 | 2025-07-25 | C7F
PM3 | DAHL | T-AKR 312 | VR (Z) MSC | ACTIVE | 2026-11-01 | 2026-11-15 | 15 | 2025-07-25 | C7F
PM3 | PILILAAU | T-AKR 304 | VR (Z) MSC | ACTIVE | 2026-11-01 | 2026-11-14 | 14 | 2025-07-25 | C7F
PM3 | SEAY | T-AKR 302 | VR (Z) MSC | ACTIVE | 2026-11-01 | 2026-11-14 | 14 | 2025-07-25 | C7F
PM3 | SGT WILLIAM R BUTTON | T-AK 3012 | VR (Z) MSC | ACTIVE | 2026-11-01 | 2026-11-15 | 15 | 2025-07-25 | C7F
PM3 | SISLER | T-AKR 311 | VR (Z) MSC | ACTIVE | 2026-11-01 | 2026-11-15 | 15 | 2025-07-25 | C7F
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2026-11-02 | 2026-11-16 | 15 | 2025-08-07 | CTF 80
PM8 | YUMA | T-EPF 8 | VR (Z) MSC | ACTIVE | 2026-11-02 | 2026-11-22 | 21 | 2025-08-15 | Rhoads Industries
PM8 | BURLINGTON | T-EPF 10 | VR (Z) MSC | ACTIVE | 2026-11-02 | 2026-11-22 | 21 | 2025-08-19 | CTF 80
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2026-11-03 | 2026-11-16 | 14 | 2025-04-03 | CTF 80
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2026-11-04 | 2026-11-18 | 15 | 2024-09-14 | C6F
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2026-11-06 | 2026-11-19 | 14 | 2025-02-28 | CTF 80
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2026-11-09 | 2026-11-23 | 15 | 2025-03-09 | CTF 80
PM1 | LEROY GRUMMAN | T-AO 195 | VR (Z) MSC | ACTIVE | 2026-11-09 | 2026-11-23 | 15 | 2023-07-27 | C6F
PM2 | HOWARD O LORENZEN | T-AGM 25 | VR (Z) MSC | ACTIVE | 2026-11-09 | 2026-11-23 | 15 | 2025-07-17 | C7F
PM2 | ARROWHEAD | T-AGSE 4 | VR (Z) MSC | ACTIVE | 2026-11-12 | 2026-11-21 | 10 | 2025-07-17 | C3F
PM2 | ABLE | T-AGOS 20 | VR (Z) MSC | ACTIVE | 2026-11-15 | 2026-12-29 | 45 | 2025-08-08 | C7F
PM4 | BILLY FRANK JR | T-ATS 11 | VR (Z) MSC | ACTIVE | 2026-11-16 | 2026-11-29 | 14 | 2025-07-28 | C7F
PM2 | BOWDITCH | T-AGS 62 | VR (Z) MSC | ACTIVE | 2026-11-16 | 2026-12-04 | 19 | 2025-07-02 | C7F
PM2 | PATHFINDER | T-AGS 60 | VR (Z) MSC | ACTIVE | 2026-11-17 | 2026-12-05 | 19 | 2025-07-10 | CTF 80
PM3 | PFC DEWAYNE T WILLIAMS | T-AK 3009 | VR (Z) MSC | ACTIVE | 2026-11-22 | 2026-12-13 | 22 | 2025-07-25 | C7F
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2026-11-30 | 2026-12-14 | 15 | 2025-08-08 | C7F
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | ACTIVE | 2026-11-30 | 2026-12-14 | 15 | 2025-08-27 | C7F
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | DEFERRED | 2026-11-30 | 2026-12-20 | 21 | 2024-12-02
PM1 | RAPPAHANNOCK | T-AO 204 | MTA (MSC) | ACTIVE | 2026-12-01 | 2027-02-14 | 76 | 2025-02-21 | C7F
PM8 | NEWPORT | T-EPF 12 | VR (Z) MSC | ACTIVE | 2026-12-01 | 2026-12-21 | 21 | 2025-07-29 | Port of Orange
PM1 | ROBERT F KENNEDY | T-AO 208 | VR (Z) MSC | ACTIVE | 2026-12-01 | 2026-12-14 | 14 | 2025-08-08 | CTF 80
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2026-12-01 | 2026-12-15 | 15 | 2025-07-25 | C6F
PM8 | CARSON CITY | T-EPF 7 | VR (Z) MSC | ACTIVE | 2026-12-01 | 2026-12-21 | 21 | 2025-04-28 | C2F
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2026-12-03 | 2026-12-17 | 15 | 2025-07-16 | C5F
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | ACTIVE | 2026-12-07 | 2026-12-20 | 14 | 2025-08-11 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2026-12-07 | 2027-01-15 | 40 | 2025-04-03 | CTF 80
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2026-12-07 | 2026-12-20 | 14 | 2025-03-10 | CTF 80
PM1 | HENRY J KAISER | T-AO 187 | ROH (MSC) | ACTIVE | 2026-12-15 | 2027-04-13 | 120 | 2025-02-21 | C3F
PM2 | LOYAL | T-AGOS 22 | VR (Z) MSC | ACTIVE | 2026-12-28 | 2027-01-26 | 30 | 2025-08-08 | C7F
PM4 | MOUNT WHITNEY | LCC 20 | VR (Z) MSC | ACTIVE | 2027-01-01 | 2027-01-14 | 14 | 2025-08-11 | C6F
PM1 | PECOS | T-AO 197 | VR (Z) MSC | CANCELED | 2027-01-01 | 2027-01-14 | 14 | 2025-05-29
PM6 | SACAGAWEA | T-AKE 2 | VR (Z) MSC | ACTIVE | 2027-01-04 | 2027-01-27 | 24 | 2024-05-10 | C7F
PM8 | POINT LOMA | T-EPF 15 | VR (Z) MSC | ACTIVE | 2027-01-04 | 2027-01-24 | 21 | 2025-08-15 | C7F
PM1 | JOHN LEWIS | T-AO 205 | VR (Z) MSC | ACTIVE | 2027-01-04 | 2027-01-17 | 14 | 2024-03-21 | C7F
PM8 | APALACHICOLA | T-EPF 13 | ROH / DD (MSC) | ACTIVE | 2027-01-05 | 2027-06-05 | 152 | 2025-01-13 | CTF 80
PM4 | NAVAJO | T-ATS 6 | VR (Z) MSC | ACTIVE | 2027-01-08 | 2027-01-21 | 14 | 2025-07-28 | C3F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | ROH (MSC) | ACTIVE | 2027-01-11 | 2027-04-20 | 100 | 2025-01-17 | CTF 80
PM4 | GRASP | T-ARS 51 | ROH / DD (MSC) | ACTIVE | 2027-01-11 | 2027-03-26 | 75 | 2025-08-11 | C3F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2027-01-11 | 2027-01-24 | 14 | 2025-03-28 | C5F
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2027-01-11 | 2027-01-25 | 15 | 2022-05-17 | CTF 80
PM1 | KANAWHA | T-AO 196 | VR (Z) MSC | ACTIVE | 2027-01-11 | 2027-01-25 | 15 | 2023-06-05 | C6F
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | ACTIVE | 2027-01-11 | 2027-01-24 | 14 | 2025-08-11 | C5F
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2027-01-11 | 2027-02-10 | 31 | 2025-09-03 | GUAM
PM2 | BRUCE C HEEZEN | T-AGS 64 | VR (Z) MSC | ACTIVE | 2027-01-11 | 2027-01-28 | 18 | 2025-04-25 | C6F
PM1 | OSCAR V PETERSON | T-AO 206 | VR (Z) MSC | ACTIVE | 2027-01-11 | 2027-01-25 | 15 | 2025-07-24 | CTF 80
PM3 | ROBERT E SIMANEK | ESB 7 | VR (Z) MSC | ACTIVE | 2027-01-14 | 2027-01-27 | 14 | 2025-07-25 | C6F
PM3 | PILILAAU | T-AKR 304 | VR (Z) MSC | ACTIVE | 2027-01-15 | 2027-02-04 | 21 | 2025-07-25 | C7F
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2027-01-19 | 2027-02-17 | 30 | 2025-02-21 | C7F
PM1 | JOHN LENTHALL | T-AO 189 | VR (Z) MSC | ACTIVE | 2027-01-29 | 2027-02-12 | 15 | 2025-08-07 | C2F
PM4 | BILLY FRANK JR | T-ATS 11 | PSA (MSC) | ACTIVE | 2027-01-31 | 2027-04-15 | 75 | 2025-07-28 | C7F
PM8 | CODY | T-EPF 14 | MTA (MSC) | ACTIVE | 2027-02-01 | 2027-04-16 | 75 | 2025-04-04 | CTF 80
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | MTA (MSC) | ACTIVE | 2027-02-01 | 2027-03-17 | 45 | 2025-07-25 | C6F
PM3 | 1ST LT JACK LUMMUS | T-AK 3011 | ROH / DD (MSC) | ACTIVE | 2027-02-01 | 2027-05-31 | 120 | 2025-07-25 | C3F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2027-02-01 | 2027-02-15 | 15 | 2025-07-25 | C7F
PM4 | EMORY S LAND | AS 39 | VR (Z) MSC | ACTIVE | 2027-02-01 | 2027-03-04 | 32 | 2025-09-03 | GUAM
PM2 | MARIE THARP | T-AGS 66 | VR (Z) MSC | ACTIVE | 2027-02-01 | 2027-02-18 | 18 | 2025-04-07 | C6F
PM2 | HENSON | T-AGS 63 | VR (Z) MSC | ACTIVE | 2027-02-01 | 2027-02-18 | 18 | 2025-04-25 | C7F
PM3 | SISLER | T-AKR 311 | VR (Z) MSC | ACTIVE | 2027-02-01 | 2027-02-15 | 15 | 2025-07-25 | C7F
PM2 | WESTWIND | T-AGSE 2 | ROH (MSC) | ACTIVE | 2027-02-03 | 2027-03-09 | 35 | 2023-05-10 | CTF 80
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2027-02-06 | 2027-02-19 | 14 | 2024-01-05 | C3F
PM8 | YUMA | T-EPF 8 | VR (Z) MSC | ACTIVE | 2027-02-07 | 2027-02-27 | 21 | 2025-08-15 | Rhoads Industries
PM8 | BURLINGTON | T-EPF 10 | VR (Z) MSC | ACTIVE | 2027-02-07 | 2027-02-27 | 21 | 2025-08-19 | CTF 80
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | ACTIVE | 2027-02-07 | 2027-02-20 | 14 | 2025-08-07 | C3F
PM2 | IMPECCABLE | T-AGOS 23 | MTA (MSC) | ACTIVE | 2027-02-08 | 2027-04-08 | 60 | 2025-08-08 | C7F
PM4 | MERCY | T-AH 19 | MTA (MSC) | ACTIVE | 2027-02-08 | 2027-04-07 | 59 | 2025-09-22 | C3F
PM6 | ARCTIC | T-AOE 8 | ROH / DD (MSC) | ACTIVE | 2027-02-08 | 2027-07-03 | 146 | 2025-05-15 | CTF 80
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2027-02-08 | 2027-02-21 | 14 | 2025-04-24 | C7F
PM3 | GYSGT FRED W STOCKHAM | T-AK 3017 | ROH / DD (MSC) | DEFERRED | 2027-02-10 | 2027-06-20 | 131 | 2025-05-15 | CTF 80
PM8 | POINT LOMA | T-EPF 15 | VR (Z) MSC | ACTIVE | 2027-02-15 | 2027-03-07 | 21 | 2025-08-15 | C7F
PM2 | VICTORIOUS | T-AGOS 19 | VR (Z) MSC | ACTIVE | 2027-02-19 | 2027-04-04 | 45 | 2025-07-18 | C7F
PM3 | SGT WILLIAM R BUTTON | T-AK 3012 | VR (Z) MSC | ACTIVE | 2027-02-21 | 2027-03-14 | 22 | 2025-07-25 | C7F
PM1 | ROBERT F KENNEDY | T-AO 208 | MTA (MSC) | ACTIVE | 2027-02-22 | 2027-04-05 | 43 | 2025-06-26 | CTF 80
PM1 | LARAMIE | T-AO 203 | VR (Z) MSC | ACTIVE | 2027-02-22 | 2027-03-08 | 15 | 2023-06-06 | C6F
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2027-02-22 | 2027-03-07 | 14 | 2025-04-03 | CTF 80
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2027-02-25 | 2027-03-06 | 10 | 2025-07-30 | C7F
PM1 | EARL WARREN | T-AO 207 | VR (Z) MSC | ACTIVE | 2027-02-25 | 2027-03-10 | 14 | 2024-03-16 | C7F
PM3 | JOHN L CANLEY | ESB 6 | MTA (MSC) | ACTIVE | 2027-03-01 | 2027-04-15 | 46 | 2025-08-27 | C7F
PM1 | LUCY STONE | T-AO 209 | PSA (MSC) | ACTIVE | 2027-03-01 | 2027-06-01 | 93 | 2025-09-25 | C3F
PM2 | HOWARD O LORENZEN | T-AGM 25 | ROH (MSC) | ACTIVE | 2027-03-01 | 2027-04-14 | 45 | 2025-08-08 | C7F
PM8 | NEWPORT | T-EPF 12 | VR (Z) MSC | ACTIVE | 2027-03-01 | 2027-03-21 | 21 | 2025-07-29 | Port of Orange
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2027-03-01 | 2027-03-15 | 15 | 2025-08-07 | CTF 80
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2027-03-03 | 2027-03-17 | 15 | 2025-07-25 | C5F
PM3 | PFC DEWAYNE T WILLIAMS | T-AK 3009 | VR (Z) MSC | ACTIVE | 2027-03-03 | 2027-03-17 | 15 | 2025-07-25 | C7F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | MTA (MSC) | ACTIVE | 2027-03-05 | 2027-04-23 | 50 | 2025-02-21 | C7F
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | ACTIVE | 2027-03-08 | 2027-03-21 | 14 | 2025-08-11 | C7F
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2027-03-13 | 2027-03-26 | 14 | 2024-01-04 | C7F
PM3 | ROBERT E SIMANEK | ESB 7 | VR (Z) MSC | ACTIVE | 2027-03-15 | 2027-03-28 | 14 | 2025-07-25 | C6F
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2027-03-15 | 2027-03-28 | 14 | 2022-05-17 | C6F
PM3 | JOHN GLENN | T-ESD 2 | VR (Z) MSC | ACTIVE | 2027-03-17 | 2027-04-07 | 22 | 2025-07-25 | C3F
PM4 | SOLOMON ATKINSON | T-ATS 12 | VR (Z) MSC | ACTIVE | 2027-03-19 | 2027-04-01 | 14 | 2025-07-11 | C3F
PM6 | LEWIS AND CLARK | T-AKE 1 | VR (Z) MSC | ACTIVE | 2027-03-20 | 2027-04-02 | 14 | 2024-12-30 | C7F
PM1 | KANAWHA | T-AO 196 | VR (Z) MSC | ACTIVE | 2027-03-22 | 2027-04-04 | 14 | 2023-06-05 | C6F
PM8 | CITY OF BISMARCK | T-EPF 9 | VR (Z) MSC | ACTIVE | 2027-03-22 | 2027-04-11 | 21 | 2025-04-01 | C7F
PM1 | TIPPECANOE | T-AO 199 | MTA (MSC) | ACTIVE | 2027-03-25 | 2027-06-08 | 76 | 2025-02-21 | C3F
PM4 | NAVAJO | T-ATS 6 | VR (Z) MSC | ACTIVE | 2027-03-25 | 2027-04-07 | 14 | 2025-07-28 | C3F
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | ACTIVE | 2027-03-29 | 2027-04-11 | 14 | 2025-08-11 | C5F
PM8 | BRUNSWICK | T-EPF 6 | VR (Z) MSC | CANCELED | 2027-03-29 | 2027-04-18 | 21 | 2025-07-24 | C2F
PM1 | YUKON | T-AO 202 | MTA (MSC) | ACTIVE | 2027-04-01 | 2027-06-15 | 76 | 2025-02-21 | C7F
PM4 | COMFORT | T-AH 20 | ROH / DD (MSC) | ACTIVE | 2027-04-01 | 2027-10-01 | 184 | 2024-08-30 | CTF 80
PM3 | SODERMAN | T-AKR 317 | ROH / DD (MSC) | ACTIVE | 2027-04-01 | 2027-07-01 | 92 | 2024-06-07 | C2F
PM3 | SEAY | T-AKR 302 | ROH / DD (MSC) | ACTIVE | 2027-04-01 | 2027-07-29 | 120 | 2025-07-25 | C2F
PM4 | MOUNT WHITNEY | LCC 20 | VR (Z) MSC | ACTIVE | 2027-04-01 | 2027-04-14 | 14 | 2025-08-11 | C6F
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2027-04-04 | 2027-04-17 | 14 | 2023-12-10 | C7F
PM6 | RICHARD E BYRD | T-AKE 4 | MTA (MSC) | ACTIVE | 2027-04-05 | 2027-05-24 | 50 | 2025-03-28 | C7F
PM8 | POINT LOMA | T-EPF 15 | MTA (MSC) | ACTIVE | 2027-04-05 | 2027-06-18 | 75 | 2025-07-25 | C7F
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | CANCELED | 2027-04-05 | 2027-04-19 | 15 | 2025-04-29
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2027-04-06 | 2027-04-19 | 14 | 2023-12-10 | C7F
PM6 | MEDGAR EVERS | T-AKE 13 | ROH / DD (MSC) | ACTIVE | 2027-04-12 | 2027-07-10 | 90 | 2025-09-18 | CTF 80
PM1 | OSCAR V PETERSON | T-AO 206 | MTA (MSC) | ACTIVE | 2027-04-14 | 2027-05-25 | 42 | 2025-08-01 | CTF 80
PM2 | EFFECTIVE | T-AGOS 21 | VR (Z) MSC | ACTIVE | 2027-04-14 | 2027-05-28 | 45 | 2025-08-08 | C7F
PM2 | PATHFINDER | T-AGS 60 | ROH / DD (MSC) | ACTIVE | 2027-04-19 | 2027-06-17 | 60 | 2025-04-07 | CTF 80
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2027-04-19 | 2027-05-02 | 14 | 2024-01-05 | C7F
PM1 | JOHN LEWIS | T-AO 205 | VR (Z) MSC | ACTIVE | 2027-04-19 | 2027-05-02 | 14 | 2024-03-21 | C7F
PM8 | NEWPORT | T-EPF 12 | ROH / DD (MSC) | ACTIVE | 2027-04-26 | 2027-09-26 | 154 | 2025-07-28 | CTF 80
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2027-04-28 | 2027-05-07 | 10 | 2025-07-30 | C7F
PM1 | EARL WARREN | T-AO 207 | MTA (MSC) | ACTIVE | 2027-05-01 | 2027-06-11 | 42 | 2025-07-30 | C7F
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | ACTIVE | 2027-05-01 | 2027-05-14 | 14 | 2025-08-07 | C3F
PM3 | DAHL | T-AKR 312 | VR (Z) MSC | ACTIVE | 2027-05-01 | 2027-05-21 | 21 | 2025-07-25 | C7F
PM3 | SISLER | T-AKR 311 | VR (Z) MSC | ACTIVE | 2027-05-01 | 2027-05-21 | 21 | 2025-07-25 | C7F
PM1 | PECOS | T-AO 197 | VR (Z) MSC | CANCELED | 2027-05-01 | 2027-05-14 | 14 | 2025-05-29
PM8 | USNS LANSING | T-EPF 16 | PSA (MSC) | ACTIVE | 2027-05-03 | 2027-07-31 | 90 | 2025-08-11 | CTF 80
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2027-05-03 | 2027-05-17 | 15 | 2022-05-17 | CTF 80
PM1 | JOHN LENTHALL | T-AO 189 | VR (Z) MSC | ACTIVE | 2027-05-03 | 2027-05-17 | 15 | 2025-08-07 | C2F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2027-05-03 | 2027-05-17 | 15 | 2025-07-25 | C7F
PM4 | MERCY | T-AH 19 | VR (Z) MSC | ACTIVE | 2027-05-07 | 2027-05-28 | 22 | 2024-04-03 | C3F
PM2 | BOWDITCH | T-AGS 62 | VR (Z) MSC | ACTIVE | 2027-05-10 | 2027-05-27 | 18 | 2025-04-25 | C7F
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2027-05-15 | 2027-05-28 | 14 | 2024-01-05 | C3F
PM2 | WATERS | T-AGS 45 | ROH (MSC) | ACTIVE | 2027-05-17 | 2027-08-31 | 107 | 2025-04-07 | CTF 80
PM6 | CARL BRASHEAR | T-AKE 7 | ROH (MSC) | ACTIVE | 2027-05-17 | 2027-07-15 | 60 | 2025-04-24 | C7F
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2027-05-31 | 2027-06-13 | 14 | 2025-08-11 | C3F
PM3 | LEWIS B PULLER | ESB 3 | MTA (MSC) | ACTIVE | 2027-06-01 | 2027-07-16 | 46 | 2025-07-25 | C5F
PM2 | LOYAL | T-AGOS 22 | MTA (MSC) | ACTIVE | 2027-06-01 | 2027-07-30 | 60 | 2025-08-08 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | MTA (MSC) | ACTIVE | 2027-06-01 | 2027-07-20 | 50 | 2024-12-20 | CTF 80
PM2 | EAGLEVIEW | T-AGSE 3 | ROH (MSC) | ACTIVE | 2027-06-01 | 2027-07-05 | 35 | 2025-07-17 | C3F
PM3 | SISLER | T-AKR 311 | ROH / DD (MSC) | ACTIVE | 2027-06-01 | 2027-08-28 | 89 | 2025-07-25 | C2F
PM4 | MERCY | T-AH 19 | VR (Z) MSC | ACTIVE | 2027-06-01 | 2027-07-01 | 31 | 2025-07-22 | C3F
PM4 | EMORY S LAND | AS 39 | VR (Z) MSC | ACTIVE | 2027-06-01 | 2027-07-01 | 31 | 2025-09-03 | GUAM
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2027-06-01 | 2027-07-30 | 60 | 2025-09-03 | GUAM
PM4 | SOLOMON ATKINSON | T-ATS 12 | VR (Z) MSC | ACTIVE | 2027-06-03 | 2027-06-16 | 14 | 2025-07-11 | C3F
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | ACTIVE | 2027-06-07 | 2027-06-21 | 15 | 2025-08-07 | C7F
PM1 | ROBERT F KENNEDY | T-AO 208 | VR (Z) MSC | ACTIVE | 2027-06-07 | 2027-06-20 | 14 | 2025-08-08 | CTF 80
PM4 | SALVOR | T-ARS 52 | VR (Z) MSC | ACTIVE | 2027-06-07 | 2027-06-20 | 14 | 2025-08-11 | C7F
PM8 | CODY | T-EPF 14 | VR (Z) MSC | ACTIVE | 2027-06-07 | 2027-06-27 | 21 | 2025-08-15 | C7F
PM4 | NAVAJO | T-ATS 6 | PSA (MSC) | ACTIVE | 2027-06-09 | 2027-08-22 | 75 | 2025-07-28 | C3F
PM1 | PATUXENT | T-AO 201 | MTA (MSC) | ACTIVE | 2027-06-14 | 2027-08-27 | 75 | 2023-06-05 | CTF 80
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | ACTIVE | 2027-06-14 | 2027-06-27 | 14 | 2025-08-11 | C5F
PM3 | ROBERT E SIMANEK | ESB 7 | VR (Z) MSC | ACTIVE | 2027-06-14 | 2027-06-27 | 14 | 2025-07-25 | C6F
PM2 | BRUCE C HEEZEN | T-AGS 64 | VR (Z) MSC | ACTIVE | 2027-06-14 | 2027-07-01 | 18 | 2025-04-25 | C6F
PM2 | HENSON | T-AGS 63 | VR (Z) MSC | ACTIVE | 2027-06-14 | 2027-07-01 | 18 | 2025-04-25 | C7F
PM2 | MARY SEARS | T-AGS 65 | VR (Z) MSC | ACTIVE | 2027-06-14 | 2027-07-01 | 18 | 2025-04-25 | C7F
PM8 | CHOCTAW COUNTY | T-EPF 2 | ROH / DD (MSC) | CANCELED | 2027-06-17 | 2027-09-14 | 90 | 2024-04-24 | CTF 80
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2027-06-19 | 2027-07-03 | 15 | 2025-03-09 | CTF 80
PM8 | PUERTO RICO | T-EPF 11 | VR (Z) MSC | ACTIVE | 2027-06-21 | 2027-07-11 | 21 | 2025-08-15 | C7F
PM6 | CHARLES DREW | T-AKE 10 | MTA (MSC) | ACTIVE | 2027-06-22 | 2027-08-10 | 50 | 2025-02-21 | C7F
PM4 | BILLY FRANK JR | T-ATS 11 | VR (Z) MSC | ACTIVE | 2027-06-22 | 2027-07-05 | 14 | 2025-07-28 | C7F
PM2 | ABLE | T-AGOS 20 | ROH (MSC) | ACTIVE | 2027-06-25 | 2027-08-23 | 60 | 2025-08-08 | C7F
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2027-06-26 | 2027-07-05 | 10 | 2025-07-30 | C7F
PM1 | LARAMIE | T-AO 203 | MTA (MSC) | ACTIVE | 2027-06-28 | 2027-09-11 | 76 | 2025-01-17 | C7F
PM1 | HENRY J KAISER | T-AO 187 | VR (Z) MSC | ACTIVE | 2027-06-29 | 2027-07-12 | 14 | 2025-08-07 | C3F
PM2 | IMPECCABLE | T-AGOS 23 | VR (Z) MSC | ACTIVE | 2027-06-30 | 2027-08-13 | 45 | 2025-08-08 | C7F
PM6 | ROBERT E PEARY | T-AKE 5 | MTA (MSC) | ACTIVE | 2027-07-01 | 2027-08-15 | 46 | 2022-07-22 | CTF 80
PM4 | MOUNT WHITNEY | LCC 20 | ROH / DD (MSC) | ACTIVE | 2027-07-01 | 2027-10-29 | 121 | 2025-08-11 | C6F
PM4 | MERCY | T-AH 19 | VR (Z) MSC | ACTIVE | 2027-07-01 | 2027-07-31 | 31 | 2024-04-03 | C3F
PM3 | JOHN GLENN | T-ESD 2 | VR (Z) MSC | ACTIVE | 2027-07-01 | 2027-07-21 | 21 | 2025-07-25 | C3F
PM3 | MONTFORD POINT | T-ESD 1 | VR (Z) MSC | ACTIVE | 2027-07-01 | 2027-07-21 | 21 | 2025-07-25 | C2F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2027-07-01 | 2027-07-16 | 16 | 2025-07-25 | C6F
PM1 | KANAWHA | T-AO 196 | MTA (MSC) | ACTIVE | 2027-07-05 | 2027-09-17 | 75 | 2023-06-05 | CTF 80
PM8 | BURLINGTON | T-EPF 10 | ROH / DD (MSC) | ACTIVE | 2027-07-07 | 2027-12-07 | 154 | 2025-01-06 | CTF 80
PM6 | ALAN SHEPARD | T-AKE 3 | ROH / DD (MSC) | ACTIVE | 2027-07-12 | 2027-10-09 | 90 | 2024-08-12 | C3F
PM8 | CITY OF BISMARCK | T-EPF 9 | VR (Z) MSC | ACTIVE | 2027-07-12 | 2027-08-01 | 21 | 2025-04-01 | C7F
PM6 | SACAGAWEA | T-AKE 2 | VR (Z) MSC | ACTIVE | 2027-07-12 | 2027-08-08 | 28 | 2024-05-10 | C7F
PM8 | BRUNSWICK | T-EPF 6 | VR (Z) MSC | CANCELED | 2027-07-12 | 2027-08-01 | 21 | 2025-07-24 | C2F
PM3 | SGT WILLIAM R BUTTON | T-AK 3012 | VR (Z) MSC | ACTIVE | 2027-07-15 | 2027-07-29 | 15 | 2025-07-25 | C7F
PM1 | SOJOURNER TRUTH | T-AO 210 | PSA (MSC) | ACTIVE | 2027-07-16 | 2027-12-15 | 153 | 2025-08-20 | CTF 80
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2027-07-20 | 2027-08-02 | 14 | 2023-12-10 | C7F
PM3 | 1ST LT JACK LUMMUS | T-AK 3011 | VR (Z) MSC | ACTIVE | 2027-07-22 | 2027-08-04 | 14 | 2025-07-25 | C7F
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2027-07-24 | 2027-08-22 | 30 | 2025-02-21 | C7F
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2027-07-25 | 2027-08-07 | 14 | 2023-12-10 | C7F
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2027-07-26 | 2027-08-08 | 14 | 2024-01-05 | C7F
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | ACTIVE | 2027-07-26 | 2027-08-09 | 15 | 2025-08-27 | C7F
PM3 | DAHL | T-AKR 312 | VR (Z) MSC | ACTIVE | 2027-08-01 | 2027-08-15 | 15 | 2025-07-25 | C7F
PM4 | MERCY | T-AH 19 | MTA (MSC) | ACTIVE | 2027-08-02 | 2027-10-07 | 67 | 2025-07-22 | C3F
PM2 | MARIE THARP | T-AGS 66 | VR (Z) MSC | ACTIVE | 2027-08-02 | 2027-08-19 | 18 | 2025-08-08 | C6F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2027-08-02 | 2027-08-16 | 15 | 2025-08-07 | CTF 80
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2027-08-02 | 2027-08-16 | 15 | 2025-07-25 | C7F
PM4 | EMORY S LAND | AS 39 | VR (Z) MSC | ACTIVE | 2027-08-02 | 2027-09-01 | 31 | 2025-09-03 | GUAM
PM8 | CARSON CITY | T-EPF 7 | VR (Z) MSC | CANCELED | 2027-08-02 | 2027-08-22 | 21 | 2025-07-24 | C2F
PM1 | LUCY STONE | T-AO 209 | VR (Z) MSC | ACTIVE | 2027-08-04 | 2027-08-17 | 14 | 2025-09-25 | C7F
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2027-08-09 | 2027-08-23 | 15 | 2022-05-17 | CTF 80
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | ACTIVE | 2027-08-13 | 2027-08-27 | 15 | 2025-08-08 | C3F
PM1 | JOHN LENTHALL | T-AO 189 | DECOM AVAIL (MSC) | ACTIVE | 2027-08-16 | 2027-09-30 | 46 | 2025-08-22 | C2F
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2027-08-16 | 2027-08-29 | 14 | 2025-08-11 | C3F
PM4 | SOLOMON ATKINSON | T-ATS 12 | VR (Z) MSC | ACTIVE | 2027-08-18 | 2027-08-31 | 14 | 2025-07-11 | C3F
PM4 | CHEROKEE NATION | T-ATS 7 | VR (Z) MSC | ACTIVE | 2027-08-20 | 2027-09-02 | 14 | 2025-07-28 | C5F
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2027-08-25 | 2027-09-04 | 11 | 2025-07-30 | C7F
PM8 | POINT LOMA | T-EPF 15 | VR (Z) MSC | ACTIVE | 2027-08-30 | 2027-09-19 | 21 | 2025-08-15 | C7F
PM3 | PFC DEWAYNE T WILLIAMS | T-AK 3009 | VR (Z) MSC | ACTIVE | 2027-08-30 | 2027-09-13 | 15 | 2025-07-25 | C7F
PM1 | GUADALUPE | T-AO 200 | MTA (MSC) | DEFERRED | 2027-09-01 | 2028-01-19 | 141 | 2025-02-21 | C3F
PM1 | PECOS | T-AO 197 | MTA (MSC) | CANCELED | 2027-09-01 | 2027-10-30 | 60 | 2025-05-29
PM1 | GUADALUPE | T-AO 200 | ROH (MSC) | ACTIVE | 2027-09-01 | 2028-01-19 | 141 | 2025-02-21 | C3F
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | ACTIVE | 2027-09-01 | 2027-09-15 | 15 | 2025-08-27 | C7F
PM6 | LEWIS AND CLARK | T-AKE 1 | VR (Z) MSC | ACTIVE | 2027-09-01 | 2027-09-28 | 28 | 2024-12-30 | C7F
PM3 | 1ST LT JACK LUMMUS | T-AK 3011 | VR (Z) MSC | ACTIVE | 2027-09-01 | 2027-09-14 | 14 | 2025-07-25 | C7F
PM1 | JOHN LEWIS | T-AO 205 | ROH / DD (MSC) | ACTIVE | 2027-09-06 | 2027-11-05 | 61 | 2025-07-23 | C7F
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2027-09-06 | 2027-09-20 | 15 | 2025-02-28 | C6F
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | ACTIVE | 2027-09-06 | 2027-09-20 | 15 | 2025-08-07 | C7F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2027-09-06 | 2027-09-19 | 14 | 2024-01-05 | C7F
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2027-09-06 | 2027-09-19 | 14 | 2022-05-17 | C6F
PM8 | APALACHICOLA | T-EPF 13 | VR (Z) MSC | ACTIVE | 2027-09-08 | 2027-09-28 | 21 | 2025-08-19 | CTF 80
PM8 | PUERTO RICO | T-EPF 11 | VR (Z) MSC | ACTIVE | 2027-09-08 | 2027-09-28 | 21 | 2025-08-15 | C7F
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | CANCELED | 2027-09-08 | 2027-09-28 | 21 | 2025-07-24 | CTF 80
PM4 | BILLY FRANK JR | T-ATS 11 | VR (Z) MSC | ACTIVE | 2027-09-09 | 2027-09-22 | 14 | 2025-07-28 | C7F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2027-09-10 | 2027-09-23 | 14 | 2023-12-10 | C3F
PM3 | PILILAAU | T-AKR 304 | VR (Z) MSC | ACTIVE | 2027-09-14 | 2027-09-27 | 14 | 2025-07-25 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2027-09-20 | 2027-10-03 | 14 | 2025-02-13 | CTF 80
PM1 | OSCAR V PETERSON | T-AO 206 | VR (Z) MSC | ACTIVE | 2027-09-20 | 2027-10-04 | 15 | 2025-07-24 | CTF 80
PM4 | CATAWBA | T-ATF 168 | DECOM AVAIL (MSC) | ACTIVE | 2027-10-01 | 2027-10-31 | 31 | 2025-08-11 | C5F
PM4 | SALVOR | T-ARS 52 | DECOM AVAIL (MSC) | ACTIVE | 2027-10-01 | 2027-10-31 | 31 | 2025-08-11 | C7F
PM8 | GUAM | HST 1 | ROH / DD (MSC) | ACTIVE | 2027-10-01 | 2027-12-15 | 76 | 2025-07-30 | C7F
PM1 | HENRY J KAISER | T-AO 187 | VR (Z) MSC | ACTIVE | 2027-10-01 | 2027-10-14 | 14 | 2025-08-07 | C3F
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2027-10-01 | 2027-10-15 | 15 | 2025-07-25 | C5F
PM6 | CESAR CHAVEZ | T-AKE 14 | ROH / DD (MSC) | ACTIVE | 2027-10-05 | 2028-01-02 | 90 | 2024-01-05 | C7F
PM2 | BLACK POWDER | T-AGSE 1 | MTA (MSC) | ACTIVE | 2027-10-06 | 2027-11-19 | 45 | 2025-08-08 | CTF 80
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2027-10-11 | 2027-10-24 | 14 | 2024-01-05 | C5F
PM8 | CODY | T-EPF 14 | VR (Z) MSC | ACTIVE | 2027-10-13 | 2027-11-02 | 21 | 2025-08-15 | C7F
PM2 | LOYAL | T-AGOS 22 | VR (Z) MSC | ACTIVE | 2027-10-14 | 2027-11-27 | 45 | 2025-08-08 | C7F
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2027-10-14 | 2027-10-28 | 15 | 2025-08-08 | C7F
PM3 | MIGUEL KEITH | ESB 5 | ROH (MSC) | ACTIVE | 2027-10-18 | 2027-12-17 | 61 | 2025-07-17 | C7F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2027-10-18 | 2027-10-31 | 14 | 2025-03-10 | CTF 80
PM2 | ARROWHEAD | T-AGSE 4 | ROH (MSC) | ACTIVE | 2027-10-20 | 2027-11-24 | 36 | 2025-08-08 | C3F
PM2 | VICTORIOUS | T-AGOS 19 | ROH (MSC) | ACTIVE | 2027-10-24 | 2027-12-22 | 60 | 2025-07-18 | C7F
PM6 | AMELIA EARHART | T-AKE 6 | MTA (MSC) | ACTIVE | 2027-10-29 | 2027-12-17 | 50 | 2024-01-05 | C7F
PM4 | NAVAJO | T-ATS 6 | VR (Z) MSC | ACTIVE | 2027-10-29 | 2027-11-11 | 14 | 2025-07-28 | C3F
PM2 | SBX-1 | SBX 1 | ROH (MSC) | ACTIVE | 2027-11-01 | 2028-01-29 | 90 | 2025-08-08 | C3F
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-14 | 14 | 2024-03-06 | CTF 80
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-14 | 14 | 2025-08-11 | C3F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-15 | 15 | 2025-07-25 | C6F
PM4 | FRANK CABLE | AS 40 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-12-10 | 40 | 2025-09-03 | GUAM
PM8 | CARSON CITY | T-EPF 7 | VR (Z) MSC | CANCELED | 2027-11-01 | 2027-11-21 | 21 | 2025-07-24 | C2F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-14 | 14 | 2025-09-18 | C3F
PM2 | BOWDITCH | T-AGS 62 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-18 | 18 | 2025-04-25 | C7F
PM2 | MARY SEARS | T-AGS 65 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-18 | 18 | 2025-04-25 | C7F
PM3 | MONTFORD POINT | T-ESD 1 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-21 | 21 | 2025-07-25 | C2F
PM3 | 1ST LT JACK LUMMUS | T-AK 3011 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-21 | 21 | 2025-07-25 | C7F
PM3 | DAHL | T-AKR 312 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-15 | 15 | 2025-07-25 | C7F
PM3 | PILILAAU | T-AKR 304 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-14 | 14 | 2025-07-25 | C7F
PM3 | SEAY | T-AKR 302 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-14 | 14 | 2025-07-25 | C7F
PM3 | SISLER | T-AKR 311 | VR (Z) MSC | ACTIVE | 2027-11-01 | 2027-11-15 | 15 | 2025-07-25 | C7F
PM4 | SOLOMON ATKINSON | T-ATS 12 | PSA (MSC) | ACTIVE | 2027-11-02 | 2028-01-15 | 75 | 2025-07-11 | C3F
PM2 | IMPECCABLE | T-AGOS 23 | VR (Z) MSC | ACTIVE | 2027-11-04 | 2027-12-18 | 45 | 2025-08-08 | C7F
PM4 | CHEROKEE NATION | T-ATS 7 | VR (Z) MSC | ACTIVE | 2027-11-04 | 2027-11-17 | 14 | 2025-07-28 | C5F
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2027-11-08 | 2027-11-22 | 15 | 2023-06-06 | C6F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2027-11-08 | 2027-11-21 | 14 | 2023-07-09 | C3F
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | CANCELED | 2027-11-08 | 2027-11-21 | 14 | 2024-05-18 | C3F
PM2 | HOWARD O LORENZEN | T-AGM 25 | VR (Z) MSC | ACTIVE | 2027-11-09 | 2027-11-29 | 21 | 2025-08-08 | C7F
PM3 | SGT WILLIAM R BUTTON | T-AK 3012 | VR (Z) MSC | ACTIVE | 2027-11-09 | 2027-11-22 | 14 | 2025-07-25 | C7F
PM1 | LARAMIE | T-AO 203 | VR (Z) MSC | ACTIVE | 2027-11-12 | 2027-11-26 | 15 | 2025-08-07 | C7F
PM1 | EARL WARREN | T-AO 207 | VR (Z) MSC | ACTIVE | 2027-11-12 | 2027-11-25 | 14 | 2025-02-21 | C7F
PM6 | ARCTIC | T-AOE 8 | MTA (MSC) | ACTIVE | 2027-11-15 | 2028-01-05 | 52 | 2025-08-14 | CTF 80
PM6 | WALLY SCHIRRA | T-AKE 8 | ROH (MSC) | ACTIVE | 2027-11-21 | 2028-01-19 | 60 | 2023-12-10 | C7F
PM3 | PFC DEWAYNE T WILLIAMS | T-AK 3009 | VR (Z) MSC | ACTIVE | 2027-11-22 | 2027-12-13 | 22 | 2025-07-25 | C7F
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2027-11-23 | 2027-12-06 | 14 | 2025-02-21 | C7F
PM2 | EFFECTIVE | T-AGOS 21 | ROH (MSC) | ACTIVE | 2027-11-26 | 2028-01-24 | 60 | 2025-08-08 | C7F
PM4 | BILLY FRANK JR | T-ATS 11 | VR (Z) MSC | ACTIVE | 2027-11-28 | 2027-12-11 | 14 | 2025-07-28 | C7F
PM1 | TIPPECANOE | T-AO 199 | MTA (MSC) | ACTIVE | 2027-11-29 | 2028-02-12 | 76 | 2025-01-17 | C7F
PM2 | PATHFINDER | T-AGS 60 | VR (Z) MSC | ACTIVE | 2027-11-29 | 2027-12-16 | 18 | 2025-04-07 | CTF 80
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | CANCELED | 2027-11-29 | 2027-12-19 | 21 | 2025-07-24 | CTF 80
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | ACTIVE | 2027-11-29 | 2027-12-13 | 15 | 2025-08-27 | C7F
PM8 | PUERTO RICO | T-EPF 11 | MTA (MSC) | ACTIVE | 2027-12-01 | 2028-02-13 | 75 | 2025-07-25 | C7F
PM1 | RAPPAHANNOCK | T-AO 204 | MTA (MSC) | ACTIVE | 2027-12-06 | 2028-03-16 | 102 | 2025-01-17 | C7F
PM8 | CITY OF BISMARCK | T-EPF 9 | ROH / DD (MSC) | ACTIVE | 2027-12-06 | 2028-03-04 | 90 | 2025-09-08 | C7F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2027-12-06 | 2027-12-20 | 15 | 2025-08-07 | CTF 80
PM1 | ROBERT F KENNEDY | T-AO 208 | VR (Z) MSC | ACTIVE | 2027-12-06 | 2027-12-19 | 14 | 2025-08-08 | CTF 80
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2027-12-13 | 2027-12-26 | 14 | 2025-03-20 | C5F
PM1 | JOHN LEWIS | T-AO 205 | VR (Z) MSC | ACTIVE | 2027-12-17 | 2027-12-30 | 14 | 2024-03-21 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2027-12-22 | 2028-01-05 | 15 | 2024-12-20 | CTF 80
PM4 | MOUNT WHITNEY | LCC 20 | VR (Z) MSC | ACTIVE | 2028-01-01 | 2028-01-14 | 14 | 2025-08-11 | C6F
PM3 | ROBERT E SIMANEK | ESB 7 | VR (Z) MSC | ACTIVE | 2028-01-02 | 2028-01-16 | 15 | 2025-07-25 | C6F
PM6 | RICHARD E BYRD | T-AKE 4 | ROH / DD (MSC) | ACTIVE | 2028-01-03 | 2028-04-01 | 90 | 2025-09-18 | C3F
PM4 | MERCY | T-AH 19 | VR (Z) MSC | ACTIVE | 2028-01-03 | 2028-02-03 | 32 | 2025-07-22 | C3F
PM6 | CARL BRASHEAR | T-AKE 7 | VR (Z) MSC | ACTIVE | 2028-01-03 | 2028-01-17 | 15 | 2024-01-16 | C5F
PM4 | EMORY S LAND | AS 39 | VR (Z) MSC | ACTIVE | 2028-01-03 | 2028-02-03 | 32 | 2025-09-03 | GUAM
PM1 | KANAWHA | T-AO 196 | VR (Z) MSC | ACTIVE | 2028-01-04 | 2028-01-17 | 14 | 2025-08-07 | CTF 80
PM8 | CARSON CITY | T-EPF 7 | ROH / DD (MSC) | CANCELED | 2028-01-05 | 2028-06-05 | 153 | 2025-07-24 | CTF 80
PM8 | YUMA | T-EPF 8 | ROH / DD (MSC) | CANCELED | 2028-01-05 | 2028-06-05 | 153 | 2025-07-24 | CTF 80
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2028-01-05 | 2028-01-19 | 15 | 2025-07-25 | C5F
PM8 | APALACHICOLA | T-EPF 13 | MTA (MSC) | ACTIVE | 2028-01-10 | 2028-03-24 | 75 | 2025-07-24 | C7F
PM8 | CODY | T-EPF 14 | MTA (MSC) | ACTIVE | 2028-01-10 | 2028-03-24 | 75 | 2025-07-25 | C7F
PM1 | LUCY STONE | T-AO 209 | MTA (MSC) | ACTIVE | 2028-01-10 | 2028-02-22 | 44 | 2025-09-25 | C7F
PM2 | BRUCE C HEEZEN | T-AGS 64 | ROH (MSC) | ACTIVE | 2028-01-10 | 2028-03-09 | 60 | 2025-04-25 | C6F
PM8 | APALACHICOLA | T-EPF 13 | ROH / DD (MSC) | CANCELED | 2028-01-10 | 2028-03-31 | 82 | 2025-07-24 | C7F
PM6 | SUPPLY | T-AOE 6 | VR (Z) MSC | ACTIVE | 2028-01-10 | 2028-01-23 | 14 | 2024-02-29 | CTF 80
PM6 | SACAGAWEA | T-AKE 2 | VR (Z) MSC | ACTIVE | 2028-01-10 | 2028-01-30 | 21 | 2024-05-10 | C7F
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2028-01-10 | 2028-01-24 | 15 | 2025-08-08 | C7F
PM8 | POINT LOMA | T-EPF 15 | VR (Z) MSC | ACTIVE | 2028-01-10 | 2028-01-30 | 21 | 2025-08-15 | C7F
PM8 | NEWPORT | T-EPF 12 | VR (Z) MSC | ACTIVE | 2028-01-10 | 2028-01-30 | 21 | 2025-08-15 | C7F
PM2 | ABLE | T-AGOS 20 | VR (Z) MSC | ACTIVE | 2028-01-13 | 2028-02-26 | 45 | 2025-08-08 | C7F
PM3 | PILILAAU | T-AKR 304 | VR (Z) MSC | ACTIVE | 2028-01-15 | 2028-02-04 | 21 | 2025-07-25 | C7F
PM4 | NAVAJO | T-ATS 6 | VR (Z) MSC | ACTIVE | 2028-01-16 | 2028-01-29 | 14 | 2025-07-10 | C3F
PM2 | HENSON | T-AGS 63 | ROH (MSC) | ACTIVE | 2028-01-17 | 2028-04-15 | 90 | 2025-04-07 | C7F
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2028-01-17 | 2028-01-30 | 14 | 2025-08-11 | C3F
PM4 | CHEROKEE NATION | T-ATS 7 | VR (Z) MSC | ACTIVE | 2028-01-19 | 2028-02-01 | 14 | 2025-07-28 | C5F
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2028-01-22 | 2028-02-05 | 15 | 2025-03-20 | C7F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | MTA (MSC) | ACTIVE | 2028-01-24 | 2028-04-07 | 75 | 2025-01-17 | CTF 80
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2028-01-24 | 2028-02-06 | 14 | 2023-07-09 | C7F
PM2 | MARIE THARP | T-AGS 66 | VR (Z) MSC | ACTIVE | 2028-01-24 | 2028-02-10 | 18 | 2025-07-02 | C6F
PM1 | LARAMIE | T-AO 203 | VR (Z) MSC | ACTIVE | 2028-01-31 | 2028-02-13 | 14 | 2025-08-07 | C7F
PM1 | EARL WARREN | T-AO 207 | VR (Z) MSC | ACTIVE | 2028-01-31 | 2028-02-13 | 14 | 2025-02-21 | C7F
PM1 | ROBERT F KENNEDY | T-AO 208 | MTA (MSC) | ACTIVE | 2028-02-01 | 2028-03-14 | 43 | 2025-06-26 | CTF 80
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | ROH / DD (MSC) | ACTIVE | 2028-02-01 | 2028-04-01 | 61 | 2025-07-25 | C6F
PM3 | JOHN L CANLEY | ESB 6 | ROH / DD (MSC) | ACTIVE | 2028-02-01 | 2028-04-01 | 61 | 2025-07-16 | C7F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2028-02-01 | 2028-02-15 | 15 | 2025-07-25 | C7F
PM3 | SISLER | T-AKR 311 | VR (Z) MSC | ACTIVE | 2028-02-01 | 2028-02-15 | 15 | 2025-07-25 | C7F
PM6 | MEDGAR EVERS | T-AKE 13 | MTA (MSC) | ACTIVE | 2028-02-07 | 2028-03-27 | 50 | 2024-05-22 | CTF 80
PM6 | SUPPLY | T-AOE 6 | ROH / DD (MSC) | ACTIVE | 2028-02-08 | 2028-07-02 | 146 | 2025-09-18 | CTF 80
PM2 | WATERS | T-AGS 45 | VR (Z) MSC | ACTIVE | 2028-02-14 | 2028-03-02 | 18 | 2025-07-10 | CTF 80
PM4 | BILLY FRANK JR | T-ATS 11 | MTA (MSC) | ACTIVE | 2028-02-15 | 2028-04-14 | 60 | 2025-07-28 | C7F
PM8 | TRENTON | T-EPF 5 | MTA (MSC) | CANCELED | 2028-02-15 | 2028-04-29 | 75 | 2025-01-03
PM4 | FRANK CABLE | AS 40 | ROH / DD (MSC) | ACTIVE | 2028-02-15 | 2028-07-15 | 152 | 2024-04-03 | C3F
PM6 | ROBERT E PEARY | T-AKE 5 | VR (Z) MSC | ACTIVE | 2028-02-15 | 2028-02-29 | 15 | 2025-03-10 | CTF 80
PM6 | SACAGAWEA | T-AKE 2 | ROH / DD (MSC) | ACTIVE | 2028-02-21 | 2028-05-21 | 91 | 2024-11-06 | CTF 80
PM3 | SGT WILLIAM R BUTTON | T-AK 3012 | VR (Z) MSC | ACTIVE | 2028-02-21 | 2028-03-14 | 23 | 2025-07-25 | C7F
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2028-02-25 | 2028-03-06 | 11 | 2025-07-30 | C7F
PM2 | WESTWIND | T-AGSE 2 | MTA (MSC) | ACTIVE | 2028-02-28 | 2028-03-16 | 18 | 2025-08-08 | CTF 80
PM4 | COMFORT | T-AH 20 | VR (Z) MSC | ACTIVE | 2028-02-28 | 2028-03-28 | 30 | 2025-08-11 | CTF 80
PM2 | HOWARD O LORENZEN | T-AGM 25 | MTA (MSC) | ACTIVE | 2028-03-01 | 2028-03-30 | 30 | 2025-08-08 | C7F
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2028-03-01 | 2028-03-15 | 15 | 2025-07-16 | C5F
PM3 | SEAY | T-AKR 302 | VR (Z) MSC | ACTIVE | 2028-03-01 | 2028-03-21 | 21 | 2025-07-25 | C7F
PM3 | ROBERT E SIMANEK | ESB 7 | VR (Z) MSC | ACTIVE | 2028-03-01 | 2028-03-15 | 15 | 2025-07-25 | C6F
PM1 | HENRY J KAISER | T-AO 187 | MTA (MSC) | ACTIVE | 2028-03-02 | 2028-05-15 | 75 | 2025-02-21 | C3F
PM3 | PFC DEWAYNE T WILLIAMS | T-AK 3009 | VR (Z) MSC | ACTIVE | 2028-03-03 | 2028-03-17 | 15 | 2025-07-25 | C7F
PM1 | PATUXENT | T-AO 201 | VR (Z) MSC | ACTIVE | 2028-03-06 | 2028-03-19 | 14 | 2025-08-07 | CTF 80
PM8 | BURLINGTON | T-EPF 10 | VR (Z) MSC | ACTIVE | 2028-03-06 | 2028-03-26 | 21 | 2025-08-19 | C7F
PM1 | OSCAR V PETERSON | T-AO 206 | VR (Z) MSC | ACTIVE | 2028-03-06 | 2028-03-20 | 15 | 2025-07-24 | CTF 80
PM2 | IMPECCABLE | T-AGOS 23 | ROH (MSC) | ACTIVE | 2028-03-08 | 2028-05-06 | 60 | 2025-08-08 | C7F
PM6 | LEWIS AND CLARK | T-AKE 1 | VR (Z) MSC | ACTIVE | 2028-03-11 | 2028-03-24 | 14 | 2024-12-30 | C7F
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | MTA (MSC) | ACTIVE | 2028-03-13 | 2028-05-01 | 50 | 2023-07-09 | C3F
PM6 | CHARLES DREW | T-AKE 10 | VR (Z) MSC | ACTIVE | 2028-03-14 | 2028-03-27 | 14 | 2025-02-21 | C7F
PM3 | JOHN GLENN | T-ESD 2 | VR (Z) MSC | ACTIVE | 2028-03-17 | 2028-04-07 | 22 | 2025-07-25 | C3F
PM6 | AMELIA EARHART | T-AKE 6 | VR (Z) MSC | ACTIVE | 2028-03-20 | 2028-04-02 | 14 | 2025-08-11 | C7F
PM4 | SOLOMON ATKINSON | T-ATS 12 | VR (Z) MSC | ACTIVE | 2028-03-23 | 2028-04-05 | 14 | 2025-07-11 | C3F
PM1 | JOHN LEWIS | T-AO 205 | VR (Z) MSC | ACTIVE | 2028-03-24 | 2028-04-06 | 14 | 2024-03-21 | C7F
PM4 | MOUNT WHITNEY | LCC 20 | VR (Z) MSC | ACTIVE | 2028-04-01 | 2028-04-14 | 14 | 2025-08-11 | C6F
PM1 | YUKON | T-AO 202 | MTA (MSC) | ACTIVE | 2028-04-03 | 2028-06-17 | 76 | 2025-01-17 | C7F
PM8 | POINT LOMA | T-EPF 15 | ROH / DD (MSC) | ACTIVE | 2028-04-03 | 2028-07-01 | 90 | 2025-07-25 | C7F
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2028-04-03 | 2028-04-16 | 14 | 2025-08-11 | C3F
PM8 | NEWPORT | T-EPF 12 | VR (Z) MSC | ACTIVE | 2028-04-03 | 2028-04-23 | 21 | 2025-08-15 | C7F
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | DEFERRED | 2028-04-03 | 2028-04-16 | 14 | 2025-05-21
PM4 | CHEROKEE NATION | T-ATS 7 | PSA (MSC) | ACTIVE | 2028-04-04 | 2028-06-17 | 75 | 2025-07-28 | C5F
PM4 | NAVAJO | T-ATS 6 | VR (Z) MSC | ACTIVE | 2028-04-05 | 2028-04-18 | 14 | 2025-07-10 | C3F
PM1 | KANAWHA | T-AO 196 | VR (Z) MSC | ACTIVE | 2028-04-10 | 2028-04-24 | 15 | 2025-08-07 | CTF 80
PM6 | ALAN SHEPARD | T-AKE 3 | VR (Z) MSC | ACTIVE | 2028-04-12 | 2028-04-26 | 15 | 2025-03-20 | C7F
PM6 | MATTHEW PERRY | T-AKE 9 | ROH (MSC) | ACTIVE | 2028-04-17 | 2028-06-15 | 60 | 2025-03-20 | C7F
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2028-04-17 | 2028-04-30 | 14 | 2023-07-09 | C7F
PM2 | VICTORIOUS | T-AGOS 19 | VR (Z) MSC | ACTIVE | 2028-04-22 | 2028-05-22 | 31 | 2025-08-08 | C7F
PM8 | CITY OF BISMARCK | T-EPF 9 | VR (Z) MSC | ACTIVE | 2028-04-24 | 2028-05-14 | 21 | 2025-08-19 | C7F
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2028-04-28 | 2028-05-07 | 10 | 2025-07-30 | C7F
PM1 | EARL WARREN | T-AO 207 | ROH / DD (MSC) | ACTIVE | 2028-05-01 | 2028-06-29 | 60 | 2025-08-01 | C7F
PM3 | MONTFORD POINT | T-ESD 1 | ROH / DD (MSC) | ACTIVE | 2028-05-01 | 2028-08-29 | 121 | 2025-07-25 | C3F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2028-05-01 | 2028-05-15 | 15 | 2025-07-25 | C7F
PM3 | DAHL | T-AKR 312 | VR (Z) MSC | ACTIVE | 2028-05-01 | 2028-05-21 | 21 | 2025-07-25 | C7F
PM3 | SISLER | T-AKR 311 | VR (Z) MSC | ACTIVE | 2028-05-01 | 2028-05-21 | 21 | 2025-07-25 | C7F
PM1 | LARAMIE | T-AO 203 | MTA (MSC) | ACTIVE | 2028-05-08 | 2028-07-21 | 75 | 2025-01-17 | C7F
PM6 | WALLY SCHIRRA | T-AKE 8 | VR (Z) MSC | ACTIVE | 2028-05-08 | 2028-05-21 | 14 | 2023-07-09 | C7F
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | ACTIVE | 2028-05-08 | 2028-05-22 | 15 | 2025-08-08 | C3F
PM6 | CARL BRASHEAR | T-AKE 7 | MTA (MSC) | ACTIVE | 2028-05-09 | 2028-06-27 | 50 | 2025-08-11 | C7F
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | ACTIVE | 2028-05-09 | 2028-05-23 | 15 | 2025-08-07 | C3F
PM2 | BOWDITCH | T-AGS 62 | VR (Z) MSC | ACTIVE | 2028-05-15 | 2028-06-01 | 18 | 2025-07-02 | C7F
PM8 | PUERTO RICO | T-EPF 11 | VR (Z) MSC | ACTIVE | 2028-05-15 | 2028-06-04 | 21 | 2025-08-15 | C7F
PM2 | LOYAL | T-AGOS 22 | ROH (MSC) | ACTIVE | 2028-05-26 | 2028-07-24 | 60 | 2025-08-08 | C7F
PM6 | ROBERT E PEARY | T-AKE 5 | ROH / DD (MSC) | ACTIVE | 2028-05-28 | 2028-08-26 | 91 | 2025-03-10 | CTF 80
PM6 | WILLIAM MCLEAN | T-AKE 12 | MTA (MSC) | ACTIVE | 2028-05-29 | 2028-07-17 | 50 | 2025-03-10 | CTF 80
PM1 | PATUXENT | T-AO 201 | ROH (MSC) | ACTIVE | 2028-05-29 | 2028-09-05 | 100 | 2024-01-09 | CTF 80
PM2 | PATHFINDER | T-AGS 60 | VR (Z) MSC | ACTIVE | 2028-05-29 | 2028-06-15 | 18 | 2025-07-10 | CTF 80
PM2 | EAGLEVIEW | T-AGSE 3 | MTA (MSC) | ACTIVE | 2028-06-01 | 2028-07-15 | 45 | 2025-08-08 | C3F
PM3 | LEWIS B PULLER | ESB 3 | ROH (MSC) | ACTIVE | 2028-06-01 | 2028-07-31 | 61 | 2025-07-16 | C5F
PM4 | MERCY | T-AH 19 | VR (Z) MSC | ACTIVE | 2028-06-01 | 2028-07-01 | 31 | 2025-07-22 | C3F
PM4 | EMORY S LAND | AS 39 | VR (Z) MSC | ACTIVE | 2028-06-01 | 2028-07-01 | 31 | 2025-09-03 | GUAM
PM3 | ROBERT E SIMANEK | ESB 7 | VR (Z) MSC | ACTIVE | 2028-06-01 | 2028-06-15 | 15 | 2025-07-25 | C6F
PM6 | ALAN SHEPARD | T-AKE 3 | MTA (MSC) | ACTIVE | 2028-06-05 | 2028-07-24 | 50 | 2025-03-20 | C7F
PM1 | KANAWHA | T-AO 196 | ROH (MSC) | ACTIVE | 2028-06-05 | 2028-09-13 | 101 | 2025-06-06 | CTF 80
PM8 | APALACHICOLA | T-EPF 13 | VR (Z) MSC | ACTIVE | 2028-06-05 | 2028-06-25 | 21 | 2025-08-19 | CTF 80
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2028-06-05 | 2028-06-19 | 15 | 2025-08-07 | CTF 80
PM8 | CODY | T-EPF 14 | VR (Z) MSC | ACTIVE | 2028-06-05 | 2028-06-25 | 21 | 2025-08-15 | C7F
PM8 | BURLINGTON | T-EPF 10 | VR (Z) MSC | ACTIVE | 2028-06-05 | 2028-06-25 | 21 | 2025-08-19 | C7F
PM1 | LUCY STONE | T-AO 209 | VR (Z) MSC | ACTIVE | 2028-06-05 | 2028-06-18 | 14 | 2025-09-25 | C7F
PM4 | SOLOMON ATKINSON | T-ATS 12 | VR (Z) MSC | ACTIVE | 2028-06-10 | 2028-06-23 | 14 | 2025-07-11 | C3F
PM2 | MARY SEARS | T-AGS 65 | VR (Z) MSC | ACTIVE | 2028-06-12 | 2028-06-29 | 18 | 2025-07-02 | C7F
PM1 | ROBERT F KENNEDY | T-AO 208 | VR (Z) MSC | ACTIVE | 2028-06-12 | 2028-06-25 | 14 | 2025-08-08 | CTF 80
PM1 | RAPPAHANNOCK | T-AO 204 | VR (Z) MSC | ACTIVE | 2028-06-12 | 2028-06-26 | 15 | 2025-08-07 | C7F
PM2 | EFFECTIVE | T-AGOS 21 | VR (Z) MSC | ACTIVE | 2028-06-14 | 2028-07-28 | 45 | 2025-08-08 | C7F
PM1 | JOHN LEWIS | T-AO 205 | MTA (MSC) | ACTIVE | 2028-06-16 | 2028-07-30 | 45 | 2025-02-21 | C7F
PM4 | GRASP | T-ARS 51 | VR (Z) MSC | ACTIVE | 2028-06-19 | 2028-07-02 | 14 | 2025-08-11 | C3F
PM4 | CATAWBA | T-ATF 168 | VR (Z) MSC | DEFERRED | 2028-06-19 | 2028-07-02 | 14 | 2025-05-21
PM6 | CHARLES DREW | T-AKE 10 | ROH (MSC) | ACTIVE | 2028-06-20 | 2028-08-18 | 60 | 2025-02-21 | C7F
PM4 | BILLY FRANK JR | T-ATS 11 | VR (Z) MSC | ACTIVE | 2028-06-21 | 2028-07-04 | 14 | 2025-07-28 | C7F
PM1 | OSCAR V PETERSON | T-AO 206 | ROH / DD (MSC) | ACTIVE | 2028-06-22 | 2028-08-20 | 60 | 2025-08-01 | CTF 80
PM4 | NAVAJO | T-ATS 6 | MTA (MSC) | ACTIVE | 2028-06-23 | 2028-08-21 | 60 | 2025-07-10 | C3F
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2028-06-26 | 2028-07-05 | 10 | 2025-07-30 | C7F
PM3 | JOHN GLENN | T-ESD 2 | VR (Z) MSC | ACTIVE | 2028-07-01 | 2028-07-21 | 21 | 2025-07-25 | C3F
PM3 | 1ST LT JACK LUMMUS | T-AK 3011 | VR (Z) MSC | ACTIVE | 2028-07-01 | 2028-07-14 | 14 | 2025-07-25 | C7F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2028-07-01 | 2028-07-15 | 15 | 2025-07-25 | C6F
PM2 | MARIE THARP | T-AGS 66 | VR (Z) MSC | ACTIVE | 2028-07-03 | 2028-07-20 | 18 | 2025-07-02 | C6F
PM8 | TRENTON | T-EPF 5 | VR (Z) MSC | CANCELED | 2028-07-05 | 2028-07-25 | 21 | 2025-01-03
PM8 | BRUNSWICK | T-EPF 6 | ROH / DD (MSC) | CANCELED | 2028-07-07 | 2028-12-07 | 154 | 2025-07-24 | CTF 80
PM8 | TRENTON | T-EPF 5 | ROH / DD (MSC) | CANCELED | 2028-07-07 | 2028-12-07 | 154 | 2025-07-24 | CTF 80
PM8 | NEWPORT | T-EPF 12 | MTA (MSC) | ACTIVE | 2028-07-10 | 2028-09-22 | 75 | 2025-07-25 | C7F
PM8 | USNS LANSING | T-EPF 16 | MTA (MSC) | ACTIVE | 2028-07-10 | 2028-09-22 | 75 | 2025-07-31 | CTF 80
PM6 | AMELIA EARHART | T-AKE 6 | ROH / DD (MSC) | ACTIVE | 2028-07-10 | 2028-10-07 | 90 | 2023-07-08 | C7F
PM6 | ARCTIC | T-AOE 8 | VR (Z) MSC | ACTIVE | 2028-07-10 | 2028-07-23 | 14 | 2024-03-06 | CTF 80
PM6 | SACAGAWEA | T-AKE 2 | VR (Z) MSC | ACTIVE | 2028-07-10 | 2028-08-06 | 28 | 2024-05-10 | C7F
PM6 | MEDGAR EVERS | T-AKE 13 | VR (Z) MSC | ACTIVE | 2028-07-10 | 2028-07-23 | 14 | 2024-05-22 | C6F
PM2 | ABLE | T-AGOS 20 | VR (Z) MSC | ACTIVE | 2028-07-10 | 2028-08-23 | 45 | 2025-08-08 | C7F
PM8 | CITY OF BISMARCK | T-EPF 9 | VR (Z) MSC | ACTIVE | 2028-07-10 | 2028-07-30 | 21 | 2025-08-19 | C7F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2028-07-10 | 2028-07-23 | 14 | 2025-09-21 | C3F
PM3 | SGT WILLIAM R BUTTON | T-AK 3012 | VR (Z) MSC | ACTIVE | 2028-07-15 | 2028-07-29 | 15 | 2025-07-25 | C7F
PM1 | GUADALUPE | T-AO 200 | VR (Z) MSC | DEFERRED | 2028-07-15 | 2028-07-22 | 8 | 2025-02-21
PM2 | BRUCE C HEEZEN | T-AGS 64 | VR (Z) MSC | ACTIVE | 2028-07-17 | 2028-08-03 | 18 | 2025-07-02 | C6F
PM3 | JOHN L CANLEY | ESB 6 | VR (Z) MSC | ACTIVE | 2028-07-24 | 2028-08-07 | 15 | 2025-08-27 | C7F
PM3 | ROBERT E SIMANEK | ESB 7 | MTA (MSC) | ACTIVE | 2028-08-01 | 2028-09-15 | 46 | 2025-07-25 | C6F
PM3 | MIGUEL KEITH | ESB 5 | VR (Z) MSC | ACTIVE | 2028-08-01 | 2028-08-15 | 15 | 2025-07-25 | C7F
PM3 | DAHL | T-AKR 312 | VR (Z) MSC | ACTIVE | 2028-08-01 | 2028-08-15 | 15 | 2025-07-25 | C7F
PM3 | SEAY | T-AKR 302 | VR (Z) MSC | ACTIVE | 2028-08-01 | 2028-08-14 | 14 | 2025-07-25 | C7F
PM4 | EMORY S LAND | AS 39 | MTA (MSC) | ACTIVE | 2028-08-02 | 2028-10-07 | 67 | 2025-09-03 | GUAM
PM4 | MERCY | T-AH 19 | VR (Z) MSC | ACTIVE | 2028-08-02 | 2028-10-07 | 67 | 2025-07-22 | C3F
PM6 | CESAR CHAVEZ | T-AKE 14 | VR (Z) MSC | ACTIVE | 2028-08-07 | 2028-08-20 | 14 | 2023-07-09 | C7F
PM1 | JOSHUA HUMPHREYS | T-AO 188 | VR (Z) MSC | ACTIVE | 2028-08-07 | 2028-08-21 | 15 | 2025-08-07 | CTF 80
PM6 | WASHINGTON CHAMBERS | T-AKE 11 | VR (Z) MSC | ACTIVE | 2028-08-14 | 2028-08-27 | 14 | 2023-07-09 | C3F
PM2 | WATERS | T-AGS 45 | VR (Z) MSC | ACTIVE | 2028-08-14 | 2028-08-31 | 18 | 2025-07-10 | CTF 80
PM2 | SBX-1 | SBX 1 | VR (Z) MSC | ACTIVE | 2028-08-15 | 2028-10-24 | 71 | 2025-08-08 | C3F
PM4 | CHEROKEE NATION | T-ATS 7 | VR (Z) MSC | ACTIVE | 2028-08-24 | 2028-09-06 | 14 | 2025-07-28 | C5F
PM8 | GUAM | HST 1 | VR (Z) MSC | ACTIVE | 2028-08-25 | 2028-09-04 | 11 | 2025-07-30 | C7F
PM2 | HENSON | T-AGS 63 | VR (Z) MSC | ACTIVE | 2028-08-28 | 2028-09-15 | 19 | 2025-07-02 | C7F
PM1 | YUKON | T-AO 202 | VR (Z) MSC | ACTIVE | 2028-08-28 | 2028-09-11 | 15 | 2025-08-08 | C7F
PM8 | PUERTO RICO | T-EPF 11 | VR (Z) MSC | ACTIVE | 2028-08-28 | 2028-09-17 | 21 | 2025-08-15 | C7F
PM6 | LEWIS AND CLARK | T-AKE 1 | VR (Z) MSC | ACTIVE | 2028-08-28 | 2028-09-24 | 28 | 2024-12-30 | C7F
PM4 | SOLOMON ATKINSON | T-ATS 12 | VR (Z) MSC | ACTIVE | 2028-08-29 | 2028-09-11 | 14 | 2025-07-11 | C3F
PM3 | PFC DEWAYNE T WILLIAMS | T-AK 3009 | VR (Z) MSC | ACTIVE | 2028-08-30 | 2028-09-13 | 15 | 2025-07-25 | C7F
PM6 | WILLIAM MCLEAN | T-AKE 12 | VR (Z) MSC | ACTIVE | 2028-08-31 | 2028-09-13 | 14 | 2024-12-20 | CTF 80
PM1 | GUADALUPE | T-AO 200 | ROH (MSC) | ACTIVE | 2028-09-01 | 2028-12-10 | 101 | 2025-01-17 | C3F
PM3 | HERSHEL WOODY WILLIAMS | ESB 4 | VR (Z) MSC | ACTIVE | 2028-09-01 | 2028-09-15 | 15 | 2025-07-25 | C6F
PM3 | 1ST LT JACK LUMMUS | T-AK 3011 | VR (Z) MSC | ACTIVE | 2028-09-01 | 2028-09-14 | 14 | 2025-07-25 | C7F
PM1 | TIPPECANOE | T-AO 199 | VR (Z) MSC | ACTIVE | 2028-09-04 | 2028-09-18 | 15 | 2025-08-08 | C3F
PM2 | IMPECCABLE | T-AGOS 23 | VR (Z) MSC | ACTIVE | 2028-09-04 | 2028-10-18 | 45 | 2025-08-08 | C7F
PM8 | APALACHICOLA | T-EPF 13 | VR (Z) MSC | ACTIVE | 2028-09-06 | 2028-09-26 | 21 | 2025-08-19 | CTF 80
PM8 | POINT LOMA | T-EPF 15 | VR (Z) MSC | ACTIVE | 2028-09-06 | 2028-09-26 | 21 | 2025-08-15 | C7F
PM4 | BILLY FRANK JR | T-ATS 11 | VR (Z) MSC | ACTIVE | 2028-09-08 | 2028-09-21 | 14 | 2025-07-28 | C7F
PM1 | EARL WARREN | T-AO 207 | VR (Z) MSC | ACTIVE | 2028-09-10 | 2028-09-23 | 14 | 2025-02-21 | C7F
PM3 | PILILAAU | T-AKR 304 | VR (Z) MSC | ACTIVE | 2028-09-14 | 2028-09-27 | 14 | 2025-07-25 | C7F
PM8 | CODY | T-EPF 14 | ROH / DD (MSC) | ACTIVE | 2028-09-18 | 2028-12-16 | 90 | 2025-07-25 | C7F
PM6 | MATTHEW PERRY | T-AKE 9 | VR (Z) MSC | ACTIVE | 2028-09-18 | 2028-10-01 | 14 | 2025-03-20 | C7F
PM6 | RICHARD E BYRD | T-AKE 4 | VR (Z) MSC | ACTIVE | 2028-09-18 | 2028-10-01 | 14 | 2025-09-21 | C3F
PM2 | VICTORIOUS | T-AGOS 19 | MTA (MSC) | ACTIVE | 2028-09-24 | 2028-11-22 | 60 | 2025-08-08 | C7F
PM1 | LUCY STONE | T-AO 209 | VR (Z) MSC | ACTIVE | 2028-09-25 | 2028-10-08 | 14 | 2025-09-25 | C7F
PM4 | GRASP | T-ARS 51 | DECOM AVAIL (MSC) | ACTIVE | 2028-10-01 | 2028-10-31 | 31 | 2025-08-11 | C3F
PM4 | MOUNT WHITNEY | LCC 20 | MTA (MSC) | ACTIVE | 2028-10-01 | 2028-11-15 | 46 | 2025-08-11 | C6F
PM8 | GUAM | HST 1 | ROH / DD (MSC) | ACTIVE | 2028-10-01 | 2028-12-15 | 76 | 2025-07-30 | C7F
PM3 | LEWIS B PULLER | ESB 3 | VR (Z) MSC | ACTIVE | 2028-10-01 | 2028-10-15 | 15 | 2025-07-16 | C5F

## MSC certs
|  | As of 28 Oct2022, all MSC certs have been updated IAW the new Readiness Manual https://navy.deps.mil/sites/msc/QMS/SMS/N04.04A.3502.1-Q.pdf | [5 empty] | New TYCOM view and new due dates as of 30 Sep 2022
Event | Links | Summary | Time | Underway | Crew Involved | Cargo Ops | Shipyard | Details | POCs | POC office | Info comes from_______? | 1 hr | Yes
ABS5YRCLASSCERT ABS5YRCLASSCERTDUE DNVGL DNVGL Due | ABS | American Bureau of Shipping Instruction: https://ww2.eagle.org/en.html Periodicity: 5 years (and annuals) | [5 empty] | Some ships are covered under Det Norske Veritas and Germanischer Lloyd DNVGL. The DNVGL Due Date will populate as an ABS 5 Year Due Date http://vesselregister.dnvgl.com/vesselregister/vesselregister.html | Rumble (ABS Eagle) (DNVGL) | ABS | ABS website ( or DNVGL) maybe from PM
ARQ ARQ Due | ARQ | Aviation Readiness Qualification: MSC training for flight deck personnel Instruction: MSFSCINST 3700.1 Periodicity: 24 months. (ARQ inspectors target 18 month renewal) | 3 days | Yes | Yes | No | No | Underway: When possible we do the ARQ in conjunction with the AVCERT week. When doing an ARQ by itself or a midterm ARQ (where we also give the master a look at his facility), we plan for 3 days. These can be done underway. Crew Involved: ARQ is for the people, AVCERT is for the gear. | timothy.p.smith5.civ@us.navy.mil patrick.j.halinski.civ@us.navy.mil mark.l.henson2.mil@us.navy.mil richard.t.hejnal.civ@us.navy.mil | N04T | Email from N04T aviation guys | 1 to 5 | No
ATA-I ATA-R ATA-T ATA Due | ATA-I ATA-R ATA-T | Afloat Training Availability-Initial (ATA-I). Unit-level training is conducted following a vessel’s ROH (or as indicated in Fg model). Previously known as ATT-Program (ATT-P) Afloat Training Availability–Refresher (ATA-R). Unit-level training is conducted following a vessel’s MTA (or as indicated in Fg model). Formerly known as ATT–Refresher (ATT-R) Afloat Training Availability–Tailored (ATA-T). Unit or individual training conducted solely at the Master’s discretion to correct shortfalls in crew training. Formerly known as Tailored Team Training (TTT) Instruction: COMSCINST 3502.2, Appedix G | 11 - 5 Days depending on Class of Vessel and Event Type. See "Scheduling Length" in DETAILS tab. | Yes | Yes | No | No | Underway: Can be performed while U/W but only while in transit to a location, vessel is not ready for tasking until the ATT is completed. Crew Involed: Yes, Training is considered the ship’s mission during assigned ATA days, and shall not overlap with other events including, but not limited to, loading cargo, shipyard maintenance, audits, and inspections. Scheduling Length: ATA-I T-AOE / AS / LCC – 11 days (including weekends and holidays) T-AO / AKE / ESB / ARC – 10 days (including weekends and holidays) T-EPF / ATF / ARS / ATS – 7 days (including weekends and holidays) ATA-R T-AOE / AS / LCC – 8 days (including weekends and holidays) T-AO / AKE / ESB / ARC – 7 days (including weekends and holidays) T-EPF / ATF / ARS / ATS – 5 days (including weekends and holidays) | Afloat Training Director coy.m.adams.civ@us.navy.mil Director Training Center East robert.j.farmer.civ@us.navy.mil ATT-East peter.a.cesarski.civ@us.navy.mil ATT-West michael.w.keller3.civ@us.navy.mil | N12 | Email from Shannon, Anton or msg traffic | 5 to 10
AVCERT AVCERT Due | AVCERT | Aviation Certification: NAVAIR flight deck certification Instruction: MSFSCINST 3700.1 Periodicity: USNS - 36 months or after ROH>70days USS - 24 months | 5 days | No | Yes | No | No | Time requirement: 5 days Underway: AVCERTS are done in port Crew Involved: Crew is involved for demonstrating and correction of items for AVCERT | timothy.p.smith5.civ@us.navy.mil patrick.j.halinski.civ@us.navy.mil mark.l.henson2.mil@us.navy.mil richard.t.hejnal.civ@us.navy.mil | N04T | Msg traffic | 10 to 24
BRM Training BRM Training Due | BRM | Bridge Resource Management: Instruction: for AO - COMSCINST 3501.4B, for AS - MSC/SUBPAC 5000, for LCC - COMSC/COMNAVSURFLANT 5239, for ESB - COMSCINST/COMNAVSURFLANTINST 3000.1 (11JUN18) Periodicity: Twice every 5 years, not to exceed 30 months | 2 days | No | Yes | Yes | Yes | Crew involved is typically: Master, Mates, Navy CO, Navy XO. Can be performed in S/Y if mate billets are filled Time requirement: 2 days | cody.l.holliday.civ@us.navy.mil at MUTC or Area Commands and PMs |  | MUTC/Ship/Area Command/PM | 24 to 36
Crane Audit (nomenclature in ABS)/ Cargo Gear (MSC nomenclature) | Cargo Equip | Cranes, Ramps, Sideports: Instruction: https://ww2.eagle.org/en.html Periodicity: varies by equipment | [5 empty] | Expiry dates are taken from ABS Eagle, Certificates tab | ABS Eagle | ABS | ABS website maybe from PM
USCG COI USCG COI DUE | COI | USCG Certificate of Inspection Instruction: COMSCINST 4730 USCG COI, https://cgmix.uscg.mil/PSIX/PSIXSearch.aspx Periodicity: 5 years (and annuals) | [5 empty] | https://cgmix.uscg.mil/PSIX/PSIXSearch.aspx | USCG PSIX | USCG | PSIX website or OCI reports
CURVE CURVE Due | CURVE | Certification for UnRestricted Vessel Employment: Instruction: COMSCINST 3502.2, Appedix D Periodicity: 30 months | [7 empty] | N04T |  | 36 to 48
ISA ISA Due | ATPR | Individual Ship Assessment: Conducted by Area Commands Instruction: COMSCINST 5530.3F Periodicity: 3 years (No ISA for USS ships) | 2 days | No | Yes | No | No | Cargo ops: Typically the Chief Mate is the ISA lead Time requirement: 2 days (No ISA for USS ships) | andrew.m.kirkland2.civ@us.navy.mil michael.j.azevedo2.civ@us.navy.mil | N34 | MSC Portal or Mike Azevedo | 48 +
ABSSMCAUDIT ABSSMCAUDITDUE ABSSMCINTAUDIT ABSSMCINTAUDITDUE | ISM ext | International Safety Management Audit (External): (also listed as "ABS SMC") Overview: An ISM Audit (Internal or External) is an audit (not inspection) which deals with sampling the Safety Management System to see if vessels are in compliance. Instruction: https://ww2.eagle.org/en.html , MSC SMS 12.1-002-SQ Revision 1.1 Periodicity: 5 years | 2 days | Yes | Yes | Yes | No | Paragraphs 13.7 and 13.8 of the ISM code require external audits to be conducted in order to receive and maintain a Safety Management Certificate (SMC). The first external audit is to verify that the Command is operating in accordance with the approved Safety Management System prior to issuing a SMC. An intermediate verification audit is required between the 2nd and 3rd year. A renewal audit is required between the 4th and 5th year. These audits are conducted by either the USCG or the American Bureau of Shipping for MSC Ships | ABS Eagle as primary daphanie.r.brown.civ@us.navy.mil | N75 | ABS Eagle, PSIX, DNVGL websites or Daphne Brown | 48 +
ISM INTERNAL AUDIT ISM INTERNAL AUDIT Due | ISM int | International Safety Management Audit (Internal): Instruction: MSC SMS 12.1-002-SQ Revision 1.1 Periodicity: 12 months | 2 days | Yes | Yes | Yes | No | Paragraphs 12.1 and 12.2 of the ISM code require internal safety audits on board and ashore at intervals not to exceed twelve months. The purpose of the audit is to verify whether safety and pollution-prevention activities comply with and to periodically evaluate the effectiveness of the Safety Management System (SMS). | john.d.szczecinski.civ@us.navy.mil | N75 | Daphne Brown | 1
MRI MRI Due | MRI | Medical Readiness Inspection: Instruction: MRI QMS N013.91.2.Q Periodicity: 36 months | 2 days | Yes | Yes | No | No | Time requirement: MRI normally takes 2 business days minimum Underway: Yes it can be accomplished underway; Crew Involved: MSO is the only one involved on MSO Ships, MDR/Master/CHENG/Cook/Pursur/Training Officer involved onboard MDR Platforms; Cargo Ops: If MSO/MDR is part of cargo ops then that will impair MRI conductance; S/Y: Event does not need to be completed at/during shipyard but is dependent on MRI due date and specific deployment status of vessel involved. | davitri.brooks1@navy.mil stephanie.minix@navy.mil randy.boucher@navy.mil beau.j.bostwick.mil@health.mil (HMCS) | N02H | Force Employment slides (Tues 1000)
OCI OCI Due | OCI | Onboard Condition Inspection: comparable to SMART / INSURV Instruction: COMSCINST 4700.18 Periodicity: 12 months +/-3months | [6 empty] | steven.b.frazier2.civ@us.navy.mil ronald.r.costain.civ@us.navy.mil | N73 | Email from N73 | 1
PEVI PEVI Due | PEVI | Port Engineer Visual Inspection: Instruction: N7 Periodicity: 12 months | [6 empty] | steffen.j.wojeck.civ@us.navy.mil | N7 | SAMM or email from N7
SESI SESI Due | SESI | Shipboard Explosive Safety Inspection: Used to be Conventional Ordinance Safety Review Instruction: COMSCINST 8023.2B Periodicity: 36 months | 5 days | No | Yes | Yes | No | Time requirement: The SESI inspection team requires 5 work days. Underway: SESI will not be conducted while the ship is under way Crew Involved: Only the ship's crew that is involved in handling explosive Cargo Ops: SESI is conducted in port only so if no ordnance cargo is being handled on the pier it should not affect the inspection. SESI will not be conducted during any scheduled ordnance handling evolution. S/Y: SESI will not be conducted while the ship is in a shipyard period | richard.f.hart.civ@us.navy.mil lester.l.hood.civ@us.navy.mil christopher.a.perkins4.civ@us.navy.mil | N4 | ask for XLS from N47
SMART SMART Due | SMART | Ships Material Assessment and Readiness Training: comparable to Navy INSURV Instruction: COMSC 4730.4A Periodicity: 3 years | 10 days | Yes | Yes | No | Yes | Time requirement: 5 days (pre-SMART 4 days prior) Note: Per SMS Memo#: 164 Date: 17 Sep 2020, SMART periodicity is 3 years. Prior to this memo, the interval was 5 years. All exisiting expiration dates will remain in place. The 3 year periodicity will be applied to all SMART completions. | steven.b.frazier2.civ@us.navy.mil brendan.e.mccauley.civ@us.navy.mil | N73 | Email from N73
SQTS SQTS Due | SQTS | Ship Qualification Trial: UNREP training Instruction: COMSCINST 3502.2, Appedix O Periodicity: when a ship leaves ROH | [5 empty] | MUTC = MSC UNREP Training Center UNREP, CONREP, VERTREP MTP: Mission Training Period = time set asside for vessel/type specific training | Cody.l.holliday.civ@us.navy.mil robert.j.farmer@navy.mil | N16 | PM or MUTC | 1
SRTTE SRTTE Due | SRTTE | Surface Rescue Team Training & Evaluation : Instruction: COMSCINST 3130.2C Periodicity: 24 months | 4 days | No | Yes | No | No | Material condition inspection of the following: Individual Rescue Swimmer equipment, Rescue Boat & J-Bar/Forecastle rescue equipment. Administrative inspection: Ship's SAR Binder, Rescue Equipment Maintenance Binder, and Rescue Swimmer Training Folders. Pool and open water training and practical applications | melvin.fai.civ@us.navy.mil Karl.summers@navy.mil | N04T | Email from Mel | 1
TACAN TACAN Due | TACAN | Tactical Air Navigation: Navigational aid certification Instruction: NAVAIR AE TACAN-GYD-000 Inst & Proc for Cert Periodicity: 18 months (540 days) | [5 empty] | Conducted by SESEF, certifies the ships navigation aid for aviation assets |  | N04T | Sometimes it is included in an ARQ letter. Might have to go to SESEF sites
T-EPF Type Rating Cert | T-EPF Type Rating Cert | T-EPF Type Rating Certification: Vessel specific training for T-EPF crews, approx 21 days. Can be conducted on any EPF hull Instruction: COMSCINST 3502.2, Appendix R Periodicity: 2 years, tracked as individual CIVMAR qual | 21 days | Yes | Yes | no | no |  | nedra.j.johnson.civ@us.navy.mil | N1
VSA VSA Due | VSA | Vessel Self Assessment Instruction: COMSCINST 3502.2, Appendix H Periodicity: GOGO -Once per calendar year (but not needed in SMART year) GOCO -as needed per OCI results | 30 days | min 1 day | yes | yes | no | The VSA is done in addition to normal operations being conducted in that time period, and does require underway time (minimum of approximately one day). | steffen.j.wojeck.civ@us.navy.mil | N7 | SAMM or email from N7 | 1
YELLOW GEAR DUE | YGD | Yellow Gear Due Instruction: ESSM, Office of the Supervisor of Salvage (SUPSALV) within the Naval Sea Systems Command Periodicity: Typically 12 months. Individual systems listed at: https://www.navsea.navy.mil/Home/SUPSALV/ESSM/Salvage-Equipment/ | 5 days |  |  |  |  | Yellow gear is a compliment of salvage, battle damage, mooring and de-beaching equipment carried aboard the USNS Salvor and Grasp. | jon.t.schauwecker.civ@us.navy.mil PM4 Michael.a.woods1.mil@us.navy.mil PM4 richard.a.thiel@navy.mil SUPSALV paul.f.hankins@navy.mil SUPSALV | PM4 | Michael.a.woods1.mil@us.navy.mil
| FIWT | Fleet Integrated Warfare Training (akin to COMPTUEX) | [9 empty] | 1
| MTP | Mission Training Period. Time for hull-specific training (T-AGOS, T-AGS mission related training) | [9 empty] | 1
| ROH | Regular OverHaul | [9 empty] | 1
| MTA | Mid Term Availability | [9 empty] | 1
| VR | Voyage Repair
| ORA | Operational Readiness Assessment
| BV OPS | Blocking Vessel Operations
| FMEA DP | Failure Mode and Effects Analyses Dynamic Positioning
| RFS | Ready For Sea
Note on D2: Roberts, Thomas J LT USN CTF-53 BAHRAIN: Number of hours it will take to complete inspection
Note on E2: Roberts, Thomas J LT USN CTF-53 BAHRAIN: Can inspection be done while ship is underway? If not, it will be assumed the inspection must be completed at a dock or ship yard.
Note on F2: Roberts, Thomas J LT USN CTF-53 BAHRAIN: Does the ship's crew need to be involved in the inspection?
Note on G2: Roberts, Thomas J LT USN CTF-53 BAHRAIN: Can Cargo Ops be conducted while inspection is taking place
Note on H2: Roberts, Thomas J LT USN CTF-53 BAHRAIN: Does inspection need to be completed at a ship yard?
Note on C18: MSC SESI for: AGOS, AKE, AO, AOE, ARS, ATF, EPF, ESD SURFOR SESI for: AS, ESB No SESI for: AG, AGM, AGS, AGSE, AH, AK, AKR, AOT, ARC, HST, LCC, SBX